### Global Shelter Cluster Shelter Projects Working Group

### Dial in call 20 September 2018

### Meeting minutes

Date and venue: 20 September 2018 – Dial in call, 14:00-14:45 (GMT+1)

Participants:

Mohamed Hilmi (Interaction),	 			Chiara Jasna Vaccaro (DRC),

Alberto Piccioli (IOM),					Step Haiselden (CARE International UK) Charles Parrack (Cendep),				Renee Wynveen (UNHCR),

Loren Lockwood (CRS),					Boshra Khoshnevis (IOM).

Apologies: Jim Kennedy (independent), Joseph Ashmore (IOM), Sandra d’Urzo (IFRC), James Schell (IMPACT).

### Agenda

- Recap of contributions to date for the next edition;

- Update on the submissions;

- Discuss agenda for session at the GSC meeting;

- Agree on timeline for peer review and development of the publication;

- AOB: Locations for future workshops, translations, dissemination.

### Actions

- ACTION (pending): DRC, CARE, Cendep and IFRC to confirm their contributions to the next edition.

- ACTION (ongoing): IOM to collect the first draft of case studies.

- ACTION (pending): IOM to share case study drafts for first round of peer review and all working group members to participate with reviewing approx. 3-4 case studies each.

- ACTION (done): IOM to ask for two sessions and finalise agenda for WG sessions at GSC meeting.

- ACTION (ongoing): IOM to follow up on participation of the working group in the upcoming UK Shelter Forum.

### Discussion

Recap of contributions to date for the next edition:

- CARE also volunteered for proof reading and will confirm their contribution to formatting.

- Cendep is not likely to receive funding for long-term impact studies within the timeline for this edition, but is still looking for options.

- DRC will confirm their contribution to printing. Between 5-10k USD.

- UNHCR will follow-up on their pending case studies and opinion pieces.

- Interaction can contribute to workshops costs (eg venue) and can follow up on possible funding for translations.

Update on the submissions:

First draft of 17 case studies (out of 39) are received. The submission deadline in some cases is extended until September 30th.

Information on the number of cases received by country is shared within the WG. There is still time to directly connect organizations if a specific response which is worth including is currently missing.

Discuss agenda for session at the GSC meeting:

There were no comments on the draft agenda shared before the call.

The working group will convene in Geneva during the GSC meeting.

IOM will request a second session at the GSC meeting on October 3rd to be more flexible on presentations and participation of WG members. This will also allow to include a discussion on long-term impact studies requested by Cendep.

Agree on timeline for peer review and development of the publication:

After the GSC meeting in October, the second week of October, case studies will be sent out for the first round of peer review. Considering the number of cases and WG members, the group agreed on the allocation of approx. 4 case studies to each member for review. Members are committed to do the reviews, in two rounds, overall by the end of December. Specific deadlines will be communicated with each reviewer. There may be two requests for review within this timeframe (i.e. two rounds), to account for case studies submitted late or for those which require a second review.

Members are asked to communicate if they wish to review any specific case study. Loren/CRS is happy to support with reviewing Nepal case studies alongside with writing an overview for these.

AOB:

- Translations:

IOM have translated 6 case studies into Spanish and 2 into Arabic. These are in the formatting process. Waiting to receive 4 case study translations in French.

- Thematic Booklets:

DRC asked for copies of the East Africa edition.

- Workshops:

CRS suggested participation of Shelter Projects in the UK shelter forum which happens in November.  IOM to follow-up.

IOM updated the group of the possibility to hold a workshop in Indonesia if they confirm hosting the next Asia shelter forum in 2019.

Next meeting to be held in Geneva on the 3th of October (GSC meeting).