Mozambique Shelter Cluster

ShelterCluster.org

Coordinating Humanitarian Shelter

# National SITREP 4

# Cylcone IDAI

DATE: 06.04.2019

## Key points

- Current data puts the number of houses damaged / destroyed as 216,000 houses. This is twice the number of houses originally estimated in the appeal, leaving a significant gap.

- Distributions are in process with over 83,000 people assisted to date, 29,000 tarpaulins distributed.

- Partners are unable to deliver full household kits due to lack of items, in stock and in pipeline.

- Current pipeline gap of 61,000 tarpaulins, based on original appeal target. This calculation may change with revised damage data.

- Distribution capacity is limited. The new focus is on quality of programming and Operational partners are urgently required to scale up ability to distribute emergency shelter and NFI.

- Airlift operations are scaling back and renewed focus is on ground transportation wherever possible.

- Road access is improving, markets are recovering and affected populations are beginning their own self recovery where they have land and capacity to do so, but many remain cut off from roads, or displaced in evacuation centres and unable to return.

- Active CCCM sub-cluster is working in relocation sites and transit camps to establish safe living spaces and to ensure that sites are habitable before schools and other collective centres are closed.

## Overall situation analysis

Category 4 cyclone Idai made landfall on 14/03/19. High winds damaged and destroyed houses and infrastructure, and the ensuing flooding caused major additional damage and displacement. Although waters are receding, over 15,000 houses remain flooded.

As of 05/04/2019, The Mozambique National Institute for Disaster Management (INGC) damage data puts the total number of households damaged or destroyed at 103,537 partially destroyed, 97,424 totally destroyed, 15.784 flooded, or a total of 216,000 HH damaged / destroyed.  Shelter damage assessment lead by the Government of Mozambique is ongoing.

Based on earlier estimates, the cluster is targeting 475,000 people in 87,500 households. This is based on 80,000 households targeted in the Flash appeal and 7,500 households in the Red Cross appeal.

## 3. 	Activity updates

- Working with INGC, distributions are conducted facilitated by airlift (working with logcluster/WFP), by road or by boat. The largest delivery has been by road, a trend that is set to continue as operations scale up, and funding for air assets falls.

- The full cluster 4w is published here. https://bit.ly/2I3zftc

Partners are encouraged to look at it to check if their activities are correctly reported.

- 450,000 mosquito nets have been released by the ministry of health.

## 4.	Achievements

- Assisted 93,752 people (17'437 HH) to date, receiving 19,000 tarpaulins

- Established Cluster coordination cell in Beira co lead by INGC, IOM and CVM/IFRC

- Active CCCM sub cluster is coordinating development work on camp sites in Beira city. has mapped collective sites, and developed transit/ relocation camps in Beira and is monitoring needs.

## 5. Beira pipeline request process:

The following is required to release stock from the common pipeline:

Consignee name:

Consignee organization:

Consignee contact number:

Preferred Delivery date:

Preferred Delivery time:

Delivery address:

Notes on access:

Road access conditions:

Number of HH:

Item:

Confirm coordinated with local authorities:

## Note: it is preferable to deliver direct to site, to ensure that items are delivered to affected populations and do not remain stuck in warehouse, unless there is a clear need to move to consolidate on warehouses. Agencies should have a proven track record of working with international partners and regularly attend cluster meetings. For agencies first distributions, smaller targeting numbers of people are encouraged.

## 6.	Challenges, issues and constraints

The major constraints are with data for planning and targeted purposes, rapid scale up and implementation capacity

There are insufficient materials in the pipeline to meet needs and there remain delivery gaps in the pipeline for all items.

## 7.	Advocacy messages

Prioirity items:

- Tarpaulins and rope (pipeline Gap at least 61,000 tarpaulins)

- Tool kits

- Blankets (pipeline Gap at least 33,000 tarpaulins)

- Sleeping mats

- Buckets

- Solar lamps

Based on the initial cluster target of 87,500 households in need of shelter assistance (but noting revised damage data doubling the target population), we see the following critical gap in the most basic of life saving shelter assistance in the next two months:

- Gap of 61,360 x 6mx4m plastic tarpaulins if provided at 2 per household.

- Plastic Tarpaulins: 113,640 in pipeline / committed: target for 85,000 households, 170,000.

- All other items are insufficient supply

- Although significant efforts have been put in by all partners, and it should be noted that the targets may change as further assessment data comes in, support is required to address these gaps.

# 8. 	Emergency Shelter Coordination

All Shelter documents related to the response can also be found at https://www.sheltercluster.org/response/mozambique-tropical-cyclone-idai-2019

| Co-Coordinators Maputo: |  |
| --- | --- |
| Nuno Nunes moz.coord2@sheltercluster.org | Francesco Monteiro moz.coord3@sheltercluster.org +258 84 500 7662 |
| Coordinators Beira |  |
| Jim kennedy IOM Moz.Coord1@sheltercluster.org |  |
| Information management |  |
| Mohamed Bakr - Beira Mbakr@iom.int | Brian Mcdonald – Maputo Moz.IM1@sheltercluster.org |
| Technical coordinator |  |
| Lucio cocconi Moz.Tech1@sheltercluster.org |  |
| CCCM Camp management, camp coordination |  |
| ABIS Rafael rabis@iom.int |  |

# Pipeline analysis

| agency | status | family tents | tarpaulins | kitchen sets | toolkits | Blanket | solar lamps |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Tendas Casas | Lonas 4mx6m | Kits de cozinha | toolkits | Mantas |  |
| dfid / IOM | Arrived | 100 | 18900 |  |  | 3200 | 1000 |
| Swiss / IOM | Arrived |  | 2000 |  | 500 |  |  |
| CVM | Arrived |  |  |  |  |  |  |
| CVM | Arrived | 55 | 9040 | 5806 | 3091 | 16098 |  |
| IOM | Arrived |  |  |  |  |  |  |
| CRS/CARITAS | Arrived |  | 1500 |  |  |  |  |
| Plan | Arrived |  | 1200 |  |  |  |  |
| SOS attitude | Arrived | 20 |  |  |  |  | 784 |
| CVM/IFRC | Arrived | 70 | 9170 | 6776 | 4500 | 18000 | 7500 |
| USAID-OFDA/IOM | Arrived |  | 1800 | 1800 |  | 3600 |  |
| Italy / IOM / INGC | Arrived | 100 | 300 | 100 |  | 1000 |  |
| Samaritans purse | Arrived |  | 8500 |  |  | 4800 |  |
| Consortium | Arrived |  | 930 |  | 16 | 55 |  |
| subtotal | Arrived | 245 | 53340 | 14482 | 8107 | 46753 | 9284 |
| la reunion / CVM | Pipeline/ procured |  | 6000 |  | 3000 |  |  |
| IFRC | Pipeline/ procured |  | 6000 |  | 1000 |  |  |
| CRS/CARITAS | Pipeline/ procured |  | 8000 |  |  |  |  |
| UNHCR | Pipeline/ procured | 420 | 300 | 2000 |  | 10000 | 1000 |
| Cosaca | Pipeline/ procured | 1049 |  |  | 3.970 |  |  |
| OFDA/IOM/WV | Pipeline/ procured |  | 18000 | 19.020 | 1.800 | 60.400 |  |
| CHEMO Consortium | Pipeline/ procured |  | 12000 |  |  |  |  |
| subtotal | Pipeline/ procured | 1469 | 50300 | 21020 | 9770 | 70400 | 1000 |
| in country plus pipeline |  | 1714 | 103640 | 35502 | 17877 | 117153 | 10284 |
| IOM |  |  |  |  |  |  |  |
| CHEMO Consortium | planned |  | 10000 |  |  | 20.000 |  |
| subtotal | planned |  | 10000 | 0 | 0 | 20000 |  |
| total |  | 1714 | 113640 | 35502 | 17877 | 137153 | 10284 |
| target for 87500 hh |  |  | 175000 | 87500 | 87500 | 175000 | 87500 |
| gap |  |  | 61360 | 51998 | 69623 | 37847 | 77216 |