Location: 	Baghdad – UNHCR meeting room in D2

Time: 		12:35 am – 01:35 pm

Present: 	Sub-National S-NFI Cluster (Michel Tia); National CCCM Cluster (Marguerite Nowak); Blumont (Ali Tahseen); Caritas (Ali Aied); IOM (Drew Craig, Munir Ali); Mercy Hands (Hussam Jabbar); UNHCR (Layth Al-Azzawi); Osamu Ahmad (UIMS)

WebEx:               UNHCR conference room BGD-IZ; Baghdad RICC 3;

The following are additional points to the PowerPoint presentation of the meeting.

| Agenda Item | Key Points | Action points |
| --- | --- | --- |
| - Review of action points from minutes of previous meeting | The 23rd Jan.19 meeting minutes was approved and the action point that require bilateral follow up are: - CRS – to update the WDS Data Collection Tool based / share their proposed locations of shelter rehabilitation with shelter cluster to prevent the duplication. Key issues – Assessments (plan, ongoing completed) - Collect partners assessments reports, raw data, maps whenever available. - Collect partners 2019 assessment plan. | Sub-national cluster coordinator to follow up on those. |
| - Key issues and Partners updates - War Damaged Shelter: who is doing what where and when - Plan / Ongoing - Assessments - Rehabilitation – Reconstruction - Camp closure / Camp consolidation (been covered in CCCM meeting) - Tents replacements – key concern and way forward - Ongoing / planned NFI response (including winter response) - 2019 overall assessments (planned, ongoing, completed) | Please refer to the PowerPoint presentation of the meeting: - The Iraq Housing Rehabilitation Overview (as of 20th Feb.19) was presented, with focus on Centre and South. Partners were encouraged to share all their related interventions, straighten the coordination to avoid overlapping in field. - (been covered in CCCM meeting) - Tent replacement is a key concern for most of the camp mangers as they have been expressing the need. Agreed way forward is to first collect tent related issues in the CCCM FSMT. Then, from that overview, analysis and further verification can be done to confirm that need and advocate for the replacement. - In Centre and South, partners have almost completed their winter distributions. The very few remaining gaps or complains from the IDP Call Centre are covered after thorough assessments, to avoid re-serving same beneficiaries. IOM and UNHCR have confirmed their availability to cover pending winter need if any. - Available resources Iraq Assessment Tools and Guidance: https://www.humanitarianresponse.info/en/node/168141 - Iraq Common Database of Indicators (CDI) - Catalogue of Assessment Tools Iraq Assessment Registry: https://www.humanitarianresponse.info/en/operations/iraq/assessments | Key contact to liaise with: hoveen.yaseen@un.org im3.iraq@sheltercluster.org CCCM to Provide a brief presentation on the best practices and lessons learnt from the camp closure. Camp managers to contribute to the ongoing data collection process in the CCCM FSMT. Partners were encouraged to share their 2019 assessments data: For completed assessments: please share the report and raw data. For planned / ongoing assessments: please use the online form that was shared for the purpose. |
| - AOB | The Sub-National CCCM & S-NFI Clusters monthly meeting plan was presented and approved; - Frequency of the meetings was agreed for every 4 weeks, - Meetings will be starting at 10:00 am. |  |