Shelter/NFI Cluster Coordination Meeting, Dahuk

Location: 		BRHA Conference Room, Dahuk

Date and time: 		2nd July 2019

Attendance:		ACTED, BRHA, CCCM Cluster, SNFI Cluster, Medair, OCHA, and UNHCR

| Agenda Item | Key Points | Actions |
| --- | --- | --- |
| General SNFI Update | - SNFI will be conducting a number of shelter-related trainings in Dohuk – more updates and invitations to follow. - SNFI Cluster Kobo form for kerosene distribution has been shared with camp managers and should be consistently used to track distributions in camps. We are working with MoMD new management to get regular updates on distributions and kerosene. Kerosene for cooking information is also fed to us through the Kerosene Distribution Kobo form collected from CM and shared with us by BRHA. - SNFI Cluster 4W tool on Activity Info has been presented. Currently 0 partners in Dohuk have reported planned activities or assessments. - SNFI cluster continues to advocate for critical MoMD tent replacement with senior management and donors. | - Camp managers to use the CCCM Cluster tool to provide updates on kerosene distribution. - SNFI Cluster to send monthly updates to BRHA on what has been reported on kerosene. |
|  |  | - Partners encouraged to share plans and ongoing activities on AI. |
| CAMPS | UNHCR and ACTED: Share the list of maintenance activities in camps that have been agreed on. ACTED: AFAD tent replacement, the process is still ongoing to identify supplier. | - UNHCR to share the complete list of activities for camp maintenance with SNFI cluster. The list contain all activities requested by BRHA also |
| Out of camps | Shariya school residents have been given tents by the government to resettle in a land near by the school selected by the beneficiaries. |  |
| AOB | MoMD: Distributed the following: - 3742 clothing set - 3742 kitchen set - In support of the Yezidi females who survived ISL, the ministry distributed 2,000,000 IQD for the registered females - 92 females so far out of a target of 900. Medair Contact: Petya Boevska is the SNFI Sub-National Cluster Coordinator for KRI. She can be reached at coord3.iraq@sheltercluster.org. 0771 994 5692 | - Medair to share with SNFI Cluster a short “lessons learnt” document on the use of SEVAT and their experience with designing a voucher NFI programme. |

Next meeting:		6th August 2019