Shelter/NFI Cluster Coordination Meeting, Dahuk

Location: 		BRHA Conference Room, Dahuk

Date and time: 		6th August 2019

Attendance:		ACTED, BRHA, CCCM Cluster, Medair, SNFI Cluster, OCHA, PWJ, Qandil, UNICEF and UNHCR

| Agenda Item | Key Points | Actions |
| --- | --- | --- |
| General SNFI Update | - SNFI presented gaps in HRP and non-HRP response at Mid-Year, as per AI reporting. - SNFI clarified the process for Partners to apply for the 2nd IHF Allocation – timeline, criteria, prioritized locations and activities for Dohuk. - SNFI Cluster tools in Activity Info has been presented, together with the Interactive Dashboard - SNFI cluster has completed a cycle of trainings for Dohuk-based Partners with 60 people trained in Activity Info, Assessments and Common Database of Indicators, War-Damaged Shelter Rehabilitation, and the use of SEVAT. | - SNFI Cluster to send an update to UNHCR on IPs against targets. |
|  |  | - SNFI will send a second message on the IHF Allocation – 8 August through national and sub-national mailing list. |
|  |  | - Partners to inform SNFI of any additional trainings needed. |
| CAMPS | UNHCR and ACTED: Share the list of maintenance activities in camps that have been agreed on. Bajet Kandala: UNHCR, BRHA, SNFI and other interested partners to conduct a technical visit to assess the condition of the 162 communal tents – end of August. ACTED tent replacement: Supplier has been identified and testing to be performed on 8 August with BRHA, SNFI at Shariya camp. Timeline for the start of replacement now shifted to 1 Sept (Shariya) and 29 Sept (Bersive 1). Tent replacement work to be finished by 10 October. | - UNHCR and ACTED to share the list of maintenance activities that have been agreed on. - SNFI to send invitation for Bajet Kandala meeting and set dates. |
| Out of camps | Out of camp locations in in Sumel and Zakho has been identified as hosting a significant number of IDPs living in critical shelter. Partners to prioritize these districts which have seen zero shelter achievements in 2019. | - Partners to check ILA VI data set to locate populations with critical needs. |
| AOB | MoMD: SNFI expressed concern over the lack of coordination and credible information on MoMD tents arrival in Dohuk. SNFI shared MoMD camp prioritization for replacement with BRHA and partners. MoMD has been distributing food basket, hygiene kit, home/kitchen set and clothes in Akre, Zakho, Bardarash and Dohuk city in July. Plans are to continue distributions for in and out of camps in August. Fire Incident: 20 tents have been destroyed on 6 Aug in Chamishku IDP camp, due to electrical fault. No casualties – UNHCR has already replenish NFIs for the affected families. Contact: Petya Boevska is the SNFI Sub-National Cluster Coordinator for KRI. She can be reached at coord3.iraq@sheltercluster.org. 0771 994 5692 | - SNFI to continue advocacy at national level. - BRHA to keep partners updated on the plans of MoMD, if new information is received. |

Next meeting:		3rd September 2019