## Slide 1: NFI Practices WG
update call Dec. 17th 2019
Global Shelter Cluster
ShelterCluster.org
Coordinating Humanitarian Shelter

## Slide 2: Suggested AGENDA
Introduction: quick intro round of participants in the call
Quick introduction/review on WG scope and workplan 2019 (if wanted)
Update on the concept note for NFI training
Topics to be discussed whether they are within the scope of the WG:
  development of environmentally friendlier alternatives for tarpaulin
  Fuel and energy sources for cooking, heating and lighting, as they often fall under NFI
  Document/monitor how modalities have changed over time (e.g. from in kind to cash) and what kind of impact that has on beneficiaries
Decision on future format of NFI WG communication/interaction
AOB

## Slide 3: NFI WG scope/workplan 2019/20
No. | Priority | GSC Strategy 2018-2022 Output/Action1. | Activity | Comments | By who (Lead, participants) | For when (Date) | Status
1 | High | 4.1.G.1 Capacity assessment framework to review gaps and capacity development needs; 4.1.G.11 Relevant online trainings integrated into the GSC website and availabe in key operational languages; (4.3.G.2 Support country-level clusters with shelter-related materials to guide appropriate use of cash and markets modalities in achieving shelter outcomes). | Development of training curriculum outline for online learning modules on NFI practices, based on materials already existing and identified gap areas. |  | WG chairs (UNHCR,IFRC) with input from WG members | Q2 2019 | finished
 |  |  | Drafting of funding proposal for the consolidation of content and development of missing topics into online modules for the full curriculum by relevant experts. |  | WG chairs (UNHCR,IFRC) with input from WG members | Q3 2019 | ongoing
 |  |  | Develoment of content for the different training modules/topcis and production of e-learning sessions/modules to be made available on the GSC website as well as IFRC and UNHCR and other humanitarian learning platforms and translated into at least three relavant languages (French, Spanish, Arabic). | Contingent upon funding | identifed experts/consultants with support input and validation from WG members | Q3 2020 | Planned
2 | Low | 3.3.G.1 GFP for Learning and Knowledge Management - to gather and disseminate country-level lessons and best practice; 3.3.C.1; 3.3.G.4 4.1.G.8 Update and maintain Coordination Toolkit | Maintain the contextualized repository of NFI practices at: https://www.sheltercluster.org/working-group/nfi-practices | Quarterly | UNHCR | Quarterly | Ongoing

## Slide 4: Concept Note for NFI training
Chart: People supported with Shelter items and NFI
| 2015 | 2016 | 2017 | 2018 | 2019
Mio ppl supported with shelter NFI | 16.5 | 12.2 | 10 | 8.6 | 6
Mio ppl supported with shelter | 6.3 | 3.6 | 4.8 | 3.5 | 1.9
Between 65% and 75% of beneficiaries that received shelter related support received it through NFI, In average over the last 5 years that amounts to almost 8mio people/ year!
An average of 439 Mio $ of funding per year was spent on shelter & NFI, unfortunately we have not disaggregated data regarding the split between Shelter & NFI) but it seems fair to assume that larger amount of funding goes to NFI operations.
All consultation by the NFI WG (workshops with shelter practitioners in Nairobi 2016 and Bangkok 2018, an online survey 2018, GSC meetings 2017/18/19) indicate that practitioners in the field to not feel adequately equipped to deal with all aspects and complexities of NFI operations. Agencies do not have resources to develop on all aspects and topics related to NFIs and roll out trainings regularly for field staff.
Confirmed need to develop generic guidance/training modules on all aspects of NFI operations that can be easily accessible for any agency staff anywhere in the world.

## Slide 5
Topic | Content outline | resource | Existing expertise from …
Needs assessment | Introduction to needs assessment with focus on interaction communities/community participation, cultural appropriateness and “do no harm” ? rapid response mechanism = agency collaboration to do rapid multisectoral assessments and cover needs as last resort but also coordinate | Mostly existing content, to be synthesized and complemented | Various (almost every agency has some guidance; focus on UNHCR and IFRC)
Beneficiary selection and targeting | How to select and target most vulnerable and “taylor” assistance to different needs, using score cards and other approaches | partially existing content to be synthesized and complemented | Various resources to be explored (UNICEF in DR Congo, WV South Sudan)
NFI modalities | Introduction and basic knowledge of possible NFI approaches such as cash, NFI fairs, vouchers, in kind distribution etc. ; maybe short module per modality? How to choose the most appropriate modality for the context; include technical assistance as necessary complement to shelter materials | Partially existing content, to be synthesized and complemented | Various agencies have different approaches and related guidance
Contextu-alisation of kits | Contextualisation of NFI kits: how to define context specific NFI kits, what main factors need to be considered? Consider differences of needs for urban & rural, hot & cold climates, conflict or natural disaster, etc.. Maybe to be elaborated in 2 or 3 modules | Mostly new content to be developed; maybe to split into several modules | 
Procurement | Local vs International procurement? Introduction to procurement processes;  How to discern whether local or international procurement is more appropriate and feasible | Content probably existing, to be adapted to NFI specific Qs (in collaboration with procurement units) | IFRC & UNHCR & IOM…
Please let us know of any existing resources on these topics that you are aware of

## Slide 6
Topic | Content outline | resource | Existing expertise from …
Procurement | Common pipeline : when is a common pipeline approach useful and appropriate? How to take an informed and inclusive decision? What role does the Cluster take in this process? | Content existing decision guidance to be developed | 
contingency planning, preparedness, | How to conduct/support contingency planning exercises? Basic guidance on stock keeping / warehousing ? | Guidance partially existing, | Agency specific guidance to be compiled and generalized
Markets (for local procurement | Introduction to market assessment to support decision making reg local procurement; especially look at rental market (work form UNHCR and CashCap) | Content existing, to be adapted to NFI specific Qs | Various market assessment tools (EMMA; IFRC tools RAM and MAG British RC market assessment training,
Specifications (for local procurement) | How to draft good specs, decide on samples, basic methods of quality control etc. Connect with environmental considerations | Mostly new content to be developed; maybe to split into separate modules | 
Quality control | How to control delivered items whether the quality conforms to the given specs? (ICRC has a 5 day QC practical training for the most procured NFI internationally) | Content mostly existing, not suitable for online learning. | ICRC; maybe short online summary and link to ICRC training schedule?
Distribution planning | how to plan and set up a distribution; targeted vs blanket; preparations, safety, contact to community leaders, site selection, communications | Mostly existing content, to be synthesized and complemented | Various agencies (Red Cross Relief ERUs, UNHCR, IOM, MSF, Oxfam, Habitat etc.)
Distribution implementation | How to set up the site, accessibility registration, crowd control, behaviour/body language, GBV prevention, transport; distribution to inaccessible areas, etc. | Mostly existing content, to be synthesized and complemented | Various agencies (Red Cross Relief ERUs, UNHCR, IOM, MSF, Oxfam, Habitat etc.)
Please let us know of any existing resources on these topics that you are aware of

## Slide 7
Topic | Content outline | resource | Existing expertise from …
Demonstration/ technical assistance | For what items is additional support useful (e.g. demonstrations of solar lamps or stoves, or hygiene promotion for hygiene kits) or more sophisticated technical assistance necessary (e.g. help or trainings on using shelter kits or construction materials) and how to best deliver this assistance | Mostly new content to be developed; maybe to split into several modules | IFRC-SRU?
Gender related vulnerabilities, GBV, inclusion | How to identify, avoid, mitigate situations that could be conducive to GBV | existing content, liaise with IOM/the GBV WG to adapt/include their GBV guidance | IOM, UNICEF
environmental considerations | What environmental considerations to identify potential issues; basic ideas for avoiding unnecessary waste (single use plastic & other packaging), recycling, decommissioning. Raising awareness to topics like production processes, material quality, exploitation of natural resources etc. | Mostly new content to be developed; Liaise/collaborate with environmental WG and green response network | 
Post Distribution Monitoring | How to set up your monitoring framework, what information, lessons, learning, and insights to capture? How to conduct the monitoring? | Mostly existing content, to be synthesized and complemented | 
Accountability (anti-corruption and aid diversion) | Communication with Communities, how to set up and rung complaints mechanisms, procurement related transparency (tender processes etc, understand how corruption can be spotted and prevented) | Content partially existing, to be adapted to NFI specific Qs | 
longer term impact | How to assess whether the distributed items have met the needs and what is the longer term impact | Mostly new content to be developed; | 
Please let us know of any existing resources on these topics that you are aware of

## Slide 8: Clarification on whether these topics are within the scope of the WG and further interest
  development of environmentally friendlier alternatives for tarpaulin
  Fuel and energy sources for cooking, heating and lighting, as they often fall under NFI
  Document/monitor how modalities have changed over time (e.g. from in kind to cash) and what kind of impact that has on beneficiaries.

## Slide 9: Future format of NFI WG interactions
Is there any interest to have regular calls and if so how often?
What would be the format and content of such calls?
  exchange experience on particular topics of interest from field level. Participants to volunteer to prepare short presentations on their work of interest and share present during sykpe call?
  Other ideas to make the WG more useful and interesting?

## Slide 10: AOB