## Slide 1
Centre and south Shelter Cluster Hub Coordination Structure
Michel Tia - IOM
Sub National Cluster Coordinator for Centre and South
+964 (0) 782 294 9258
coord4.iraq@sheltercluster.org
Nicoletta Roccabianca - PUI
Deputy Area Coordinator – Centre and South
Shelter Cluster Focal Point for Anbar Governorate
+964 (0) 783 306 1031
ira.csi.deputy-areacoo-prog@pu-ami.org
Lottie McCarthy - DRC
Shelter and Infrastructure Programme Manager – Tikrit
Shelter Cluster Focal Point for Salah ad-Din Governorate
+ 964 (0) 772 997 2314
lottie.mccarthy@drc.ngo
Layth Al-Azzawi - UNHCR
Snr. Field Associate – CCCM & Shelter-NFI - Centre and South
Shelter Cluster Focal Point for Diyala Governorate
+964 (0) 780 195 3136
alazzawi@unhcr.org

## Slide 2
Iraq humanitarian response Centre and south Shelter Cluster Hub Coordination meeting
Baghdad
February 5th, 2020

## Slide 3
AGENDA
Review of action points from minutes of previous meeting;
Key issues
  2020 Activity Plan;
  Housing Rehabilitation interventions (ongoing/planned);
  Update on the ongoing winter response;
  Tents replacement;
Information Management
  2019 HRP / Non-HRP achievements – as of 31 December 2019;
  2020 ActivityInfo training plan;
AOB
Inhabited chicken farm in Falluja, 2/2018

## Slide 4
Review of action points from minutes of previous meeting
# | Action Points | Focal Point | Status / Deadline
1 | Housing rehabilitation: Shelter Cluster Team (SAD Focal Point & C&S Coordinator) to follow up with partners (OXFAM, NRC, MEDAIR, DRC & Mercy Corps) to update their WDS data on the platform: https://www.sheltercluster.org/iraq/iraq-war-damaged-shelter-rehabilitation-interactive-dashboard; | Cluster partners C&S Hub Coordinator | Ongoing process
2 | Housing rehabilitation: Shelter Cluster to prepare and share 2019 WDS achievements. | Cluster IM Unit | ASAP
3 | Pending action point: The Cluster partners will be sharing key challenges they have been facing in their housing rehabilitation programme, solutions and/or recommendations on way forward. | Cluster partners | Ongoing process
4 | Winter response: find alternative areas for IOM to distribute available 930 winter kits; liaise with UNHCR/ZOA to cover identified new areas in BzBz; coordinate with DRC any potential winter distributions in Baiji to avoid overlapping; | Cluster partners C&S Hub Coordinator | Completed
5 | CCCM & Shelter Cluster to jointly prepare the 2020 meeting plan and share with partners. | CCCM & Shelter Cluster Coordinators | Completed

## Slide 5
Key issues and Partner’s updates
  2020 Activity Plan
Project | Donor | Target | Status | Locations | # houses
Rehabilitation (Cat2 houses) Cash modality | OFDA | 1,700 Shelter units including 1,050 Shelter units in Centre & South | Project just started Assessment phase Using SEVAT | Anbar - Heet | 250
 |  |  |  | Anbar - Karma | 350
 |  |  |  | Salah al-Din | 150
 |  |  |  | Diyala | 300
Rehabilitation (Cat2 houses) |  | 150 Shelter units | Expecting SEVAT result from PUI | Anbar – Kaim (Al-Rummanah) | 150
Critical Shelter | ECHO | 300 Shelter unit | Planned | TBC | 
Critical Shelter | GERMAN | 300 Shelter unit | Planned | TBC | 
IOM – Shelter plan

## Slide 6
Key issues and Partner’s updates
  2020 Activity Plan
IOM – NFI plan
Funded by OFDA
Distribution will be starting after completion of SEVAT
Planned Activities | Target | Modality | Targeted Location | Details
Full Basic NFI Kits | 450 | In-kind | Salah Al-Din , Shirqat center | Targeting both camps and out of camps.
 | 750 | In-kind | Anbar, Al-Qaim, Habaniyah Tourist City | 
 | 300 | In-kind | Ninawa , Mosul, Hamam Aleel | 
 | 500 | In-kind | Ninawa, Shora, Makhmor | 
Full Basic NFI Kits | 800 | Voucher | Baghdad | Target, Abu Ghraib, Yousfiya and Al-Taji
 | 1,100 | Voucher | Diyala | Target: Baquba, Al-Khalis, Muqdadiya and Khanaqin
 | 1,100 | Voucher | Salah Al-Din | Target: Samara, Balad and Al-Dour
 | 200 | Voucher | Anbar | Target: Falluja
 | 250 | Voucher | Kirkuk | Target: Daquq
 | 550 | Voucher | Ninawa | Target: Talafar and Tilkaif
Partial NFI Kits (for replacement) | 1,650 | Voucher | Anbar | Target: Fallujah, Heet & Ramadi
 | 2,650 | Voucher | Salah Al-Din | Target: Tikrit, Samara, Tooz, Balad, Baiji & Al-Dour
 | 500 | Voucher | Baghdad | Target: Abu Ghraib & Latifiya
 | 500 | Voucher | Diyala, Al-Khalis | Target: Al-Khalis & Muqdadiya
 | 1,750 | Voucher | Kirkuk | Target: Hawija, Center & Daquq
 | 4,950 | Voucher | Ninawa | Target: Akre, Sheikan, Mosul, Tilkaif, Sinjar & Talafar
 | 18,000 |  |  | 
 | 8,300 | Kits for Kirkuk and Ninewa |  | 
 | 9,700 | Kits for Centre & South |  | 

## Slide 7
Key issues and Partner’s updates
  2020 Activity Plan
UNDP – Fund to be confirmed
1,500 Shelter units (Cat 1&2) in Falluja & in Ramadi (in four neighborhoods)
500 Shelter units (Cat 1&2) in Baiji in Salah al-Din
Demining & Reconstruction of the apartments complex in Ramadi
UNHCR – to be confirmed
NFI replacement in all managed Camps
770 RHU (Cat4 damaged houses)
770 Shelter units (Cat2)
Potential location: Anbar, Baghdad, Diyala, Salah al-Din
CRS – confirmed
150 Shelter units (Cat2)
Potential location: Falluja/Anbar - Jubail neighborhood (except in sector 212) & Hay Al Wilda neighborhood and Hay Al Shuhadaa including the new distribution area

## Slide 8
Key issues and Partner’s updates
  Housing Rehabilitation interventions (ongoing/planned) – for only Centre & South – without Ninewa & Kirkuk
Governorate | Location | 2019 - Project (Case) Name | # of units | Status
Anbar | Haditha | Rehabilitation Housing Works of 214 Units in Haqlaniya in two villages (Khasfa and Zawia) Villages in Haditha | 214 | Completed
Anbar | Haditha | Rehabilitation Housing Works of 187 Units in Barwanah District (Al-Sumood) | 187 | Completed
Anbar | Haditha | Rehabilitation of Housing Works of 136 Units in Haqlaniya (Al-BoHayat) Village in Haditha | 136 | Completed
Anbar | Haditha | Rehabilitation Housing Works of 137 Units in Barwanah District (Al-Ata'a) in Haditha | 137 | Completed
Anbar | Qaim | Rehabilitation of Housing works for 137 Units in Hay Sikak in Qaim City-Lot 1 | 137 | Completed
Anbar | Qaim | Rehabilitation of 342 houses units in Hay 12 Rabee Awalin Qaim lot-2 | 342 | Completed
Anbar | Anah | Rehabilitation of 241 houses units in Sagrah village in Anah District | 241 | Completed
Anbar | Anah | Rehabilitation of 186 housing units in Hasa village in Anah city | 186 | Completed
Anbar | Anah | Rehabilitation of 92 houses units in Obour Neighborhood in Anah | 92 | Completed
 |  |  | 1,672 | 
UNPD - Completed / on hold - 2019 Shelter rehabilitation projects
Governorate | Location | 2019 - Project (Case) Name | # of units | Status
Anbar | Anah | rehabilitation 350 houses in Rehanna | 350 | On hold
Anbar | Rawa | Rehabilitation of 600 houses units in Rawa (Two lots) | 600 | On hold
 |  |  | 950 | 

## Slide 9
UNPD - Ongoing 2019 Shelter rehabilitation projects
Governorate | Location | 2019 - Project (Case) Name | # of units | Status
Anbar | Qaim | Rehabilitation of 321 houses units in Hay Risala in Qaim (lots-3) | 321 | Ongoing
Salah al-Din | Baiji | Rehabilitation of 174 housing units in Baiji Askary1 Neighborhood | 374 | Ongoing
Salah al-Din | Baiji | Rehabilitation of 364 housing units in Baiji Risala neighborhood | 500 | Ongoing
 |  |  | 1,195 | 
Governorate | Location | 2019 - Project (Case) Name | # of units | Status
Anbar | Karma | rehabilitation 303 houses in Khairat (Shortan Village). | 241 | Procurement
Salah al-Din | Baiji | Rehabilitation of 426 housing units in Baiji Tal Alza’atar Neighborhood | 426 | Procurement
 |  |  | 667 | 
Key issues and Partner’s updates
  Housing Rehabilitation interventions (ongoing/planned) – for only Centre & South – without Ninewa & Kirkuk
PUI - Ongoing 2019 Shelter rehabilitation project
108 Shelter units (Cat2)
Location: Al-Rummanah sub district in AL-Kaim district / Anbar
SEVAT has been completed
Contractor has been selected
Technical assessment will be starting around the second week of February 2020

## Slide 10
Country wide / Target In Centre & South
70,734 houses 34,858 houses (49% )
Key issues and Partner’s updates
  Housing Rehabilitation interventions (ongoing/planned) – for only Centre & South – without Ninewa & Kirkuk
Details on locations & Partners

## Slide 11
Key issues and Partner’s updates
  Update on the ongoing winter response
Have we reached all vulnerable people in camps (formal or informal) with our winter response ?
Governorate | District | Formal Camps | # HHs | Status
Anbar | Fallujah | AAF (21 Camps) | 882 | In-kind distribution
Anbar | Ramadi | HTC (5 Camps) | 589 | In-kind distribution
Baghdad | Al-Mahmoudiya | Latifiya 1 & 2 | 49 | Cash for winter ($200)
Baghdad | Al-Mada’in Al-Kadhmiyah Al-Risafa | Al-Nabi Younis Al-Ahel Zayona | 63 94 105 | Need Cash for winter ($200) Need
Diyala | Khanaqin | Al-Wand 1 Al-Wand 2 Qoratu | 601 199 200 | Cash for winter ($200) Cash for winter ($200) Cash for winter ($200)
Diyala | Baquba | Muskar Saad | 118 | Need
Kerbela | Al-Hinidya | Al-Kawthar | 104 | Need
Salah Al-Din | Tikrit | Al Karama | 202 | In-kind distribution
What about the informal Camps in Anbar, Baghdad, Missan & Qadissiya ?
Have we covered them ?

## Slide 12
Qayyarah-Jad'ah 5 camp, 4/2019
Makeshift shelter in Anbar, 2/2018
Key issues and Partner’s updates
  Tents replacement
Anbar
UNHCR - HTC 29 tents completed
Tahrir 1: 6 tents
Tahrir 2: 11 tents
Central tahrir: 12 tents
IOM - ongoing
AAF & BzBz: 150 IHF tents
Salah al-Din
UNHCR/IOM - completed
Al-Karama: 70 IHF tents
Baghdad
UNHCR - need
Latifiya 1 & 2: 40 tents are needed (MoMD type)
Diyala
UNHCR - need
Al-Wand 1 & 2: around 250 to 300 tents are needed
For Al-Wand 1 & 2 and Latifiya 1 & 2 camps, UNHCR through the CCCM Cluster is closely working with the local authorities on options and appropriate support to be provided.

## Slide 13
Information Management
  2019 HRP / Non-HRP achievements – as of 31 December 2019
Activity | 2019 target | HRP achievement |  | Non HRP achievement |  | Total HRP & non-HRP achievements | 
NFI | 513,900 | 347,278 | 68% | 114,799 | 22% | 462,077 | 90%
Shelter | 347,750 | 121,657 | 35% | 28,330 | 8% | 149,987 | 43%
Eprep | 20,000 | 0 | 0% | - | 0% | 0 | 0%
Total | 881,650 | 468,935 | 53% | 143,129 | 16% | 612,064 | 69%
29 Partners have reported their 2019 achievements in Activity info.
13 partners operating in KR-I
29 partners operating in Centre & South

## Slide 14
Information Management
  2020 ActivityInfo training plan
The training sessions will be delivered in English, with a capacity to clarify in Kurdish and/or Arabic
Dahuk (17th Feb. 20)
  Venue: UNHCR conference room
  Time: 09:30 am – 12:30 pm
Erbil ( 18th & 19th Feb. 20)
  Venue: NCCI meeting room
  Time: 02:00 pm – 05:00 pm
Baghdad (26th Feb. 20)
  Venue: UNHCR CSC office (Dawoodi area, Baghdad)
  Time: 10:30 am – 01:30 pm

## Slide 15
AOB
Shelter & CCCM Clusters up coming events in Baghdad
February 26th, 2020
Baghdad (Activity Info Training Session)
  Venue: UNHCR CSC office (Dawoodi area, Baghdad)
  Time: 10:30 am – 01:30 pm
March 25th, 2020
Sub-national Cluster coordination meeting for Centre and South
Invitation will be sent out on due time.
April 22nd, 2020
Sub-national Cluster coordination meeting for Centre and South
Invitation will be sent out on due time.