## Slide 1
Centre and south Shelter Cluster Hub Coordination Structure
Michel Tia - IOM
Sub National Cluster Coordinator for Centre and South
+964 (0) 782 294 9258
coord4.iraq@sheltercluster.org
Nicoletta Roccabianca - PUI
Deputy Area Coordinator – Centre and South
Shelter Cluster Focal Point for Anbar Governorate
+964 (0) 783 306 1031
ira.csi.deputy-areacoo-prog@pu-ami.org
Osama Luay Seddiq - DRC
ZZZZ - Tikrit
Shelter Cluster Focal Point for Salah ad-Din Governorate
+ 964 (0)
osama.seddiq@drc.ngo
Layth Al-Azzawi - UNHCR
Snr. Field Associate – CCCM & Shelter-NFI - Centre and South
Shelter Cluster Focal Point for Diyala Governorate
+964 (0) 780 195 3136
alazzawi@unhcr.org

## Slide 2
Iraq humanitarian response Centre and south Shelter Cluster Hub Coordination meeting
Baghdad
April 15th, 2020

## Slide 3
AGENDA
Review of action points from minutes of previous meeting;
Key issues
  Access letters: Coordination mechanism in place;
  Partners ongoing activities (related or not to COVID-19);
  2020 HRP review – COVID-19 related activities;
AOB
  Reporting – Activity Info
  Upcoming Cluster events
Inhabited chicken farm in Falluja, 2/2018

## Slide 4
Review of action points from minutes of previous meeting
# | Action Points | Focal Point | Status / Deadline
1 | Pending action point: The Cluster partners to share key challenges they have been facing in their housing rehabilitation programme, solutions and/or recommendations on way forward. | Cluster partners | Ongoing process
2 | Pending action point: Shelter Cluster to prepare and share 2019 WDS achievements. | Cluster IM Unit | Ongoing process
3 | Housing rehabilitation: Shelter Cluster Team to follow up with following partners (OXFAM, NRC, MEDAIR, DRC & Mercy Corps) to update their WDS data on the platform | Cluster Partners | Ongoing process
4 | Winter response: find alternative areas for IOM to distribute available 930 winter kits (IOM covered Al-wand camps in Diyala) liaise with UNHCR/ZOA to cover identified new areas in BzBz coordinate with DRC any potential winter distributions in Baiji to avoid overlapping | Cluster partners C&S Hub Coordinator | Completed
5 | CCCM & Shelter Cluster to jointly prepare the 2020 meeting plan and share with partners - | CCCM & Shelter Cluster Coordinators | Completed
6 | Action point: CRS & UNDP to share with the Cluster their respective intervention area in Hay Al Shuhadaa neighborhoods, to confirm if no overlapping and/or to convene a bilateral meeting if needed. | Hub coordinator to follow up | Ongoing process
7 | Winter uncovered need in Camps in Baghdad (2 camps), Diyala (1 camp) and Kerbala (1 camp): The Cluster will follow up with IOM and UNHCR. The total people to be covered: 390 families | Hub coordinator to follow up | Ongoing process

## Slide 5
Key issues and Partner’s updates
  Access letters: Coordination mechanism in place – OCHA & Shelter Cluster
It is important to highlight that access challenges, either because of lack of NOC letter or related to COVID-19 movement restrictions, have been different across governorates. In general, intra-governorate movements have been granted, while inter-governorates ones have remained very difficult.
Any type of movements should be directly coordinated with OCHA through their Geographic Focal Points.

## Slide 6
Key issues and Partner’s updates
  Partners ongoing activities (related or not to COVID-19) – Tour de table
Please refer to the minutes of the meeting for more details

## Slide 7
Key issues and Partner’s updates
  2020 HRP review – COVID-19 related activities – Shelter Cluster
Only two activities COVID-19 related have been added into the 2020 HRP
Provision of tents for quarantine / isolation areas
Provision of NFI for quarantine / isolation areas

## Slide 8
AOB – Shelter Cluster
Reporting – Activity Info
Partners were encouraged to continue reporting their achievement into Activity Info in timely manner.
Upcoming Cluster events
May 20th, 2020
Sub-national Cluster coordination meeting for Centre and South; Invitation to be sent out on due time.