## Slide 1
Centre and south Shelter Cluster Hub Coordination Structure
Michel Tia - IOM
Sub National Cluster Coordinator for Centre and South
+964 (0) 782 294 9258
coord4.iraq@sheltercluster.org
Nicoletta Roccabianca - PUI
Deputy Area Coordinator – Centre and South
Shelter Cluster Focal Point for Anbar Governorate
+964 (0) 783 306 1031
ira.csi.deputy-areacoo-prog@pu-ami.org
Osama Luay Seddiq - DRC
ZZZZ - Tikrit
Shelter Cluster Focal Point for Salah ad-Din Governorate
+ 964 (0)
osama.seddiq@drc.ngo
Layth Al-Azzawi - UNHCR
Snr. Field Associate – CCCM & Shelter-NFI - Centre and South
Shelter Cluster Focal Point for Diyala Governorate
+964 (0) 780 195 3136
alazzawi@unhcr.org

## Slide 2
Iraq humanitarian response Centre and south Shelter Cluster Hub Coordination meeting
Baghdad
May 20th, 2020

## Slide 3
AGENDA
Review of action points from minutes of previous meeting;
Key issues
  Update on access issues – OCHA;
  Partners planned and ongoing activities (related or not to COVID-19) – Partners;
  Activity Info: 2020 HRP Shelter Cluster achievements / PMR (Jan. - Apr. 2020) – Cluster;
AOB
  Upcoming Cluster events
Inhabited chicken farm in Falluja, 2/2018

## Slide 4
Review of action points from minutes of previous meeting
# | Action Points | Focal Point | Status / Deadline
1 | Action point: CRS & UNDP to share with the Cluster their respective intervention area in Hay Al Shuhadaa neighborhoods, to confirm if no overlapping and/or to convene a bilateral meeting if needed. | Hub coordinator to follow up with CRS & UNDP | Pending
2 | Needs Around 400 NFI kits are needed in Camps in Baghdad (Al-Nabi Younis & Zayona camps); Diyala (Muskar Saad camp) and Kerbala (Al-Kawthar camp). The Cluster will follow up with IOM and UNHCR. Around 143 NFI kits are needed in Salad al-Din. This includes 77 NFI kits in Balad Train station and 66 NFI kits in Ishaqi IDPs camp. | Hub coordinator to follow up with IOM & UNHCR | Work in progress
3 | IOM to share the key findings of their COVID-19 related assessments. | IOM | Work in progress
4 | IOM to share more details (locations, beneficiaries’ groups, …) where the COVID-19 kits will be distributed. | IOM | Work in progress
5 | Partners to share their NFI additional COVID-19 related items. | Shelter partners | Work in progress
6 | Post COVID-19 market assessment: Availabilities of the market / market prices. | Shelter partners with the capacity to procced | Work in progress

## Slide 5
Key issues and Partner’s updates
  Update on access letters issues – OCHA & Shelter Cluster
Access challenges have not changed much from previous meeting:
lack of NOC letter or related to COVID-19 movement restrictions,
Intra-governorate movements have been granted and ongoing smoothly since no related incidents have been reported so far, while inter-governorates ones have remained very difficult.
movements should be directly coordinated with OCHA through their Geographic Focal Points.
Meeting has been planned in Baghdad (right after Eid holidays) with Anbar Governor to discuss inter-governorates (Baghdad to Anbar) access and procedure issues.
At national level, meeting has also been planned with NOC.
Partners will surely be informed on new development

## Slide 6
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
NFI - response
IOM plan with confirmed funds.
OFDA 2019 carried over: 2,000 in-kind and 16,000 Cash vouchers
  The current workplan has been reviewed including locations and beneficiaries due to COVID-19 movement restrictions,
  Re-assessment to be conducted through KIs and by phone,
2020 ECHO: Cash/NFI assistance to secondary displaced IDPs (due to post-2019 camp closure and consolidation)
  Cash (320USD or 400USD) for 2,000 HHs; equivalent to the MPCA amount in two tranches
  NFI Cash Vouchers for 250 HHs (250USD)
  in Anbar, Baghdad and Ninewa governorates
2020 German:
  Cash (320USD or 400USD) for 900 HHs; equivalent to the MPCA amount in two tranches
  NFI Cash Vouchers for 350 HHs (250USD)
  in Anbar, Dahuk, Ninewa and Salah al-Din governorates
For both ECHO & German, SEVAT to be conducted or use the SEVAT assessment conducted by other partners.

## Slide 7
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
NFI - response
IOM plan with funds to be confirmed.
2020 OFDA (in-kind)
  2,700 Basic NFI kits,
  3,500 Replacements NFI kits
  in KRI, Ninewa and Kirkuk
  in Anbar, Diyala, Baghdad and Salah al-Din governorates

## Slide 8
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
UNPD - 2019 Shelter rehabilitation projects – completed before COVID-19
Housing and rehabilitation

## Slide 9
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
UNPD - 2019 Shelter rehabilitation projects – on hold due to COVID-19
1,500 Shelter units (Cat 1&2) in Falluja & in Ramadi (in four neighborhoods)
500 Shelter units (Cat 1&2) in Baiji in Salah al-Din
Demining & Reconstruction of the apartments complex in Ramadi
UNPD – 2020 Shelter rehabilitation projects – on hold due to COVID-19

## Slide 10
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
IOM – 2020 Shelter rehabilitation projects – Ongoing

## Slide 11
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
PUI - Ongoing 2019 Shelter rehabilitation project – Ongoing
108 Shelter units (Cat2) has been increase up to 125 shelter units
Location: Al-Rummanah sub district in AL-Kaim district / Anbar
SEVAT has been completed
Contractor has been selected
Technical assessment will be starting around the second week of February 2020

## Slide 12
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
UNHCR – to be confirmed - on hold due to COVID-19
NFI replacement in all managed Camps
770 RHU (Cat4 damaged houses)
2,700 Shelter units (Cat2)
Potential location: Anbar, Baghdad, Diyala, Salah al-Din
CRS – confirmed - on hold due to COVID-19
150 Shelter units (Cat2)
Potential location: Falluja/Anbar - Jubail neighborhood (except in sector 212) & Hay Al Wilda neighborhood and Hay Al Shuhadaa including the new distribution area

## Slide 13
Key issues and Partner’s updates
  Activity Info: 2020 HRP Shelter Cluster achievements / PMR (Jan. - Apr. 2020) – for Centre & South only
Shelter achievements: 1,587 Ind.
  IDPs in Camps: 618 Ind.
  IDPs out of camps: 600 Ind.
  Returnees: 369 Ind.

## Slide 14
Key issues and Partner’s updates
  Activity Info: 2020 HRP Shelter Cluster achievements / PMR (Jan. - Apr. 2020) – for Centre & South only
NFI achievements: 18,099 Ind.
IDPs in Camps: 2,510 Ind.
IDPs out of camps: 8,943 Ind.
Returnees: 6,646 Ind.

## Slide 15
AOB – Shelter Cluster
Upcoming Cluster events
June 17th, 2020 from 10:30 am
Sub-national Cluster coordination meeting for Centre and South; Invitation to be sent out on due time.