## Slide 1
Centre and south Shelter Cluster Hub Coordination Structure
Michel Tia - IOM
Sub National Cluster Coordinator for Centre and South
+964 (0) 782 294 9258
coord4.iraq@sheltercluster.org
Nicoletta Roccabianca - PUI
Deputy Area Coordinator – Centre and South
Shelter Cluster Focal Point for Anbar Governorate
+964 (0) 783 306 1031
ira.csi.deputy-areacoo-prog@pu-ami.org
Osama Luay Seddiq - DRC
Tikrit
Shelter Cluster Focal Point for Salah ad-Din Governorate
osama.seddiq@drc.ngo
Layth Al-Azzawi - UNHCR
Snr. Field Associate – CCCM & Shelter-NFI - Centre and South
Shelter Cluster Focal Point for Diyala Governorate
+964 (0) 780 195 3136
alazzawi@unhcr.org

## Slide 2
Iraq humanitarian response Centre and south Shelter Cluster Hub Coordination meeting
Baghdad
June 17th, 2020

## Slide 3
AGENDA
Review of action points from minutes of previous meeting;
Key issues
  Update on access issues – OCHA;
  Update on partners planned and ongoing activities – Partners;
  New guidance document “Construction Site Safety Protocol for COVID-19 Contexts” – Cluster;
AOB
  Upcoming Cluster events
Inhabited chicken farm in Falluja, 2/2018

## Slide 4
Review of action points from minutes of previous meeting
# | Action Points | Focal Point | Status / Deadline
1 | Action point: CRS & UNDP to share with the Cluster their respective intervention area in Hay Al Shuhadaa neighborhoods, to confirm if no overlapping and/or to convene a bilateral meeting if needed. | Hub coordinator to follow up with CRS & UNDP | Work in progress
2 | Needs Around 400 NFI kits are needed in Camps in Baghdad (Al-Nabi Younis & Zayona camps); Diyala (Muskar Saad camp) and Kerbala (Al-Kawthar camp). The Cluster will follow up with IOM and UNHCR. Around 143 NFI kits are needed in Salad al-Din. This includes 77 NFI kits in Balad Train station and 66 NFI kits in Ishaqi IDPs camp. | Hub coordinator to follow up with IOM & UNHCR | Continue to follow up with IOM
3 | IOM to share the key findings of their COVID-19 related assessments. Key findings of their COVID-19 related assessments at sub-districts level, conducted by IOM (early April 2020): http://iraqdtm.iom.int/COVID19 | IOM | Completed
4 | IOM to share more details (locations, beneficiaries’ groups, …) where the COVID-19 kits will be distributed. | IOM | Work in progress
5 | Partners to share their NFI additional COVID-19 related items. | Shelter partners | Work in progress
6 | Post COVID-19 market assessment: Availabilities of the market / market prices. | Shelter partners with the capacity to procced | Work in progress
7 | Access Issues: OCHA to share any update from Baghdad and Salah al-Din. IOM to liaise with OCHA or the Cluster if any specific need/challenges | IOM | Work in progress
8 | UNPD to shared details on their new housing & rehabilitation projects once confirmed | UNDP | Work in progress

## Slide 5
Key issues and Partner’s updates
  Update on access letters issues – OCHA & Shelter Cluster
Access challenges remain:
NOC letter or related to COVID-19 movement restrictions;
Intra-governorate movements can be granted ….. ;
Inter-governorates movements remain very difficult;
Access incidents report
All movements request should be directly coordinated with OCHA through their Geographic Focal Points.
However, above have huge impact on partners interventions (planned and / or ongoing projects), with very limited operational presence and capacity to deliver.

## Slide 6
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
NFI - response
IOM - confirmed.
OFDA: 2,000 in-kind and 16,000 Cash vouchers
ECHO:
  Cash (320USD or 400USD) for 2,000 HHs; equivalent to the MPCA amount in two tranches
  NFI Cash Vouchers for 250 HHs (250USD)
German:
  Cash (320USD or 400USD) for 900 HHs; equivalent to the MPCA amount in two tranches
  NFI Cash Vouchers for 350 HHs (250USD).
IOM - to be confirmed.
OFDA (in-kind)
  2,700 Basic NFI kits,
  3,500 Replacements NFI kits

## Slide 7
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
UNPD - 2019 Shelter rehabilitation projects – on hold due to COVID-19
UNPD – 2020 Shelter rehabilitation projects – on hold due to COVID-19
1,500 Shelter units (Cat 1&2) in Falluja & in Ramadi (in four neighborhoods)
500 Shelter units (Cat 1&2) in Baiji in Salah al-Din
Demining & Reconstruction of the apartments complex in Ramadi
Housing and rehabilitation

## Slide 8
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
IOM – 2020 Shelter rehabilitation projects – Ongoing

## Slide 9
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
PUI - Ongoing 2019 Shelter rehabilitation project – Ongoing
108 Shelter units (Cat2) has been increase up to 125 shelter units
Location: Al-Rummanah sub district in AL-Kaim district / Anbar
SEVAT has been completed
Contractor has been selected
Technical assessment will be starting around the second week of February 2020

## Slide 10
Key issues and Partner’s updates
  Partners planned and ongoing activities (related or not to COVID-19) – Tour de table - Partners
UNHCR – to be confirmed - on hold due to COVID-19
NFI replacement in all managed Camps
770 RHU (Cat4 damaged houses)
2,700 Shelter units (Cat2)
Potential location: Anbar, Baghdad, Diyala, Salah al-Din
CRS – confirmed - on hold due to COVID-19
150 Shelter units (Cat2)
Potential location: Falluja/Anbar - Jubail neighborhood (except in sector 212) & Hay Al Wilda neighborhood and Hay Al Shuhadaa including the new distribution area

## Slide 11
Key issues and Partner’s updates
  New guidance document “Construction Site Safety Protocol for COVID-19 Contexts” – Cluster
The Shelter Cluster new guidance document called “Construction Site Safety Protocol for COVID-19 Contexts” was developed with great contributions from PUI, DRC and UN-Habitat, and shared with partners on June 2nd, 2020
On June 11th, 2020, the document was presentation in a form of PowerPoint presentation during a special national Shelter Cluster meeting. That presentation was immediately shared with partners.
Currently, the Shelter Cluster is also developing an Information, Education and Communication (IEC) Toolbox based on the guidance. Once completed, the IEC - Toolbox will be shared with you.

## Slide 12
AOB – Shelter Cluster
Upcoming Cluster events
July 15th, 2020 from 10:30 am
Sub-national Cluster coordination meeting for Centre and South; Invitation to be sent out on due time.