## Slide 1
Centre and south Shelter Cluster Hub Coordination Structure
Michel Tia - IOM
Sub National Cluster Coordinator for Centre and South
+964 (0) 782 294 9258
coord4.iraq@sheltercluster.org
Osama Luay Seddiq - DRC
Shelter and Infrastructure Officer - Tikrit
Shelter Cluster Focal Point for Salah ad-Din Governorate
+964 (0) 773 489 1375
osama.seddiq@drc.ngo
Layth Al-Azzawi - UNHCR
Snr. Field Associate – CCCM & Shelter-NFI - Centre and South
Shelter Cluster Focal Point for Diyala Governorate
+964 (0) 780 195 3136
alazzawi@unhcr.org
Name - Agency - To be nominated
Function
Shelter Cluster Focal Point for Anbar
Contact details (phone & mail)

## Slide 2
Centre and south Shelter Cluster Hub Coordination meeting
Baghdad
October 07th, 2020

## Slide 3
AGENDA
Key issues
  Partners reporting status - from Activity Info and Iraq War Damaged Shelter Rehabilitation Database;
  Partners progress on ongoing/planned NFI responses in and out of Camps (related or not to COVID-19);
  Partners progress on Housing and Rehabilitation (planned and ongoing interventions);
  IHF projects - Critical Shelter repairs in Anbar &Salah al-Din Governorates and PDM;
AOB

## Slide 4
Key issues
  Partners reporting status - from Activity Info and Iraq War Damaged Shelter Rehabilitation Database

## Slide 5
Key issues
  Partners reporting status - from Activity Info and Iraq War Damaged Shelter Rehabilitation Database

## Slide 6
Key issues
  Partners progress on ongoing/planned NFI responses in and out of Camps (related or not to COVID-19) - Tour de table - Partners
UNHCR
Returnees: 263 HHs in Al-Qaim DC, Al-Rummanah sub-district

## Slide 7
Key issues
  Partners progress on ongoing/planned NFI responses in and out of Camps (related or not to COVID-19) - Tour de table - Partners
IOM
Out of 18,000 NFIs Kits planned for this year, over 8,400 (4,800 vouchers+ 3,600 in-kind) have been distributed.
9,600 in-kind to be distributed before end of Oct this year.
In addition 600 NFIs (cash + voucher) to be distributed Ninewa (likely Baiij, Sinjar,) and Anbar before end of December.

## Slide 8
IOM – 2020 Shelter rehabilitation projects – Ongoing
Governorate | Location | 2020-Project | Units | Families | Status | Donors | Status2
Anbar | Heet | Rehabilitation of Cat2 houses in Baghdady | 101 | 252 | ongoing | OFDA | 65%
Anbar | Haditha | Rehabilitation of Cat2 houses in Albohayat | 21 | 52 | ongoing | OFDA | 
Anbar | Faluja-Garma | Rehabilitation of CAT2 houses in Luhaib village | 92 | 373 | ongoing | OFDA | 38.12%
Salah al-Din | Beji | Rehabilitation od CAT2 houses in siniya | 45 | 98 | ongoing | OFDA | 41%
Diyala | Khanaqin and Muqdadya | Rehabilitation od CAT2 houses in center of Sadiya and Muqdadya | 228 | 400 | ongoing | OFDA | 80.30%
Anbar | Faluja-Garma | Reahabilitaion of CAT3 Houses in Luhaib village | 10 | 50 | ongoing | German | 0%
Salahadin | Tooz-Sulaiman Beg | Rehabilitation of CAT3 and CAT2 houses | 60 | 84 | ongoing | German | 0%
Anbar | Ana | Reahabilitaion of CAT3 Houses | 8 | 23 | ongoing | German | 0%
Key issues and Partner’s updates
  Partners progress on Housing and Rehabilitation (planned and ongoing interventions)- Tour de table - Partners
Notes: Only for C&S, 1,173 CAT 2 has been achieved and additional 750 (CAT2 and 3) are in plan until end of the year.

## Slide 9
Key issues and Partner’s updates
  Partners progress on Housing and Rehabilitation (planned and ongoing interventions)- Tour de table - Partners
UNPD - 2019 Shelter rehabilitation projects
UNPD – 2020 Shelter rehabilitation projects
1,500 Shelter units (Cat 1&2) in Falluja & in Ramadi (in four neighborhoods)
500 Shelter units (Cat 1&2) in Baiji in Salah al-Din
Demining & Reconstruction of the apartments complex in Ramadi
Last Update: | 13-Aug-2020 12:22 AM |  |  |  |  |  | 
Region |  | # | Project Name | # of Units in the Project | Project Status | Achievement Percentage | # of Units Completed
Anbar | Al Garma | 33 | Shortan-Al Khairat | 303 | Procurment | 0% | 0
Salah Al-Din | Baiji | 2 | Al-Askary1 | 174 | Ongoing | 18% | 34
Salah Al-Din | Baiji | 3 | Tal Al-Za'atar | 426 | Procurement | 0% | 0
 |  |  |  | 903 |  |  | 34

## Slide 10
Key issues and Partner’s updates
  Partners progress on Housing and Rehabilitation (planned and ongoing interventions)- Tour de table - Partners
PUI - Ongoing 2019 Shelter rehabilitation project – Ongoing
108 Shelter units (Cat2) has been increased up to 125 shelter units
Location: Al-Rummanah sub district in AL-Kaim district / Anbar
SEVAT has been completed
Contractor has been selected
Technical assessment will be starting around the second week of February 2020

## Slide 11
Key issues and Partner’s updates
  Partners progress on Housing and Rehabilitation (planned and ongoing interventions)- Tour de table - Partners
UNHCR – to be confirmed
NFI replacement in all managed Camps
770 RHU (Cat4 damaged houses)
2,700 Shelter units (Cat2)
Potential location: Anbar, Baghdad, Diyala, Salah al-Din
CRS – confirmed
150 Shelter units (Cat2)
Technical assessment for the 150 targeted WD shelters in Falluja Jubail neighborhood (except in sector 212) & Hay Al Shuhadaa;

## Slide 12
UN-HABITAT – 2020 Shelter rehabilitation projects – Ongoing
Distribution of SOK in Anbar, in Markaz Fallujah, Saqlawiyah, and Karma:
Distribution of SOK items via Vouchers with an amount of 270 USD to 1,014 pre-identified households. 927 households have been assisted as follows:
  772 households in Markaz Fallujah.
  96 households in Saqlawiyah.
  59 households in Karma.
Key issues and Partner’s updates
  IHF projects - Critical Shelter repairs in Anbar &Salah al-Din Governorates and PDM - Tour de table - Partners

## Slide 13
UN-HABITAT – 2020 Shelter rehabilitation projects – Ongoing
Rehabilitation of Houses in Anbar
  Socio-economic survey for whole Al-Baker neighborhood, Heet district, Anbar / Completed
  Technical assessment for 177 damaged house in Al-Baker neighborhood, Heet district, Anbar / Completed
  Rehabilitation of 8 damaged houses (Category 2 and 3) in Al-Baker neighborhood, Heet district, Anbar / Completed
  Rehabilitation of 169 Houses (Category 1, 2 and 3) in Al-Baker neighborhood, Heet district, Anbar / Under procurement
Key issues and Partner’s updates
  IHF projects - Critical Shelter repairs in Anbar &Salah al-Din Governorates and PDM - Tour de table - Partners

## Slide 14
UN-HABITAT – 2020 Shelter rehabilitation projects – Ongoing
Rehabilitation of Houses in Salah al-Din
  Socio-economic survey for whole Yathrib subdistrict, Balab district, Salah al-Din / Ongoing
  Technical assessment for 200 damaged house in Yathrib subdistrict, Balab district, Salah al-Din / Completed
  Rehabilitation of 7 damaged houses (Category 2 and 3) in Yathrib subdistrict, Balab district, Salah al-Din / Completed
  Rehabilitation of 52 damaged houses (Category 2 and 3) in Yathrib subdistrict, Balab district, Salah al-Din / Under procurement
Key issues and Partner’s updates
  IHF projects - Critical Shelter repairs in Anbar &Salah al-Din Governorates and PDM - Tour de table - Partners

## Slide 15
AOB – Shelter Cluster