Guidance & Vetting Criteria for projects for the HRP 2021

important Reminders

- The oPt 2021 Project upload is to be undertaken from 4 October through 16 October.

- Partners should ensure that they upload to the correct year and country portfolio (2021 oPt).

- Clusters to share the dates of their vetting meetings with OCHA (Anastasia: anastasia.gorbatova@un.org) by 8 October.

- Cluster project vetting to be undertaken from 18 October through 30 October. Clusters should organize their vetting panel meetings sufficiently in advance of the deadlines to allow for partners, whose projects are returned for amendments/additional information, to be revised and re-submitted for final review by 30 October, in order to enable their ability to appeal the decision on their project by 2 November.

- Clusters  to approve projects by 6 November.

- Clusters may organize their vetting process as they see fit (i.e. separate panels for Gaza Strip and West Bank, or one national-level joint panel).

- Vetting panels should be established by the Clusters in advance, and include, as a minimum: the Cluster Coordinator, an INGO, a local/national NGO, a UN agency and, the Cluster Protection and Gender Focal Points. A line-ministry representative may act as an advisor (non-voting member) to the vetting panel, to ensure consistency with policies and standards and promote synergies with national programmes where appropriate. OCHA focal points will support each Cluster vetting panel as active advisors. (Please contact OCHA if you need clarification on who is your focal point).

- For projects with activities that span more than one Cluster (for example, multi-sectoral projects), Cluster Coordinators should:

  - Inform implementing partners that, if they are submitting a cross-Cluster project, they need to identify the relevant Clusters in advance of the project submission to facilitate the process.

  - The Primary Cluster, identified during project upload, will make the neccessary arrangements to share the project with the  other relevant Cluster/s, who will need to review the technical elements pertinent to their area of work, ideally in advance of the vetting of the project. The Primary Cluster Coordinator should copy in OCHA (Alicia: moore23@un.org and Anastasia: anastasia.gorbatova@un.org) when sharing the project with other Clusters.

  - It is not necessary for several vetting panels to all review the project – panel review by the Primary Cluster should be fine with just comments provided by the other relevant Cluster Coordinators.

  - If needed, the Primary Cluster will invite the other Cluster Coordinators to attend vetting panel meetings to participate actively in the vetting of those specific projects.

For any technical support, please contact Anastasia Gorbatova anastasia.gorbatova@un.org

important Reminders

- The oPt 2021 Project upload is to be undertaken from 4 October through 16 October.

- Partners should ensure that they upload to the correct year and country portfolio (2021 oPt).

- Clusters to share the dates of their vetting meetings with OCHA (Anastasia: anastasia.gorbatova@un.org) by 8 October.

- Cluster project vetting to be undertaken from 18 October through 30 October. Clusters should organize their vetting panel meetings sufficiently in advance of the deadlines to allow for partners, whose projects are returned for amendments/additional information, to be revised and re-submitted for final review by 30 October, in order to enable their ability to appeal the decision on their project by 2 November.

- Clusters  to approve projects by 6 November.

- Clusters may organize their vetting process as they see fit (i.e. separate panels for Gaza Strip and West Bank, or one national-level joint panel).

- Vetting panels should be established by the Clusters in advance, and include, as a minimum: the Cluster Coordinator, an INGO, a local/national NGO, a UN agency and, the Cluster Protection and Gender Focal Points. A line-ministry representative may act as an advisor (non-voting member) to the vetting panel, to ensure consistency with policies and standards and promote synergies with national programmes where appropriate. OCHA focal points will support each Cluster vetting panel as active advisors. (Please contact OCHA if you need clarification on who is your focal point).

- For projects with activities that span more than one Cluster (for example, multi-sectoral projects), Cluster Coordinators should:

  - Inform implementing partners that, if they are submitting a cross-Cluster project, they need to identify the relevant Clusters in advance of the project submission to facilitate the process.

  - The Primary Cluster, identified during project upload, will make the neccessary arrangements to share the project with the  other relevant Cluster/s, who will need to review the technical elements pertinent to their area of work, ideally in advance of the vetting of the project. The Primary Cluster Coordinator should copy in OCHA (Alicia: moore23@un.org and Anastasia: anastasia.gorbatova@un.org) when sharing the project with other Clusters.

  - It is not necessary for several vetting panels to all review the project – panel review by the Primary Cluster should be fine with just comments provided by the other relevant Cluster Coordinators.

  - If needed, the Primary Cluster will invite the other Cluster Coordinators to attend vetting panel meetings to participate actively in the vetting of those specific projects.

For any technical support, please contact Anastasia Gorbatova anastasia.gorbatova@un.org

KEY DATES

4 October – 16 October	Project upload period by organizations.

8 October			Clusters to share dates of vetting panel meetings with OCHA.

18 October – 30 October		Cluster vetting panels.

30 October 	Vetting panels must ensure that organizations receive a confirmation on the outcome of their project/s.

2 November			Deadline for an organization to submit appeal against the panel’s decision.

6 November 			Deadline for final approval of all projects by Clusters

VETTING CRITERIA EXPLAINED

The following vetting criteria guidance accompanies the matrix provided for the vetting panels (the Excel spreadsheet).  At the end of the vetting process, the Cluster vetting panel will need to provide a summary of the outcome of the vetting process using the template provided at the end of the document.  The HC a.i. will have ultimate decision over any organisation wishing to appeal against the decision of the vetting panel.

Step 1: Review the new project’s overall relevance to the 2021 HRP and its strategic relevance to the Cluster

In order to be considered for inclusion in the HRP 2021, a new project must meet the below criteria (i.e. answers must be YES).

OVERALL 2021 HNO/HRP RELEVANCE

- The project is responding to needs identified in the 2021 HNO.

Under the “Needs” section of the project sheet, the organization submitting the project is required to reference the narrative and data from the HNO 2021, as evidence of the needs and vulnerable people the project is targeting, to be included in the 2021 HRP.

- The project must contribute to one of the 2021 Strategic Objectives.

In selecting the Cluster pre-defined activities and indicators in the Projects Module, partners will be linking the project to the Cluster Objectives, which in turn should be linked to the 2021 Strategic Objectives.

- The project must be humanitarian in nature.

While the narrative of the HRP document will provide information on linkages and synergies with development, HRP projects must remain humanitarian, i.e. the primary goal of the project must be to save lives (and/or remedy, mitigate or avert an immediate and direct humanitarian risk faced by a community (e.g. displacement; food insecurity; waterborne disease; etc.) or population group (e.g. children, girls with disabilities, adolescent boys, women). Early recovery or development projects will thus not be accepted in the HRP 2021.

- The project’s geographical scope must be within the HRP parameters

The project’s geographical area of implementation (i.e where the project will be implemented) must be in the following areas:

- The Gaza Strip (all areas)

- In the West Bank:

- East Jerusalem

- Hebron H2

- Area C

- Areas A&B (activities implemented in Areas A&B will need to be justified using the Cluster vulnerability criteria/index that informed which people will be considered in need and why the Cluster will prioritise activities in their 2021 response plan).

NEEDS BASED

- The project must be based on identified humanitarian needs

Projects should be based on a relevant and recent needs assessment. Projects based on needs assessments, which are older than 12 months and/or for which the methodology is questionable, should not be considered, unless assessments are unavailable for a target group or for addressing needs that have been identified as priority in the HNO 2021. This should have been highlighted as an information gap by the relevant Cluster, to be addressed prior to the HNO 2022. Projects should target the vulnerable group(s) identified and prioritized in the HNO 2021, while not duplicating existing activities and/or targeting communities whose needs are already completely addressed by ongoing or recent programmes.

- Project targets vulnerable group(s) identified in the HNO

Projects should demonstrate their activities are targeting the vulnerable groups identified in the 2021 HNO.

STRATEGIC RELEVANCE TO CLUSTER

- The project must contribute to the Cluster response plan through its activities/indicators

Through a feature in the Project Module, partners will have to select in their project sheets the relevant activities and indicators provided by the Clusters in a pre-defined drop-down list.

- The partner must be an active Cluster/sector member

The appealing organization must be an active member of the oPt Cluster/sector coordination structures. A few markers of active Cluster/sector membership include:

- The partner demonstrates an understanding of the duties and responsibilities associated with membership in a Cluster and commits to consistently engage in the Cluster’s collective work as well as the Cluster’s plan and activities.

- The partner attends Cluster meetings regularly.

- The partner reports to the Cluster when required (including data for monitoring reports, 4Ws information), and reports its humanitarian funding information to the Financial Tracking Service (FTS).

- The project must demonstrate that it includes a sound M&E framework

Activities and indicators selected through the drop-down lists will be linked to the Cluster logframes for the HRP, to which partners are committed to report through their Cluster. In addition to the drop-down feature, partners have space in the narrative sections, as usual, to provide a description of their “activities” and “indicators”; this narrative should provide more evidence and details of the M&E framework for the project, including the role in this regard of other organisation(s) co-implementing the project, as well as mention of any relevant mechanism intended to facilitate the involvement of beneficiaries within the M&E process.

DOES THE PROJECT FULLFIL THE BASIC REQUIREMENTS?

Are all the answers to the above answered by YES? If so, please proceed. If not, the project does not meet the minimum criteria to be included.

Step 2: If the project passes the 1st level review, the vetting panel must look into the programming quality of the project design, along the below areas.

Scores shaded in grey indicate that the project meets the targeted quality threshold, which equals a score of 31, or above, out of 44 points (70% or above). Scoring and comments should be recorded in the excel sheet provided. (Projects scoring below this threshold should be returned to organizations for improvement).

- The project must have taken the Gender and Age Marker code survey

Projects should include information on gender in their narrative on needs analysis, activities and indicators. Clusters have been provided with gender guidance documents, which partners should have consulted and followed. The guidance includes information on the Gender and Age Marker code, which partners will have self-assessed in their Project’s Module project sheet application. The Gender and Age Marker code is a self-improvement tool for the partners to understand and access the level of gender and age mainstreaming in their projects.. The score range is:

- 8 points for Gender and Age Marker code 4(M) or 4(T);

- 6 points for Gender and Age Marker code 3(M) or 3(T);

- 4 points for Gender and Age Marker code 2(M) or 2(T);

- 2 points for Gender and Age Marker code 1(M) or 1(T);

- 0 points for Gender and Age Marker code 0;

- No scoring applicable for Gender and Age Marker code N/A.

- Protection mainstreaming

Partners should demonstrate a commitment to mainstreaming protection in their programme delivery, and the project sheet should have evidence of protection mainstreaming, including in the narrative sections on needs analysis, activities, M&E, and indicators, as appropriate. Partners will also answer two narrative questions to identify their level of Protection mainstreaming. The score range is:

- 8 points for full protection mainstreaming throughout the project narrative and answers to the two Protection mainstreaming questions;

- 5 points for mainstreaming in most sections/answers;

- 3 points for partial reflection of mainstreaming;

- 0 points if no protection mainstreaming in the project sheet.

- Community Engagement

Projects that enhance Community Engagement (CE) should be considered having an added value by vetting panels. (CE, often referred to as Communication with Communities (CwC), includes three components: participation, feedback and complaints, and providing information.  It is the process by which Accountability to Affected Populations (AAP) is achieved.) Community Engagement should be reflected in the project design, implementation, and monitoring and evaluation phases of a project to the extent possible. Partners will answer a number of questions through drop-down options to identify their level of Community Engagement. The score range is:

- 8 points for full reflection of Community Engagement throughout the project narrative and in the drop-down answers to Community Engagement questions;

- 5 points for reflection of Community Engagement elements in most sections/answers;

- 3 points for partial reflection of Community Engagement;

- 0 points if no evidence of Community Engagement in the project sheet.

- PSEA

Projects that will include PSEA (Prevention of Sexual Exploitation and Abuse) activities should be considered having an added value by vetting panels. Partners will answer a question through drop-down options in the projects’ module to identify their level of intergration of PSEA activities into their projects.

The score range for the question is the following:

- 8 points for full reflection of PSEA throughout the project narrative and in the drop-down answers to PSEA;

- 5 points for reflection of PSEA elements in most sections/answers;

- 3 points for partial reflection of PSEA;

- 0 points if no evidence of PSEA in the project sheet.

- Partnerships with local NGOs

Wherever possible, projects shall include partnerships with local NGOs and other national partners, such as CBOs, as implementing partners. Projects submitted directly by local NGOs will receive the highest score in this field. The score range is:

- 8 points if project is submitted by a local NGO;

- 5 points if there is evidence of a full partnership with a local NGO (each of the partners provide substantial inputs/implementation);

- 3 points if the partnership is partial (e.g. the local NGO will receive a small grant for implementation of one activity);

- 0 points if there is no partnership.

- Budget and timeframe

The project sheet should include a sound budget. Guidance on budgets was provided in the HRP/Project Module guidance document to partners. Administrative (indirect/overhead) costs should maximum be 11% of the overall total budget. Positive consideration is given to projects that have a lower administrative cost. Multi-year projects will not be considered this year and the projects should demonstrate that they can realistically be implemented within a 12-month timeframe, and if not - be returned for partner revision. For each per cent below 11% of administrative costs, the project will receive a point:

- 4 points if 7% overhead

- 3 points if 8% overhead

- 2 points if 9% overhead

- 1 point if 10% overhead

- 0 points if 11% overhead

- Project excluded if overhead is 12% or higher

Following the scoring on the ‘common’ criteria above (where a maximum of 44 points can be earned), the vetting panel will review against ‘Cluster-specific’ criteria (for a maximum of 60 points).

Step 3: Cluster-specific criteria

- Clusters need to identify  2-6 Cluster-specific criteria for the project vetting, in advance of the vetting panel, based on their Cluster response plan.

- The criteria should be weighted between 10-30 points each, for a maximum be 60 points, out of the total 104 points.

- In order to be considered for inclusion in the HRP 2021, a project must score 35 or above out of 60 points (60% or above). Scoring and comments should be recorded in the excel sheet provided. (Projects scoring below should be returned to organizations for reassessment).

Cluster criteria 1

The project includes a sound M&E mechanism  and identify relevant outcome indicators (score range: 10 - 7 - 4 - 0)

Monitoring mechanisms are clear in all stages (beneficiary selection, design, implementation, post intervention with relevant outcome indicators) 10

Missing or unclear 1 of the above  7

Missing or unclear 2   4

Otherwise    0

Cluster criteria 2

All the project activities are implementable  within the current and unforeseen COVID 19 emergency situation (Score 10, 5,0)

full consideration of COVID19 conditions 10, partial 5, no consideration 0)

Cluster criteria 3

The project addressing and integrating multidimensional vulnerabilities including COVID19, deteriorated socioeconomic conditions, possible annexation and displacement and targeting specific vulnerable groups such as PWDs, Elderlies, FHHs... (score range: 10 - 0). more focused vulnerabilities analysis will take higher scores.

Cluster criteria 4

The Project demonstrates value for money related to activity and impact on need for recurrent

support (score range: 10 - 0)Direct inputs to beneficiaries (supplies, materials, cash,…)

70% or less  0

1 score per 1% above 70 up to 10 maximum

Cluster criteria 5

The project includes strengthening of preparedness, resilience, sustainability and protective measures (score range: 10 - 7 - 4 - 0)

full considerations 10

3-4 considerations  7

2 considerations  4

Otherwise  0

Cluster criteria 6

The project demonstrates clear beneficiary involvement in all stages: Needs assessment, design, implementation and monitoring (score range: 10 - 7 – 4 - 0)

All 4 levels above  10

Only 3 levels   7

Only 2 levels   4

Otherwise   0

PROJECT: ACCEPTED,  RETURNED TO PARTNER FOR IMPROVEMENT, REJECTED or APPEALED

The vetting panel chair will record the vetting outcome for each project including the agreed feedback from the vetting committee in the excel sheet along with the final score. Clusters must then determine the vetting outcome (accepted, rejected or returned for partner improvement). The following provides guidance:

ACCEPTED: A project is accepted and no more changes are needed from the partner to their project, if the project has:

- Fulfilled the requirements in the 1st stage of the review;

- Met the threshold for quality for “Common” criteria in the 2nd stage of the project review (i.e. received scores that were shaded in grey); and

- Scored at least 60% on the “Cluster” criteria in the 3rd stage of the review.

RETURNED TO PARTNER FOR IMPROVEMENT: A  project will be returned to the partner for improvement if the project has fulfilled the basic requirements in the 1st step, but the partner needs to address concerns raised by the panel on questions related to the “Common” criteria or the “Cluster” criteria.

The Cluster panel must set a clear deadline for partners to undertake these revisions and/or address concerns raised by the panel, in order for the partner to re-submit the project in good time to allow the panel to review it a final time. The panel should note that the deadline for an organization to appeal against the panel’s decision is COB 2 November and, therefore, the panel will need to ensure the organization receives a confirmation on the outcome of their project/s by COB 30 October.

The project will be accepted if the panel deems it has addressed all the concerns and made the necessary revisions. Should the partner unsuccessfully address the feedback provided by the panel the project will be rejected.

REJECTED: The project is outright rejected should it fail to fulfill the basic requirements in the 1st step.

APPEALS PROCESS (for rejected projects)

Appeals against vetting panel decisions should be conveyed to OCHA oPt by COB, Monday 02 November, for onward communication to the HC a.i. Appeals received after this date will not be considered.

In their email to OCHA, the organization should outline its justification for appealing against the panel’s decision, noting the panel’s feedback and its rebuttal.  Appeals will be reviewed by the HC a.i., who holds final decision-making authority; consultation with OCHA, Cluster Coordinators, and Cluster Lead Agencies, will be carried out, as needed.

Send appeals by email to moore23@un.org and anastasia.gorbatova@un.org.

Please send appeals by email to moore23@un.org and anastasia.gorbatova@un.org.