| #### Shelter Cluster Vanuatu – Meeting Notes |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| #### Meeting: | #### Shelter Cluster Vanuatu - Cluster Meeting |  |  |  |  |
| #### Date: | #### 31 October 2023 | #### Time: | #### 2pm-3.30pm |  |  |
| #### Meeting Facilitator: | #### Marta Piqueras | #### Location: | VMGD conference room |  |  |
| ### Agenda |  |  |  |  |  |
| Attendance: Name; Organization; Role; Email Address; Contact. Marta Piqueras; IFRC; Pacific Shelter coordinator; Coord.pacific@sheltercluster.org. Samandra Gete; VRCS; Shelter Cluster co-lead; coord1.vanuatu@sheltercluster.org; 5610805. Jill Aru; CARE; Maewo response co-lead; Jill.aru@careint.org; 7798945. Asheena Luaukon; DFAT; Senior Program manager Response; Sheena.luaukon@dfat.gov.au; 5511340. Emily Lyous; DFAT; Crises response team; emily.lyous@dfat.gov.au; 761417516209. Troika Kalman; Helper 1; Operation officer; torikakalman@gmail.com; 7659132. Augustine Gare; VRCS; diastercoordinator@redcrossvanuatu.com; 7747847. Rico Aru; ADRA; RicoAru@adra.org.vu; 7730703. Hellen Bani; IOM; Project Officer; hbani@iom.int; 7740942. Humility Boala; VDPA; DRR support officer; humilityBoala.vdpa@gmail.com; 7389751. Dea Bickey; Save the children; Dea.bickey@savethechildren.org.au; 5437720. Devny Toa; DVAP; Senior Housing & settlement officer; tdevny@vanuatu.gov.vu; 73066579. Timoi vosailagi; Field Ready; Field Engineer; Tim.vosailagi@fieldready.org; 77712271. Anna Spethman; USAID/BHA; Info Officer; aspethman@usaid.gov. Ben Hemingway; USAID/BHA; Reginal Director; bhemingway@usaid.gov. Mark Mc Caul; IFRC; Ops manager; Mark.mccaul@ifrc.org. |
| Topic |  |  |  |  |  |
| Agenda: - Update from NDMO on damage assessments - Update from partners on visit to affected areas and insights. - Minimum package of shelter assistance, considering minimum humanitarian standards. - Agencies Response plans/Gaps - Update stocks/ dispatching/distributions. - Logistics support from NDMO/RFA - AOB NDMO update on assessment: - Assessment in Penama and Malampa is still ongoing. - In South East Pentecost, 70% of households were destroyed, according to partners. - In North Pentecost, 75% of households were destroyed, according to visual assessment on ground from VRCS. - NDMO requested that VRCS share its assessment data with NDMO. Explanation of Minimum standard shared with Partners: - Shelter Coordination presented the minimum standards for shelter & settlements to partners. - Discussion on minimum package of assistance for HH with houses totally or heavily damaged: Emergency shelter assistance: 2 tarps and 1 shelter tool kit per HH Essential HH Items: 1 kitchen set, 3 blankets and 2 sleeping mats per HH. - VRCS and Save the Children are planning to distribute the complete package, while ADRA and CARE will focus on emergency shelter assistance (tarps and shelter tool kits). If any agency identifies that will not be able to complete the emergency assistance, will communicate it to the Shelter Cluster Coordination Team and possible support options might be explored with all partners. - It is emphasized the importance of providing safe shelter awareness and orientation to target communities on how to use the tarpaulins and shelter tool kits, since the start of the operations. Explanation of the target priority areas and update on target areas for each partner: - Cluster coordination reviewed the target priority areas and updated the target areas for each partner and identify the Gaps. Number of HH affected to be revised when more data will become available. Priority; Province; Island; Area Council Name; Total HH; Total Pop; Impact; Households affected; Pop affected; AGENCY. Priority 1; MALAMPA; Ambrym; North Ambrym; 871; 3,661; 75%; 653; 2,746; ADRA(with NDMO stocks). Priority 1; MALAMPA; Ambrym; South East Ambrym; 542; 2,063; 75%; 407; 1,547; VRCS. Priority 1; MALAMPA; Ambrym; West Ambrym; 669; 2,789; 75%; 502; 2,092; VRCS. Priority 1; MALAMPA; Malekula; South East Malekula; 1,180; 5,070; 75%; 885; 3,803. Priority 1; MALAMPA; Malekula; South Malekula; 1,065; 4,644; 75%; 799; 3,483. Priority 1; MALAMPA; Malekula; South West Malekula; 895; 3350; 75%; 671; 2,513. Priority 1; MALAMPA; Paama; Paama; 436; 1,475; 75%; 327; 1,106; VRCS. Priority 1; PENAMA; Ambae; East Ambae; 520; 1,943; 75%; 390; 1,457; VRCS. Priority 1; PENAMA; Ambae; South Ambae; 307; 1,131; 75%; 230; 848; VRCS/STC??. Priority 1; PENAMA; Maewo; North Maewo; 678; 2,913; 75%; 509; 2,185. Priority 1; PENAMA; Maewo; South Maewo; 414; 1,997; 75%; 311; 1,498; CARE. Priority 1; PENAMA; Pentecost; Central Pentecost 1; 805; 4,902; 75%; 604; 3,677; VRCS. Priority 1; PENAMA; Pentecost; Central Pentecost 2; 1,373; 3,617; 75%; 1,030; 2,713; VRCS. Priority 1; PENAMA; Pentecost; North Pentecost; 1,505; 6,898; 75%; 1,129; 5,174; VRCS. Priority 1; PENAMA; Pentecost; South Pentecost; 1,305; 5,969; 75%; 979; 4,477; CARE. Priority 1; SHEFA; Epi; Varsu; 499; 2,408; 75%; 374; 1,806. Priority 1; SHEFA; Epi; Vermali; 559; 2,401; 75%; 419; 1,801; ADRA(with NDMO stocks). Priority 1; SHEFA; Epi; Vermaul; 397; 1,741; 75%; 298; 1,306. Priority 1; TORBA; Merelava; Merelava; 154; 690; 75%; 116; 518; VRCS. Priority 2; MALAMPA; Malekula; Central Malekula; 1,546; 6,516; 50%; 773; 3,258. Priority 2; MALAMPA; Malekula; North East Malekula; 1,645; 6,969; 50%; 823; 3,485; VRCS. Priority 2; MALAMPA; Malekula; North West Malekula; 1,214; 5,414; 50%; 607; 2,707. Priority 2; PENAMA; Ambae; North Ambae; 649; 2,589; 50%; 325; 1,295; VRCS. Priority 2; SANMA; Malo; East Malo; 513; 2,071; 50%; 257; 1,036. Priority 2; SHEFA; Epi; South Epi; 367; 1,606; 50%; 184; 803. Priority 2; SHEFA; Makimae; Makimae; 276; 1,156; 50%; 138; 578; VRCS. Priority 2; SHEFA; Nguna; Nguna; 478; 1,914; 50%; 239; 957. Priority 2; SHEFA; North Tongoa; North Tongoa; 371; 1,666; 50%; 186; 833; VRCS. Priority 2; SHEFA; Tongariki; Tongariki; 232; 1,099; 50%; 116; 550; VRCS. Update of the movement of stocks and distribution on ground by each partner: - ADRA reported that Area Administrator identified 939 households as heavily damaged or destroyed in North Ambrym and had distributed only tarps to 237 households. They will use NDMO stock to continue with the distribution of traps and supplement with shelter tool kits. - CARE reported that it was working with VRCS to distribute 165 tarps from VRCS stock, in South Pentecost. - Save the Children reported that it had moved 176 tarps to CP1, but they had not yet been distributed. Also shelter tool kits, but didn’t provide the quantity. Intention is to supplement the package with Essential Household items. Possible joint proposal with AHP partners to support the response. - VRCS reported that it was sending 3000 tarps to Pentecost, 500 tarps to South East Ambrym, 500 tarps to West Ambrym, and 100 tarps to Torba. Logistics support from NDMO/RFA - SC Coordination Team reminded partners about the stock available at NDMO warehouse for distribution. List of items in country as of 1 November (including the USAID-BHA support) as follows (Australia/UK/France/NZ/USAID-BHA): Item; In; Out; Balance. Shelter Tool Kits; 1966; 432; 1774. Family Kitchen Kits; 240; 0; 240. Tarps; 3772; 270; 3502. Mattress; 1200; 0; 1200. Blanket; 1200; 0; 1200. - Reminder: To request any of the stocks at NDMO warehouse and/or transport of items, partners should communicate details (number and type of items/island to be shipped to) to the SC Coordination Team who will issue a Request for Assistance to Logs Cluster. AOB - IFRC Emergency Appeal approved on support to VRCS approved: 2,5 million CHF, target 6,000 HH in 12 months, for Shelter, Health, WASH and Livelihoods assistance - USAID/BHA: Support to NDMO with 2000 tarps and 1000 shelter tool kits. ETA: 6-7 November. - Field Ready: Field Ready is planning to provide WASH assistance in Pentecost and Ambae, and wants to coordinate with agencies working in those islands. They will initially focus on evacuation centers, but will also provide support as household level. Below partners in those areas: Province; Island; Area Council Name; AGENCY. PENAMA; Ambae; East Ambae; VRCS. PENAMA; Ambae; South Ambae; VRCS/STC. PENAMA; Pentecost; Central Pentecost 1; VRCS. PENAMA; Pentecost; Central Pentecost 2; VRCS. PENAMA; Pentecost; North Pentecost; VRCS. PENAMA; Pentecost; South Pentecost; CARE. - It is reminded to all partners the importance of coordinate with WASH partners to ensure that the affected families have access also to WASH facilities at HH level. - Update for Helper 1: - Helper 1 is at South Pentecost and will move to Santo on Friday. - From November 13-19, Helper 1 will be in Penama, Malampa, and Torba. - If any partners need to move NFIs (little capacity) or passengers in these provinces, they should contact Helper 1. A detailed plan for the scheduled trips will be shared. |
| ### Action Items |  |  |  |  |  |
| Action |  |  |  | Owner | Due Date |
| - VRCS: Share assessment data with NDMO. |  |  |  | VRCS/SCV |  |
| - Partners: Coordinate with NDMO and each other to ensure that all affected households are reached. |  |  |  | Partners/SCV |  |
| - Shared the draft distribution plan with all partners. |  |  |  | SCV |  |

| Next Meeting |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Date: | 3 November 2023 | Time: | 2pm | Location: | NDMO Conference Room |
| Comment: | - |  |  |  |  |