| #### Shelter Cluster Vanuatu – Meeting Notes |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| #### Meeting: | #### Shelter Cluster Vanuatu - Cluster Meeting |  |  |  |  |
| #### Date: | #### 3rd November 2023 | #### Time: | #### 2pm-3pm |  |  |
| #### Meeting Facilitator: | #### Marta Piqueras | #### Location: | VMGD conference room |  |  |
| ### Agenda |  |  |  |  |  |
| Attendance: Name; Organization; Role; Email Address; Contact. Ken Mana; NDMO; Shelter lead; kmana@vanuatu.gov.vu; 7305387. Marta Piqueras; IFRC; Pacific Shelter coordinator; Coord.pacific@sheltercluster.org. Samandra Gete; VRCS; Shelter Cluster co-lead; coord1.vanuatu@sheltercluster.org; 5610805. Alice Kalontano; DFAT; Senior Program manager; Alice.kalontano@dfat.gov.au; 5511341. Emily Lyous; DFAT; Crises response team; emily.lyous@dfat.gov.au; 761417516209. Liku Jimmy; NZHC; Senior Program Manager; Liku.jummy@mfat.gov.com; 5500933. Augustine Gare; VRCS; diastercoordinator@redcrossvanuatu.com; 7747847. Vanesa organo; IOM; IOM DECM Cluster; vorgano@iom.int; 7116799. Hellen Bani; IOM; Project Officer; hbani@iom.int; 7740942. Ben Hemingway; USAID/BHA; Reginal Director; bhemingway@usaid.gov. |
| Topic |  |  |  |  |  |
| Agenda: - Update on National Response plan- Shelter Cluster/ Agencies coverage and gaps - Stock available at NDMO warehouse for distribution/ Shelter Cluster Distribution Plan/ Updates on NDMO Logs / Coordination with logs cluster - Updates from partners on distributions. - AOB The Shelter Cluster is working to develop a response plan that focuses on building using local materials. This will help to reduce the reliance on imported materials and make the response more sustainable. The Cluster is also working to build the capacity of local partners to construct shelters using local materials. The Shelter Cluster is requesting that partners share their Assessment Data with NDMO. This will help to ensure that all partners are using the same stock and that there is no duplication of efforts. Save the Children is partnering with VRCS to support the Shelter Cluster response. VRCS has suggested helping NDMO to distribute in Pamma with NDMO stock and human resources from VRCS. VRCS will be responsible for the wellbeing of all of its staff. RFA, Partners need to pass through the Shelter Cluster before going to logistics. This will help to ensure that the Shelter Cluster is aware of all distributions and that there is no duplication of efforts. Partners can contact the Shelter Cluster coordination team at kmana@vanuatu.gov.vu ,coord1.vanuatu@sheltercluster.com, Coord.pacific@sheltercluster.org to request distribution support. Agencies that need to request NFIs from the Shelter Cluster should state a reason why they need the NFIs and the date for the NFIs to be expected at the sites. This will help the Shelter Cluster to prioritize requests and ensure that NFIs are distributed to those who need them most. Save the Children is flying to EPI and is willing to support NDMO distribution in Epi. Save the Children will also support 44 schools affected by TC Lola. Save the Children will coordinate with ADRA to distribute on Epi. DECM is deploying officers to the PEOCs who are doing weekly monitoring of evacuation centres. The Shelter Cluster reminds partners to update on the 3Ws: Who, What, and Where. This will help the Cluster to track distributions and ensure that all needs are being met. |  |  |  |  |  |
| ### Action Items |  |  |  |  |  |
| Action |  |  |  | Owner | Due Date |
| - VRCS: Share assessment data with NDMO. |  |  |  | VRCS/SCV |  |
| - Coordinate with NDMO and each other to ensure that all affected households are reached. |  |  |  | Partners/SCV |  |
| - Shared the draft distribution plan with all partners. |  |  |  | SCV |  |

| Next Meeting |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Date: |  | Time: |  | Location: |  |
| Comment: | - |  |  |  |  |