Meeting Minutes

Location: MS Teams

Time: 13:00 – 14:30 Sudan time

Attendance: MS Teams attendance sheet annexed at the end of the document.

Agenda:

- Situation Update

- Roundtable on Achievements & Operational Plans

- Reporting

- TWIG on ESKs

- HRP Project Revision Progress

- AOB

Situation Update:

- The situation in Sudan is becoming increasingly critical, with the number of internally displaced persons (IDPs) continuing to rise steadily, now reaching an estimated 1.4 million. The outflow of individuals from Sudan has slowed due to more stringent visa constraints, which is particularly exacerbating the situation in Halfa.

- A recent ceasefire was initiated on June 10, intended to last for 24 hours. Although there was a reported decrease in combat during this period, the ability of aid organizations to deliver assistance was still limited. The UNHCR's efforts to relocate supplies from their warehouse in Khartoum were again hampered by a resurgence of fighting.

- Violence persists unabated in various regions of Darfur, where residents are under constant threat from armed militias, with some fighters allegedly originating from neighboring countries. Disturbing reports continue to emerge from El Genina and other areas within Darfur.

- However, amidst the turmoil, some progress is being made in prepositioning of shelter and NFI supplies in Chad. Establishment of common UN cross-border operations is underway in Chad, however formal agreement from the Sudanese side is yet to be received. But two organizations, Solidarites International and MSF, are proceeding with transportation of assistance to Chad with letters of approval from Wali and HAC.

- In addition to the existing instability, new conflict dynamics are emerging in South Kordofan, with SPLM-N now engaging in fighting against SAF. There are growing concerns that this involvement from various armed factions will prolong the conflict.

- On a positive note, response is continuing in the northern and eastern areas which are safe, and OCHA is he hence moving forward with another SHF allocation. The $18 million SHF Reserve Allocation will be distributed via state-level inter-sector coordination forums – A ICCGs. The targeted states for these allocations include White Nile, Northern, River Nile, Aj Jazeera, Gadaref, Red Sea, and additional southern regions where ground reports suggest there are approximately 112,000 IDPs present.

- White Nile has been allocated a significant portion of the fund due to the large number of IDPs, while Halfa has also been prioritized given the severe situation there. For the two states that don’t have area ICCG mechanisms, Northern and River Nile, national-level meetings have already taken place. Partners have been invited to confirm their presence in these states in order to participate in the funding allocation discussions. In the case of River Nile, the Shelter and Non-Food Items (NFI) cluster received $400,000, which will be implemented by either Save the Children or Muslim Hands. In the Northern state, another $400,000 has been allocated for Shelter and NFI, with the UPO set to implement these funds.

- Since decisions for the remaining states will be made at A-ICCGs, it is crucial for partners to take an active role in these meetings to advocate for the allocation to the Sheltering/NFI Cluster, should they possess the capacity to carry out Shelter and NFI interventions.

- This allocation is different from the more flexible 48-hour one. Partners are required to submit a proposal to SHF, which can take up to several weeks before finalization. In contrast, the 48-hour allocation prepositions funds without a full proposal, allowing organizations to promptly respond in hotspot areas when opportunities arise.

- HDPO reported from Kampala, Uganda, indicating that they have an active project in El Fasher, North Darfur, funded by the IOM and USAID. HDPO has a rapid assessment report which it plans to share, detailing new arrivals of IDPs from the northern part of El Fasher to the southern part. As HDPO is not eligible for SHF funding, they expressed eagerness to partner with organizations receiving SHF funds to better address the needs of the newly arrived IDPs. The Cluster Coordinator encouraged this, highlighting the benefit of diversifying partners and improving the partner landscape.

- Muslim Hands proposed maintaining a list of national NGOs interested in partnering with international NGOs or UN agencies. He suggested that the Shelter and NFI cluster could put up a list of these NGOs to foster partnership and maximize outreach. The Cluster Coordinator agreed and mentioned that a request for such a list was made to the National NGO Forum chaired by UPO CD. The Cluster Coordinator will follow up with NNGO Forum for a comprehensive list of local partners.

- ADRA advocated for inclusion of Blue Nile in the SHF allocation. He reasoned that Blue Nile has a significant number of returnees from South Sudan, and additional arrivals from Khartoum. As ADRA is strong in Blue Nile and already has an SHF project running there, it would be advantageous to include Shelter and NFI activities in this state. The Cluster Coordinator noted that SHF prioritizes based on DTM IDP figures which may not always accurately reflect the ground situation, and promised to highlight this gap to SHF, as well as recommended partners to reach out to SHF for potential expansion of current SHF grants.

- National Coordinator from OCHA, expanded on SHF allocation briefing. It was noted that significant displacement and humanitarian needs had been identified in three localities of the River Nile states – Al-Matama, Shendi, and Atbara. Additional information was offered that funds would not only benefit the Shelter/NFI sector but also the Health, Nutrition, WASH, and Protection clusters.

- This additional information was acknowledged, leading to further discussion of specific activities for River Nile and Northern states. It was reported that SHF had expressed a preference for UN agencies to focus on NFIs due to their existing substantial funding for international procurement. Yet, an emphasis was placed on the equal importance of both shelter and NFI activities, pointing out the existing funding deficit for NFIs as well. The Cluster Coordinator also stressed that shelter often gets overlooked and suggested that organizations good at providing shelter assistance should prioritize these activities.

- Consideration was given to the current living conditions of most displaced individuals, with many staying in rented accommodation or with host community families. As such, cash aid was suggested as a viable option, particularly beneficial for women, children, and other vulnerable groups, in reducing gender-based violence and preserving health.

- Support for host community families providing for displaced persons was also proposed, in addition to the rehabilitation of public buildings. Simple improvements such as purchasing electrical fans for ventilation or installing partitions for privacy were suggested as impactful enhancements to living conditions.

- A successful example of group cash distributions for community-led emergency rooms was shared, credited to NRC. The feasibility of cash distribution was reinforced, pointing to the example of ADRA’s cash for shelter grants in White Nile. Encouragement was given to partners to consider all available options as outlined in the revised HRP.

Roundtable on Achievements and Operational Plans, Challenges, etc:

- The dialogue continued with a request for partners to share their recent achievements and challenges. The importance of these updates was underlined, indicating that they are incorporated into the OCHA flash updates and monthly narrative reports.

- UNHCR Update:

Distributions: 4,700 NFI kits were deployed to two camps in Kosti for distribution. In other states, they managed to distribute 410 kits out of the 800 that had been deployed to Halfa, Northern state, and 560 out of 1,500 in Madani, Jazeera state, as well as 20 kits for refugee returnees in Kassala. In addition, 850 partial NFI kits were distributed to refugee returnees in Blue Nile. In Gadaref, 300 emergency shelter kits (ESKs) were provided.

Flood Protection in White Nile: This is ongoing in six camps. Works have been completed in Jore camp and host community, while in other sites the progress varies from camp to camp, with completion percentages ranging from 30% to 60%. The goal is to complete the project across all six camps by the end of the following week, before the rainy season could impact their achievements.

Land Allocation for UmSangour Extension: Due to a large number of South Sudanese and secondary displacement, there is an accommodation capacity challenge in Kosti. However, an agreement with COR was reached to provide an additional piece of land to cope with the new arrivals. Documentation for land ownership is expected soon, after which tent installation will commence.

Abu Doloa Site Planning: The final version of the site plan for the new site in Al Jabalein locality was approved by A-COR in Kosti and is awaiting approval from national COR. Once approved, physical implementation on the ground will start. There are also plans for a site visit with WFP to check the site and prepare for the implementation and plan the mobilization of equipment.

Custom Clearance: Waivers were obtained from HAC last week for the clearance of 78,000 plastic sheets and 20 Rub Halls stuck in Port Susan. There is a plan to move these items to Kosti, Kassala, Gadaref, and Madani.

NFI Repositioning: Due to the critical situation in Sudan and losses due to looting, there are plans to airlift additional NFIs. The approved items include 24,000 blankets, 27,000 sleeping mats, 160 large plastic rolls, 2,000 solar lamps, 43,000 jerry cans, and 10,000 mosquito nets.

Challenges: UNHCR highlighted several challenges, including price and cost increases, the availability of shelter materials, cash availability (affecting distribution in Kassala, Gadaref, and White Nile), fuel, and internet communication issues. These issues have made it difficult to contact colleagues in various states over the last few days.

- CRS inquired on the kit content, Bill of Quantities (BOQ), photos, and cost of the ESKs distributed in Gedaref. There was an expressed interest in obtaining these details, as it would be useful for the revision of the ESK for Darfur. Further information was sought to determine whether the distributed kits came from existing stock within the country or if they were a part of new procurement.

- In response, NRC shared that in Gadaref, there had been an agreement with UNHCR to categorize the current ESK into four different types to better suit varying needs: (a) a Full ESK, which is the standard kit; (b) Medium Repair Kit (MRK), which is a pared-down version of the full ESK; (c) Light Repair Kit (LRK), mainly comprised of plastic sheets; and (d) Sides Repair Kit (SRK), designed for specific repair needs. This approach was taken due to a shortage of complete kits, making it necessary to tailor assistance to families based on their individual needs as determined by NRC's technical assessments.

- UNDP reports on logistical challenges they are facing with transporting items and asked for more detailed information about imports, security arrangements and precautions taken to ensure safe delivery of goods, especially to areas like Darfur, given recent incidents of looting.

- In response, UNHCR shared they are experiencing those same issues in hotspot areas, with transporters refusing to operate, as well as with lifting of items where recently as much as 20,000 full NFI kits were stolen from the central warehouse in El Obeid. In terms of imports, the recently secured customs clearance waiver from HAC will facilitate quick inflow of UNHCR stocks through Port Sudan, whereby they are proceeding with airlifting approximately 15,000 NFI kits. At the same time, UNHCR Principal Coordinator for Darfurs is in Chad working on establishing a cross-border operation. For in-country transportation, UNHCR relies on frame agreements established before April 15, while all movements of supplies are coordinated with security and Access Working Group led by OCHA.

- IOM Update: 470 NFI kits were distributed to newly displaced in El Obeid and 350 NFI kits were distributed to newly displaced in Gedaref.

- SCI has completed verification processes for the distribution of ESKs for 500 families in Port Sudan. New funding has been received to implement a small cash-for-rent program for 50 households in Gedaref. Additionally, 400 NFI kits and 400 Multi-Purpose Cash grants are to be delivered at the same location. Procurement is ongoing to support an additional 2,000 households with ESNFI.

- Additionally, SCI Highlighted an issue with UNHCR tents distributed in Port Sudan that was brought to their attention by a South Sudanese refugee. it was pointed out that tents offer limited protection from harsh Sudan climate during the peak of the summer.

- CRS is presently finalizing a proposal aimed at responding to needs in West, East, and Central Darfur. Engagement with the donor is at an advanced stage. Under the Shelter and Settlement sector, CRS intends to target 6,000 individuals with NFI kits and ESKs.

- WHH has secured funding from AA and additional internal resources, with a goal of facilitating access to cash for emergency shelter and NFI assistance in Gedaref, Khartoum, and Red Sea states. This effort will cater to approximately 3,500 households. Targeting will be determined according to each state's needs and will be executed in close coordination with cluster stakeholders.

- UPO is continuing with the distribution of S/NFI assistance to 500 households out of 8,000 newly displaced in Kalma, which is set to conclude by the end of next week. It was reported that tensions in Al Salam and Beleil localities were driving more IDPs towards Nyalla. As a result, UPO advocated for additional partnerships to meet the increasing needs on the ground.

- Regarding North Darfur, UPO reported that a large influx of IDPs had arrived in Al-Fasher from Kutum and were sheltering in public schools. He also anticipated an increase in new arrivals from the Kassab IDP camp.

- In Madani, UPO acknowledged the planning efforts of UNHCR and noted a migration trend towards Madani due to intensifying conflicts in the south of Khartoum. UPO also expressed concern about the situation in Central and West Darfur, highlighting communication challenges and critical needs. Despite the difficulties, UPO is exploring all possible opportunities to deliver assistance.

- Internews shared a social media post drawing attention to the urgent situation at Al-Shorouk School in Al-Nazir neighborhood of El Obeid, which has been transformed into a temporary IDP camp due to recent unfortunate events. The school currently shelters more than 200 families who are in dire need of living essentials and medical attention. Additionally, it was highlighted that support is needed for Mygoma orphans which were relocated to safety, in the form of blankets, mattresses, and similar. Additionally, Internews highlighted the overwhelming reports of forced evictions emerging on social media, as people are compelled to leave their homes due to ongoing violence.

- Disturbingly, reports have also surfaced of deaths due to hunger and thirst, including a case in Khartoum where two sisters passed away in their home due to lack of food and water. In areas near military operations, in central Khartoum, many remain trapped and unable to find a safe exit. Internews stressed the importance of addressing these issues as promptly as possible.

- One of the participants shared a personal story regarding the severe conditions experienced in the center of Khartoum, reflecting the general situation in the area. The participant recounted the heartbreaking experience of losing their grandmother due to starvation as she remained trapped in the house. Their grandfather, who attempted to seek help, was unfortunately shot. The family has yet to bury their grandmother due to the lack of safe access to the area.

- The participant also reported that numerous elderly individuals were trapped in residences located in the center of Khartoum, particularly near the British Council. This area has been deemed hazardous due to the proximity to the military HQ and presence of snipers on buildings. The participant further highlighted the severity of the situation, recounting reports of civilians, including children, being shot, and requests for food and water from individuals trapped in the area. The participant ended by stressing the need for mediation and body clearance, noting that the area's inaccessibility has led to deceased individuals remaining unburied, posing significant waste management challenges. The participant noted the efforts of the Red Cross but recognized that access to the area remains a significant issue.

- Acknowledging the severity of the situation, the Cluster Coordinator expressed sympathy and deep concern, as well as committed to sharing these firsthand testimonies with OCHA and raising these issues to the highest level within the HCT.

Reporting:

- The Cluster Coordinator highlighted the necessity to accurately record and update information in Activity Info, not only for the benefit of the organizations involved but also to ensure transparency for donors. She provides specific instructions for how to use the system and emphasizes the importance of maintaining updated information, such as organization focal points.

- Due to challenges with internet, partners have a multiplicity of options to report their achievements:

- Directly inputting data into Activity Info – links to access the database, training resources, and register of current reporting focal points are provided through email and included in the presentation.

- Completing and offline Excel Sheet – the Bulk Upload Form which is then shared through email.

- WhatsApp Group – sending brief updates on the Cluster WhatsApp group, which may prompt further bilateral discussions for more details.

- A sector-specific dynamic dashboard (PowerBi), public on the GSC website, was presented to participants to showcase the summary of most recent achievements reported in ActivityInfo. The Cluster Coordinator provided examples of how to filter the dashboard by specific population groups or indicators and emphasizes the importance of entering all information correctly to ensure a good picture for partners, donors, media and general public.

- The Cluster Coordinator presented an additional method for organizations to share narrative reports and pictures: a link found in the email signature that leads to a file dropbox (https://eu.jotform.com/form/231534447450352). This is an alternative to sharing reports via email and is designed to be more accessible and convenient.

- The Cluster Coordinator encouraged the submission of both quantitative data (through Activity Info) and qualitative data (through narrative reports and pictures), explaining that this combination gives a fuller picture of the work being done on the ground. The narrative elements and images offer a more human perspective on the data, providing insight into the impact of the work and the context in which it is being done.

- Finally, the Cluster Coordinator introduced the WhatsApp group (https://chat.whatsapp.com/LAizFt8047oGd5EiYZSgNS), as a communication tool to keep all members updated in light of telecommunication difficulties. This group is designed for everyone involved to stay informed about the situation on the ground, share achievements, difficulties, photos, and any relevant training opportunities or technical guidance.

- The Cluster Coordinator urged active participation, but also underlined the need to respect the group's confidentiality due to the potential risk that some shared information may pose to the operations, especially regarding the movement of supplies.

TWIG:

- The Cluster Co-Coordinator announced the formation of the Technical Working Group (TWIG) dedicated to the review and improvement of Emergency Shelter Kits (ESKs) given the changing context in Sudan. The group's tasks will include reviewing the existing design, creating alternative options, and exploring potential new solutions, always considering the challenging operating conditions.

- The TWIG will be chaired by the Shelter & NFI Co-Coordinator and will meet online every two weeks over a span of three months. Participants ideally will have technical expertise, though others with relevant experience are also welcome. It's beneficial for members to have field experience, local context understanding, and direct access to the affected populations.

- The group members are expected to devote at least 20 working days to the group's activities. The minutes from their meetings will be shared with the group members and posted on the Global Shelter Cluster website. The final products, such as reviewed ESK designs or proposed alternatives, will be submitted to the SAG (Strategic Advisory Group) for approval and then circulated to Shelter Cluster partners.

- Interested participants can sign up here: https://enketo.unhcr.org/x/cxbFLXq0.

- The key outcomes expected from the TWIG include the production of technical drawings, specifications and BoQs for diverse emergency shelter options, as well as the production of a Technical Guidance Note on the construction and disaster risk reduction.

- The guiding principles for the group's work emphasize the need for market availability, climate appropriateness, safety and dignity, cultural appropriateness, environmental friendliness, cost-effectiveness, practicality, and scalability in the design and implementation of the ESKs. These principles aim to ensure that the shelters are not only safe and suitable for the people using them but also practical and cost-effective from an implementation perspective.

- Cluster members have agreed to shift to a bi-weekly meeting schedule, alternating between the main Cluster and TWIG meetings, reducing the burden of too many meetings while still maintaining consistent communication and progress.

HRP Revision:

- The Cluster Coordinator provided an update on the progress of the HRP project revision process. The projects by the organizations highlighted in green have been approved, while those in yellow are still under review, awaiting approval from other cluster coordinators.

- OCHA is working to expedite this process, and once all approvals are in place, the projects will be published publicly.

End.

Participants:

| Name | First Join | Last Leave | In-Meeting Duration | Email |
| --- | --- | --- | --- | --- |
| Iva Vavic | 6/12/23, 12:50:39 PM | 6/12/23, 2:53:23 PM | 2h 2m 43s | vavic@unhcr.org |
| Susan Mulievi | 6/12/23, 12:50:31 PM | 6/12/23, 1:22:39 PM | 8m 53s | susan.mulievi@nrc.no |
| Manahil Omer | 6/12/23, 12:50:33 PM | 6/12/23, 12:50:57 PM | 24s |  |
| Ayah Omar | 6/12/23, 12:52:10 PM | 6/12/23, 2:15:58 PM | 1h 16m 43s | ayah.omar@etharrelief.org |
| collaborativeforpeace@gmail.com | 6/12/23, 12:57:39 PM | 6/12/23, 2:53:18 PM | 1h 55m 39s |  |
| Kiden stella Jacob | 6/12/23, 12:59:25 PM | 6/12/23, 2:53:23 PM | 1h 53m 57s |  |
| Waweru Ndungu | 6/12/23, 1:00:19 PM | 6/12/23, 2:53:23 PM | 1h 53m 3s | ndunguw@unhcr.org |
| Denis Walter Ojok | 6/12/23, 1:00:23 PM | 6/12/23, 2:53:15 PM | 1h 52m 51s | denis.ojok@drc.ngo |
| Lopez, Miriam | 6/12/23, 1:00:30 PM | 6/12/23, 2:53:07 PM | 1h 52m 36s | Miriam.Lopez@crs.org |
| Praveen Pravind Kumar | 6/12/23, 1:00:35 PM | 6/12/23, 2:24:48 PM | 1h 24m 13s | pkumar@sd.goal.ie |
| Oyuyo, Erick | 6/12/23, 1:00:57 PM | 6/12/23, 2:47:44 PM | 1h 45m 11s | Erick.Oyuyo@crs.org |
| Moin Muqat | 6/12/23, 1:01:15 PM | 6/12/23, 2:53:08 PM | 1h 51m 53s | muqat@unhcr.org |
| Ahmed Dawelbeit/HDPO CD | 6/12/23, 1:01:30 PM | 6/12/23, 1:03:05 PM | 1m 35s |  |
| SUD - Program Coordinator ¦ Jojanneke Spoor | 6/12/23, 1:02:04 PM | 6/12/23, 2:53:23 PM | 1h 51m 18s | prog.coo@solidarites-sudan.org |
| Eva Sztacho | 6/12/23, 1:03:02 PM | 6/12/23, 2:53:10 PM | 1h 50m 7s | Eva.Sztacho@concern.net |
| Ahmed Dawelbeit {HDPO} = CD (Guest) | 6/12/23, 1:03:51 PM | 6/12/23, 2:53:08 PM | 1h 49m 16s |  |
| Mohammed Gimish | 6/12/23, 1:04:00 PM | 6/12/23, 2:35:43 PM | 1h 23m 23s | gimish@un.org |
| Vincent - ADRA | 6/12/23, 1:04:07 PM | 6/12/23, 2:53:23 PM | 1h 49m 16s |  |
| Maysa Al-Aqil | 6/12/23, 1:05:09 PM | 6/12/23, 1:43:41 PM | 38m 31s |  |
| Rodney Shamoun | 6/12/23, 1:05:13 PM | 6/12/23, 2:53:08 PM | 1h 47m 54s | rodney.shamoun@nrc.no |
| Osman Elmakki oelmakki@usaid.gov (Guest) | 6/12/23, 1:05:52 PM | 6/12/23, 2:53:15 PM | 1h 47m 22s |  |
| Fatima Ahmed Altahir | 6/12/23, 1:06:18 PM | 6/12/23, 2:35:04 PM | 1h 28m 46s |  |
| Mauro Costa (COOPI) (Guest) | 6/12/23, 1:06:49 PM | 6/12/23, 1:52:30 PM | 45m 41s |  |
| Hingorani, Dipti | 6/12/23, 1:10:57 PM | 6/12/23, 2:53:23 PM | 1h 42m 26s | dipti.hingorani@savethechildren.org |
| Asia Kambal | 6/12/23, 1:11:26 PM | 6/12/23, 2:46:41 PM | 1h 25m 13s | akambal@INTERNEWS.ORG |
| Mohammed Alhaj | 6/12/23, 1:11:37 PM | 6/12/23, 2:14:08 PM | 46m 18s | Mohammed.Alhaj@concern.net |
| Shadrack Mutiso | 6/12/23, 1:12:04 PM | 6/12/23, 2:33:35 PM | 1h 21m 31s | Shadrack.Mutiso@welthungerhilfe.de |
| Ibrahim Rahma | 6/12/23, 1:13:29 PM | 6/12/23, 2:53:23 PM | 1h 39m 53s | Ibrahim.Rahma@welthungerhilfe.de |
| Adeel Qaiser (Guest) | 6/12/23, 1:14:09 PM | 6/12/23, 1:57:00 PM | 42m 51s |  |
| Mahmoud Elhaj | 6/12/23, 1:14:27 PM | 6/12/23, 2:53:23 PM | 1h 38m 56s | Mahmoud.Elhaj@welthungerhilfe.de |
| MOHAMED Omer | 6/12/23, 1:15:22 PM | 6/12/23, 2:25:07 PM | 1h 7s | oaltyeb@iom.int |
| Behailu (Guest) | 6/12/23, 1:17:19 PM | 6/12/23, 2:31:57 PM | 1h 14m 38s |  |
| Abeer Abdulrahman | 6/12/23, 1:21:32 PM | 6/12/23, 2:06:06 PM | 14m 1s |  |
| Elmutaz Raziq | 6/12/23, 1:22:05 PM | 6/12/23, 2:53:23 PM | 1h 31m 17s |  |
| Adil Adam (NOHS) | 6/12/23, 1:23:04 PM | 6/12/23, 2:53:23 PM | 1h 30m 18s |  |
| Ibrahim Modi, UPO | 6/12/23, 1:26:09 PM | 6/12/23, 1:43:58 PM | 17m 49s |  |
| Pascal Rukundo | 6/12/23, 1:28:16 PM | 6/12/23, 2:53:23 PM | 1h 10m 17s | rukundop@unhcr.org |
| Manahil Omer | 6/12/23, 1:29:55 PM | 6/12/23, 2:49:11 PM | 1h 19m 16s |  |
| Mohamed Juma | 6/12/23, 1:30:15 PM | 6/12/23, 1:33:04 PM | 2m 49s | juma18@un.org |
| Azhar | 6/12/23, 1:31:40 PM | 6/12/23, 2:53:10 PM | 1h 21m 29s |  |
| Omima Musa | 6/12/23, 1:35:49 PM | 6/12/23, 2:53:19 PM | 1h 17m 30s |  |
| Owais Hassan (Awima Housing Solutions) | 6/12/23, 1:43:58 PM | 6/12/23, 2:39:45 PM | 55m 46s |  |
| Ibrahim Modi, UPO | 6/12/23, 1:46:07 PM | 6/12/23, 1:49:08 PM | 3m |  |
| Ibrahim Modi, UPO | 6/12/23, 1:47:13 PM | 6/12/23, 2:53:20 PM | 1h 6m 6s |  |
| Mauro Costa (COOPI) (Guest) | 6/12/23, 1:52:40 PM | 6/12/23, 2:53:11 PM | 1h 30s |  |
| Fatima Ahmed Altahir | 6/12/23, 2:36:15 PM | 6/12/23, 2:53:23 PM | 17m 7s |  |
| Elgozoli, Nahid | 6/12/23, 2:38:33 PM | 6/12/23, 2:53:23 PM | 14m 49s | Nahid.Elgozoli@savethechildren.org |
| Manahil Omer | 6/12/23, 2:48:06 PM | 6/12/23, 2:53:23 PM | 5m 16s |  |