Location: 	Scopia link to Erbil, Baghdad, and Basrah

Time: 		12:30 – 13:15

Present:

Baghdad D1: Maha Sidky, Senior Field Coordinator,UNHCR, IOM,UNICEF, Alaa Al-Nadaf – IM Officer

Baghdad RICC-4: Ravi Solanki ,Cluster Coordinator, Centre & South ; Cornelius Weira – Co-Chair ,Cluster Coordinator for Centre & South; Graham Eastmond,–National Shelter Cluster Coordinator; John Young – National CCCM Cluster Coordinator ; Bassim Al Tamimi, Senior National Officer, UNHCR, MHE; NRC; DRC; UNHCR; IOM; UNOCHA; IRD ;and Muslim Aid,

Erbil office: IOM, UN-Habitat, CRS, NRC, ACTED, DRC, Mercy Hands, ShelterBox, HLP sub-cluster

Basra office: UNHCR; IOM; ICRC

Kirkuk office: UNHCR,DRC,& IRD

Summary of Action Points:

| No. | Action points from the meetings (10h August 2016 ) | Who: | Completed by When: |
| --- | --- | --- | --- |
|  | Partners are requested to Update Status in the google sheet and share plans in addition to the stock. | Partners | ASAP |
|  | Partners are requested to look into prepositioning of emergency shelter kits | Partners | 7TH September 2016 |
|  | Share updated Info. about on-going response in Falluja by UNHCR | Gabriel | ASAP |
|  | An Assessment of camps’ locations and potential capacity which plans to host Mosul IDP to be shared shortly. | John | ASAP |
|  | Share info. about constructing a new camp in Salah Al-Din governorate by UNHCR | Maha/Bassim,UNHCR | ASAP |
|  | Advocate Government to identify / map possible sites where people can be accommodated (such as AUBs, Public Buildings…) | S-NFI Cluster | ASAP |
|  | Partners are requested to look into Prepositioning of emergency shelter kits | Partners | ASAP |
|  | Provide contingency template for on-going emergency response to be shared with partners. | OCHA | ASAP |

Minutes:

| Agenda Item | Key Points | Action points |
| --- | --- | --- |
| - Review of previous action points | - Progress on Action Points - Include site names into the shelter and NFIs section of the google sheet for the Anbar Response. Done - Share the survey tools and methodology with the CCCM Mobile Teams Partners. Done - Share final agreed upon HNO information regarding population in need; Heat Map for 2017. Done - Share consolidated documents on Mosul Operational Planning and Template for stock. To be shared by Woody in two weeks’ time |  |
| - Information Management Update for Centre and South. 2017_Shelter and NFI Severity Map - + Vulnerability | Shelter & NFI monthly response trend against target - Dashboards been share on Aug. 21st 2016 - National coverage : - NFI Distributions: 59% coverage against target - Shelter Interventions: 11% coverage against target - Only Centre and South - NFI Distributions: 69% coverage against C&S target (149,816 HHs) - Shelter Interventions: 12% coverage against C&S target (149,816 HHs) - Funding Status: 31% of USD 180 million - 25% from bilateral - 3% from IHPF - 3% from CERF IDP families Displaced In Salah a Din since June 2016. - Tikrit 9,954 Families - Baiji 696 Families - Balad 75 Families - Al Daur 182 Families - Total Salah Al-Din: 10,907 HHs as of 22nd August 2016 Response To date Shelter Delivered: 4,000 tents – SOKs Delivered: 500 (IOM) Shelter Prepositioned: 2,000 Tents (UNHCR) Gap at Glance: 4,312 (No of IDPs with Host Families Unknown) NFIs Delivered: 4,125 basic NFI kits NFIs Planned: 4,500 basic NFI kits (Cluster partners) Gap at glance: 2,272 NFI Kits (No of IDPs with Host Families Unknown) | https://docs.google.com/spreadsheets/d/1bh74J55IzNiQ6UamyNbQcJi9ikv1hbpxLkj59Zb7G40/edit The above link to be shared with partners to update Ongoing Emergency Response of Qayyarah / Shirqat Crisis |
| - Fallujah Response Updated | - All the required info. (Locations, figures ….etc.) Already shared with Gabriel. | - Share info. On google sheet to be shared with partners. |
| - Mosul Operational Planning updates | - Quadrant 4 Planning figure = 400,000 expected to be displaced from Mosul city .75% of the solutions expected to be ‘’out of camp ‘’ . - Only 13,333 HHs planned for formal camps ( this figure may change) - 80,000, Ind. In formal camp - 40,000, Ind. in transit Centres - 105,000 Ind. in CCs - 705,000 Ind. Out of camp - Salah Al-Din government (Governor specifically) encourage the return of IDP to the liberated areas to alleviate the pressure on Tikrit and other areas which host IDPs and to prepare the same slots for those who newly arrival from Mosul. - 150 IDP Families have been notified by Samaraa authorities to leave the areas within 10 days. | - Share the aassessment of camps’ sites and potential capacity by UNHCR and Government. - Share the information with respect to the return of IDP in Salah Al-Din with protection cluster for further action. |
| - Ongoing Emergency Response – Kirkuk: current situation in Hawija and cluster response | - According to the feedback from MOMD in Kirkuk : - No IDP will be allowed to enter Kirkuk city - MOMD will be able to provide 600 Families accommodation in ”Barwa Settlement / Located about 12 km from Laylan IDP Camp” .They will in addition also provide food baskets. | - Partners to share plans of intervention and stocks. |
| - 2016_IHPF: Second round allocation: USD 45 million available to disburse | - OCHA’s Humanitarian Finance Unit (HFU) extended Partners capacity assessment application and document submission. Deadline was COB Monday 22 August (hope concerned partners succeeded to apply on time) - Aug 22th 2016: the secretariat of IHPF opened the second standard allocation window in the Grant Management System (GMS). - The goal is to fund critical and life-saving projects, which cover first and second line responses in each cluster’s emergency package - The allocation window has been opened and will close on 29 August 2016 at 18:00 / then start the Strategic review, Technical & Budget review and Grant agreement process. - October 1st 2016 : Disbursements to partners | - This allocation is open to NGOs (Nat’l & Int’l), Red Cross/Crescent Movement, UN and IOM. - Partners planning to operate in the four quadrants of the Mosul Operational Plan to submit their project proposals. - Shelter and NFI Cluster among prioritised Clusters |
| - Governorates and Agencies Updates |  |  |
| - Baghdad | - UNHCR accomplished work of the shading area (1000 m² inside Al-Hajaj Camp). - UNHCR is planning to construct “Transit Center” located out-side Al-Hajaj Camp which consist of either 4 or 6 Rub-Halls each with 250 m². | - UNHCR to share Info. On google sheet |
| - Kirkuk | NTR |  |
| - Basrah | NTR |  |

Next Meeting:  Wednesday, 7th September ,2016, Erbil; Baghdad; Basrah and Kirkuk, 11:30 – 13.30. Shelter meeting will be first to start.