## Slide 1
Shelter & WASH Working Group Meeting
Thursday 27 July, 10AM
Asia Pacific Alliance for Disaster Management

## Slide 2: Agenda
Introductions & Agenda
Information Management
NBRO – resettlement site locations and transitional needs
Displacement tracking matrix (DTM)
District focal point updates
Oxfam assessment of WASH needs
Plan Int. assessment of schools
AOB

## Slide 3: Shelter & NFI - progress to date Targets (in red) are according to working group strategy
Chart: 
| 1. Emergency Shelter | NFI - Bedding | NFI - Kitchen sets | NFI (Undefined) | 3. T/Core/Permanent Shelter | 1. Emergency Sheltering | 2. Support to Return | 3. T/Core/Permanent Shelter
Completed distributions | 535 | 3232 | 7810 | 7164
Ongoing distributions | 968 | 626
In pipeline (procurement/ onroute) | 2500
Planned (funded) | 6600 | 2760 | 2660 | 19321 | 220
Planned (subject to funding) | 2272 | 1400 | 650
8000 (based on agency capacities)
25,000 (national damage data, fully and partially damaged)
2,500 (national damage data – fully damaged)

## Slide 4: Shelter & NFI - modality
Chart: 
| 1. Emergency Sheltering | 2. Support to Return | 3. T/Core/ Permanent Shelter
Cash | 2850 | 3100
In-kind | 4285 | 45241 | 870
Not Specified | 2272 | 100

## Slide 5: Shelter programming – Objective 1
Targeting is not yet down to divisional level for all activities

## Slide 6: Shelter programming – Objective 2
Targeting is not yet down to divisional level for all activities

## Slide 7: Shelter programming – Objective 3
Targeting is not yet down to divisional level for all activities

## Slide 8: Shelter needs – damage data
National level data: DMC website
Up to 28th June covering all flood/landslide affected districts & divisions
Since 23rd July this has been posted again, though does not cover all districts and divisions
District- level data
Collected by SWG from GA offices:
District | Date collected | Date of data set
Matara | 11/07/17 | 28/06/17
Galle | 11/07/17 | 20/06/17
Kalutara | 12/07/17 | 28/06/17
Ratnapura | 18/07/17 | 17/07/17

## Slide 9: Shelter needs – damage data

## Slide 10: Shelter & NFI – gaps Targets (in red) are according to working group strategy
Chart: 
| 1. Emergency Shelter vs partially damaged houses | NFI - Bedding vs all damaged houses | NFI - Kitchen sets vs all damaged houses | NFI (Undefined) vs all damaged houses | 3. T/Core/Permanent Shelter vs fullly damaged houses | 1. Emergency Sheltering | 2. Support to Return | 3. T/Core/Permanent Shelter
HH targeted by interventions | 9407 | 9460 | 11096 | 27885 | 870
National damage data | 20439 | 23406 | 23406 | 23406 | 2967
District damage data | 71810 | 74803 | 74803 | 74803 | 2993
PLUS: Households facing mandatory relocation for high risk zones without housing damage

## Slide 11: NBRO Update on Resettlement Progress

## Slide 12
District | #of Sites | HH | Members
Rathnapura |  |  | 
Kalutara | 7 | 101 | 377
Galle | - | - | -
Matara | 1 | 16 | 66
Statistic at Temporary sites;
District | LS | Total
Rathnapura | 1068 | ~1600
Kalutara | 504 | ~1400
Galle | 92 | ~300
Matara | 200 | ~300
No of Households at High risk;

## Slide 13: Site Selection Criteria
Possibility to affect another landslide or flood
Soil condition, slope and terrain
Availability of Drinking water and Electricity
Access to town centers and public transportation.
Availability of Social Infrastructure (School, Hospital, Religious and Police)

## Slide 14
District | DS Division | No. of lands inspected | No. of Lands Approved | No. of Lands Rejected | Approved land extent (Acres)
 | Balangoda | 10 | 3 | 7 | 12
Ratnapura | Kahawatta | 2 | 1 | 1 | 1
 | Kalawana | 7 | 6 | 1 | 9
 | Kiriella | 3 | 1 | 2 | 10
 | Nivithigala | 2 | 2 | - | 17.5
 | Pelmadulla | 1 | 1 | - | 30
 | Eheliyagoda | 2 | 1 | 1 | 2.5
 | Ratnapura | 7 | 1 | 6 | 0.75
 | Kuruwita | 4 | 3 | 1 | 13
Sub Total |  | 38 | 19 | 19 | 95.75
 | Bulathsinhala | 18 | 5 | 13 | 60
Kalutara | Dodangoda | 2 | 2 | - | 12.72
 | Madurawala | 6 | 4 | 1 | 12.75
 | Mathugama | 5 | 3 | 2 | 10.5
 | Palinda nuwara | 10 | 3 | 7 | 14.18
 | Walallawita | 2 | - | 2 | -
Sub Total |  | 43 | 17 | 25 | 110.15
 | Baddegama | 2 | 1 | 1 | 0.28
Galle | Elpitiya | 3 | 3 | - | 28.5
 | Neluwa | 2 | - | 2 | -
 | Tawalama | 1 |  |  | 
 | Walivitiya Divithura | 1 | 1 | - | 30
Sub Total |  | 9 | 5 | 3 | 58.78
 | Kotapola | 2 | 2 | - | 2.5
Matara | Pasgoda | 3 | 1 | 2 | 7
 | Thihagoda | 2 | 1 | - | 2
Sub Total |  | 7 | 4 | 2 | 11.5
Total |  | 97 | 45 | 49 | 276.18

## Slide 15: Resettlement Sites

## Slide 16: Development of Resilient Communities
Steps | Activities
Geographical and demographical information | Identification of sites suitable for new settlement according to the criteria described in the implementation framework. Acquisition of sites. Identification of beneficiaries (to be resettled). Initiate process of engagement to clarify their needs and concerns Obtain site information (photographs, field visits, maps, etc.) to analyse the geographical / physical conditions of the place.
Concept design | Analyse information and start a concept design for the masterplan Feasibility study to demonstrate how many dwellings can fit in each site. Prepare drawings and discuss with HSPTD team
Consultation with community | Consultation meeting with the people to be resettled to discuss the design and to identify the families that wish /can go to each site
Revisions | Revise masterplan drawings according to people’s comments Issue drawings to all stakeholders for comment or approval
Consultation with stakeholders | Coordinate designs with NBRO Engineers, DS, Survey Department Water and Drainage Board, Electricity Board and other authorities to have their comments
Final design | Revise drawings Presentation to DS and residents Final amendments and issue for approval

## Slide 17: Standards for Settlement Development
CAT | Site Category 01 | Site Category 02 | Site Category 03
Units | Less than 25 dwellings | 25 – 50 dwellings | More than 50
Uses | Single detached houses Children park Corner shop | Single detached houses, Semidetached, low rise (G+3) Public open spaces Corner shop Child care centre Place for worship | Single detached houses, Semi- detached houses, Medium rise buildings (G+7) Parks, playground and recreational facilities Shops / restaurants / retail Childcare centre, Education centre Clinic and pharmacy Public transport
Standards for Settlement Development*
*NBRO, Implementation Framework for Resettle Landslides and Flood Victims

## Slide 18: Category 1
Single detached
houses
Children park
Corner shop

## Slide 19: Category 2
Single detached houses,
Semidetached, low rise (G+3)
Public open spaces
Corner shop
Child care centre
Place for worship

## Slide 20: Category 2

## Slide 21
TYPE PLANS
NBRO has prepared resilient house plans which are adaptive to landslides and floods, and worked out all the plans according to the “Core House” concept.
MINIMUM STANDARD FOR CORE HOUSE
Minimum floor area of 650 sq. ft.
Resilient foundation and a superstructure (As directed by NBRO)
Two bedrooms
A kitchen
A permanent roof
A water seal toilet and a septic tank
Availability of electricity and water

## Slide 22
INDIVIDUAL HOUSING

## Slide 23
CLUSTER HOUSING

## Slide 25
Safe Site ?
Prohibited zone (high risk)
Yes
Shelter
Repair Kit/Cash
Transitional /core shelter?
Partially Damaged (<40%)
Fully Damaged (>40%)
Transitional/core shelter?
No
Restricted zone (medium risk)
Warning zone
(low risk)
NITF Insurance
Govt financial assistance 1.2m on
sites identified by government
Resettlement
Owner selected sites or house:
Govt financial assistance for house purchase (with land) up to 1.6m
Reconstruction in-situ with resilient features
Fully Damaged (>40%)
Partially Damaged (<40%)
GOVERNMENT RESPONSE
SUPPORT OPTIONS
Shelter
Repair Kit/Cash
All: technical support
Transitional/core shelter?
No risk
Govt financial assistance 1.2m
NITF Insurance
Govt financial assistance 1.2m

## Slide 26
Prohibited zone (high risk)
Partially Damaged (<40%)
Restricted (medium risk)
Warning (low risk)
Reconstruction in-situ with resilient features
Fully Damaged (>40%)
Partially Damaged (<40%)
GOVERNMENT RESPONSE
No risk
Fully Damaged (>40%)
Host family / Rental home
$ Installment 1 x LKR 10,000
In situ
Evacuation site
Services
Completion up to roof level and supply of timber
LKR 300,000
Completion of roof
LKR 450,000
Completion of Core-house – Doors and Windows, Plastering, Finishing and Painting
LKR 300,000
Average
Timeline
1
2
13
3
4
7
5
6
8
9
10
11
12
14
15
16
Land preparation, excavation and completion LKR 150,000
Govt financial assistance 1.2 – 1.6 m
Re-location
Re-construction
$ Rental support 3 x LKR 7,500
Resettlement
NITF Insurance
Govt financial assistance 1.2m
NITF Insurance
Govt financial assistance 1.2m

## Slide 27
Prohibited zone (high risk)
Partially Damaged (<40%)
Restricted (medium risk)
Warning (low risk)
Reconstruction in-situ with resilient features
Fully Damaged (>40%)
Partially Damaged (<40%)
GOVERNMENT RESPONSE
No risk
Fully Damaged (>40%)
Host family / Rental home
$ Installment 1 x LKR 10,000
In situ
Evacuation site
Services
Completion up to roof level and supply of timber
LKR 300,000
Completion of roof
LKR 450,000
Completion of Core-house – Doors and Windows, Plastering, Finishing and Painting
LKR 300,000
Average
Timeline
1
2
13
3
4
7
5
6
8
9
10
11
12
14
15
16
NITF Insurance
Govt financial assistance 1.2 m
OR
NITF Insurance ?
Land preparation, excavation and completion LKR 150,000
Govt financial assistance 1.2 – 1.6 m
Re-location
Re-construction
$ Rental support 3 x LKR 7,500
Relocation
Re-construction
Transitional /core shelter?
Transitional/core shelter?
HUMANITARIAN
SUPPORT OPTIONS
Shelter
Repair Kit/Cash
All: technical support
Transitional/core shelter?
Shelter
Repair Kit/Cash
Resettlement

## Slide 28
Displacement Tracking Matrix
(DTM)
https://app.powerbi.com/view?r=eyJrIjoiZThjNmRiZTgtMjY2NC00YTEzLWFhYzMtZTlkODlkMzI4NTllIiwidCI6IjliNWVkNDg5LWZiOWEtNDVmMi04MTBjLTkyNmFlNDdjZjMzOCIsImMiOjEwfQ%3D%3D

## Slide 29
District Updates
ToRs finalised
Focal points
  WASH update
    World Vision – Kaluthra
    LEADS – Ratnapura and Matara
    Oxfam – Galle
  Shelter update
    World Vision: Ratnapura
    UN Habitat: Galle & Kalutara
    Save the Children: Matara

## Slide 30: Update by Oxfam
Started Latrine damage assessment in Kalutara
4 Camps assessed (Kalutara - 2, Ratnapura - 2)
  Kalutara (Vogan Estate – 54 families & Geekeyanakanda – 10 families)
    Lack of WASH facilities
    Oxfam is working
  Ratnapura (Elapatha – 48 families & Kalathuwava Thikiyakala School ground – 22 familes)
    Elapatha – World Vision is working
    Kalathuwava – Lack of WASH facilities and Oxfam committed to work

## Slide 31: Oxfam…
Circulated the Latrine assessment report from PS – Bulathsinhala
Latrine intervention discussion

## Slide 32: Ratnapura schools works By Plan International Sri Lanka
Observations
Damages to the water distribution lines, wells polluted with flood water , water pumps,
Damages the handwashing points / removal of taps, soap trays,
Damages to the toilets (broken doors, taps)
Drainage systems are blocked
Overuse of WASH facilities if the school is used as a camp
Lack /absence/removal of taps, soap trays and absences of cleaning material (disinfectants, brushes, wipers, dustbins)
Poor waste management practices
Debris and water logged locations
Certain schools are still closed
Flood is regular event for most of the schools

## Slide 33: Challenges
Lack of detailed data about the damages WASH facilities
Results of Rapid WASH Assessment in schools
Difficulty in verifying flood caused damages
Funds are short term (time factor)
School vacations
Government examinations in August where major constructions are prohibited during the exam period.
Distances among schools
Time limitations for software activities

## Slide 34: Web Details
www.sheltercluster.org
https://www.sheltercluster.org/response/sri-lanka-floods-2017
Damage data visualisation:
https://public.tableau.com/profile/methunan#!/vizhome/SriLanka-DamageDataTable/SummaryDamage-District
Damage data table: https://public.tableau.com/profile/methunan#!/vizhome/SriLanka-DamageDataTable/Datatable?publish=yes
DTM: https://app.powerbi.com/view?r=eyJrIjoiZThjNmRiZTgtMjY2NC00YTEzLWFhYzMtZTlkODlkMzI4NTllIiwidCI6IjliNWVkNDg5LWZiOWEtNDVmMi04MTBjLTkyNmFlNDdjZjMzOCIsImMiOjEwfQ%3D%3D