[image: image1.jpg]


Shelter Cluster Somalia
ShelterCluster.org

Coordinating Humanitarian Shelter


GUIDANCE NOTE FOR 4W MATRIX

TRAINER’S NOTE

	GENERAL BACK GROUND ON 4W Matrix


In order to coordinate needs and response in a timely and effective manor, Shelter Cluster is promoting the use of the mobile device to collect 4W information.  This allows for information to be gathered quickly and ties all information to a GPS point insuring it’s accuracy and adding credibility to Shelter Cluster reporting.
	PREPARATION FOR THE 4W


· 4 W is a great opportunity for RSCC to visit the field, build relationships with partner agencies, monitor progress and be confident/knowledgeable about all shelter activities in your region.
· Arrange to visit the field of implementing agencies once a month to capture their activity. If it is an NFI activity, it is ideal to visit on the day of distribution (you can also capture a photo of NFI items and how beneficiaries received them).
· If you are too busy to visit the field monthly: Do not send a template email to the agency.  Rather, make a phone call to them, have your mobile device open in your hand and ask all the questions in the tool and fill them out while talking to them. This is much more accurate and fast and will allow you to explain questions.  There is a question on the mobile that will ask you “where are you capturing this data?” where you can answer “in my office”.
	How many uploads do I need per project?


· It depends on the component of a project. It must be split by Location, Donor, and Activity.  For example, if in a contract it says Emergency Shelter for 200 HH and NFI for 300 HH in one location, then you have to split it into two entries (records) because it is two activities. 
· Example: DRC is implementing shelter/NFI projects in two locations.  They are NFI, Permanent Shelter and Transitional Shelter, funded by CHF, ECHO and DFID.

Location 1







Location 2
CHF


ECHO




CHF


DFID

NFI, PS


NFI, TS



NFI


PS, NFI

In this case you are supposed to upload 7 entries (records) separately, one for each project.
	4W Questionnaire: Step by Step


GPS
· Everything in the 4W is linked to a Geographical location.  The should be a record for each project per agency, even if in the same settlement.
Current or Historical Report
· This means WHEN the activity you are going to capture took place. If you were away for a month from your duty station and could not capture any data, you can still visit the field the next month and capture what has happened.  If you are capturing an activity done more than one month ago you can choose Historical.
Where are you capturing the data?
· You will be given the opportunity to answer Project Location, Implementer Office (of the agency) or My Office.  
· The principle s that you will capture the project in the field, but if you don’t have access you can do it remotely by calling partners and going through the questionnaire with them while you use the mobile application.
Date

· If it is a historical record you can keep the Day as “01”. Just enter the Month and Year when the activity you are capturing took place.
Donor

· Who is the main donor? Usually you can find this in contracts, however if it is difficult to find you can skip this question
Sub-Sector
· The “Sector” is Shelter.  Under Shelter there are five Sub-Sectors:
Needs Assessment, NFI, Emergency Shelter, Transitional Shelter, Permanent Shelter.

· Example: REACH is doing capacity building in the Shelter Cluster only through Needs Assessment.  So the Sub-Sector for REACH would be classified as “Needs Assessment”.
What is in the Kit?

· There is a list in a dropdown menu, please check each item you see in the kit.

Starting and End date of project

· Usually you can find this information in proposals, but if you can’t find it you can choose “don’t know”.
Project Specific Needs Assessment
· Bear in mind about the difference between normal needs assessment and Project Specific needs assessment.  It is also different from registration. 
· Project Specific needs assessment is to be done by the implementing agency to identify beneficiaries for the particular activity.  The agency will be able to know who has to be registered through this kind of project specific needs assessment, (though very rare in the current reality of Somalia).
Current Status

· If actual implementation has started answer “Construction/distribution ongoing”
· If planned target has been achieved (ex. Planned target was 1000 HH and distribution has taken place to 1000 HH) answer “Project Completed”.
· If a project is temporarily suspended but will resume when things have cleared answer “Suspension”. 
· If a project for some reason will not happen again, thus the agency will relocate funds elsewhere, change location, change content ect. Answer “Stop”. 
Post Implementation Review
· This includes PDM, agency’s evaluation, report, whatever happens after the project.  If it has happened/is planned answer “Yes”.
· If “yes” what kind of Post Implementation review? The Cluster standard M&E tool does not currently exist, but it will soon.
Number of HH received Shelter

· How many units were completed by the time of your visit. It can be cumulative.
· Example: A 4 month project targeting 300 HH for Emergency Shelter.


Jan


Feb

Mar

Apr


50 completed

100

200

300 completed and finished

Photo for Shelter 
· Take a photo of Typology. If there was a fire outbreak just before your visit you can even take this picture. 
· Hold your mobile phone upright, make sure the whole structure is captured in the photo.
Photo for NFI
· It is ideal if the RSCC can be present on distribution day.  Then you can monitor the activity, do the 4W on that day, take a picture of the NFI kit and of how people are lining up.
· Hold your mobile phone upright, make sure the whole structure is captured in the photo.
	GOOD QUALITY PICTURES (good and bad examples)


EXAMPLES (See presentation)

-A good photo captures the whole infrastructure or as much as possible.

	USE OF PHONE AND MFIELDWORK


See manual for mFieldwork. 

	GENERAL CHECKS BEFORE GOING TO THE FIELD


· If you do not have a log in code, contact the Shelter Cluster Secretariat for access to the website.
· Make sure you are logged in with your phone on the MFIELDWORK application before leaving the WIFI area. It is necessary to be logged in when in the field. 
· Once you start the mapping exercise turn WIFI off to save battery, as long as you are logged in to the application the data will still upload.

· Make sure the latest versions of all the questionnaires have been downloaded.

· Make sure that the GPS is functional on all the phones. Try this out at the office.

· Make sure all the phones are properly charged
SOMALIA
ToRs Shelter Cluster Somalia 
3

