## 4W
Shelter Cluster Bangladesh | [7 empty] | Total (HH) | 9323 |  | Total (HH) | 4789 | Total (HH) | 1075
Cyclone Mora and Landslide 2017 | [6 empty] | Emergency Phase | [5 empty] | Recovery Phase
As of 16 August 2017 | [6 empty] | Emergency Shelter |  |  | HH NFIS
Event | District | Upazila | Union | Interested agency | Implementing Partner | Donor | Option 1 : Tarpaulin, toolkits, Construction Materials | Option 2: Cash grant BDT 5,000 | Emergency Shelter Responded/ planned (HH) | Option 1: Cloths, Blanket, Candle, Kitchen utensils | Option 2: Cash grant BDT 3,000 | Household NFIs Responded / planned (HH) | Option : 1. Shelter Repairing / 2. Transitional Shelter / 3. Permanent Shelter constuction | Recovery : Responded / planned (HH) | Status : Completed / On-going / Planned | when | Remarks
Landslide | Bandarban | Lama | Fashiakhali | BDRCS | BDRCS | IFRC | Toolkits |  | 46 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Lama | Ruposhipara | BDRCS | BDRCS | IFRC | Toolkits |  | 35 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Lama | Gazalia | BDRCS | BDRCS | IFRC | Toolkits |  | 8 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Lama | Sadar | BDRCS | BDRCS | IFRC | Toolkits |  | 35 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Lama | Marakhola | BDRCS | BDRCS | IFRC | Toolkits |  | 25 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Lama | Pourosova | BDRCS | BDRCS | IFRC | Toolkits |  | 51 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Bandarban Sadar | Shualok | BDRCS | BDRCS | IFRC | Toolkits |  | 11 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Bandarban Sadar | Kuhalong | BDRCS | BDRCS | IFRC | Toolkits |  | 5 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Bandarban Sadar | Pourosova | BDRCS | BDRCS | IFRC | Toolkits |  | 84 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban | Naikhongchhari | Sadar | BDRCS | BDRCS | IFRC | Toolkits |  | 50 | [5 empty] | Completed | 23.07.17 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban |  |  | BDRCS | BDRCS | IFRC | Toolkits |  | 150 | [5 empty] | Planned |  | In addition Each beneficiary will receive BDT 4,000 as multipurpose cash grant support.
Landslide | Bandarban |  |  | BDRCS | BDRCS | IFRC | [6 empty] | Shelter repairing | 500 | Planned |  | Cash grant and Materials support will be provided along with PASSA.
Cyclone Mora | Chittagong | Banshkhali | Chhanua | BDRCS | BDRCS | IFRC | Toolkits |  | 100 | [5 empty] | Completed | 4.07.2017 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Cyclone Mora | Chittagong | Banshkhali | Gandamara | BDRCS | BDRCS | IFRC | Toolkits |  | 100 | [5 empty] | Completed | 4.07.2017 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Cyclone Mora | Chittagong | Anowara | Roypur | BDRCS | BDRCS | IFRC | Toolkits |  | 110 | [5 empty] | Completed | 4.07.2017 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Cyclone Mora | Chittagong | Raozan | Urkirchar | BDRCS | BDRCS | IFRC | Toolkits |  | 5 | [5 empty] | Completed | 4.07.2017 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Cyclone Mora | Chittagong | Rangunia | Islampur | BDRCS | BDRCS | IFRC | Toolkits |  | 35 | [5 empty] | Completed | 4.07.2017 | In addition Each beneficiary received BDT 4,000 as multipurpose cash grant support.
Cyclone Mora | Cox's Bazar |  |  | BDRCS | BDRCS | IFRC | Toolkits |  | 150 | [5 empty] | Planned
Cyclone Mora | Chittagong |  |  | BDRCS | BDRCS | IFRC | [6 empty] | Shelter Repairing | 500 | Planned |  | Cash grant and Materials support will be provided along with PASSA.
Cyclone Mora | Cox's Bazar | Pekua | Ujantia | Caritas Bangladesh | Caritas Bangladesh | Start Fund |  | Cash Grant BDT 5,000 | 300 | [5 empty] | Completed | 15.06.2017 | Training on house repairing provided to 300 beneficiaries
Cyclone Mora | Cox's Bazar | Pekua | Magnama | Caritas Bangladesh | Caritas Bangladesh | Start Fund |  | Cash Grant BDT 5,000 | 700 | [5 empty] | Completed | 15.06.2017 | Training on Build Back Better / Safer House Repair provided to 700 beneficiaries
Landslide | Rangamati | Kawkhali (Betbunia) | Ghagra | Caritas Bangladesh | Caritas Bangladesh | [5 empty] | Cash grant BDT 3,000 | 300 |  |  | Completed | 24.06.2017
Landslide | Rangamati | Kawkhali (Betbunia) | Betbunia | Caritas Bangladesh | Caritas Bangladesh | [5 empty] | Cash grant BDT 3,000 | 300 |  |  | Completed | 24.06.2017
Landslide | Rangamati | Kawkhali (Betbunia) | Fatik Chhari | Caritas Bangladesh | Caritas Bangladesh | [5 empty] | Cash grant BDT 3,000 | 100 |  |  | Completed | 24.06.2017
Landslide | Rangamati | Kawkhali (Betbunia) | Betbunia | Caritas Bangladesh | Caritas Bangladesh | Careitas Switzerland |  |  |  |  | Cash grant BDT 3,000 | 154 |  |  | Ongoing |  | Budget for each family BDT 3,400. The items included untensils, clothings and WASH materials
Landslide | Rangamati | Kaptai | Wagga | Caritas Bangladesh | Caritas Bangladesh | Careitas Switzerland |  |  |  |  | Cash grant BDT 3,000 | 138 |  |  | Ongoing |  | Budget for each family BDT 3,400. The items included untensils, clothings and WASH materials
Landslide | Rangamati | Kaptai | Kaptai | Caritas Bangladesh | Caritas Bangladesh | Careitas Switzerland |  |  |  |  | Cash grant BDT 3,000 | 133 |  |  | Ongoing |  | Budget for each family BDT 3,400. The items included untensils, clothings and WASH materials
Landslide | Rangamati | Kaptai | Chandraghona | Caritas Bangladesh | Caritas Bangladesh | Careitas Switzerland |  |  |  |  | Cash grant BDT 3,000 | 286 |  |  | Ongoing |  | Budget for each family BDT 3,400. The items included untensils, clothings and WASH materials
Landslide | Rangamati | Kaptai | Raikhali | Caritas Bangladesh | Caritas Bangladesh | Careitas Switzerland |  |  |  |  | Cash grant BDT 3,000 | 189 |  |  | Ongoing |  | Budget for each family BDT 3,400. The items included untensils, clothings and WASH materials
Landslide | Rangamati | Kaptai | Chitmaram | Caritas Bangladesh | Caritas Bangladesh | Careitas Switzerland |  |  |  |  | Cash grant BDT 3,000 | 100 |  |  | Ongoing |  | Budget for each family BDT 3,400. The items included untensils, clothings and WASH materials
Cyclone Mora | Rangamati | Langadu |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 300 | [5 empty] | Planned | 24.07.2017
Cyclone Mora | Rangamati | Rangamati Sadar |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 0 | [5 empty] | Planned | 24.07.2017
Cyclone Mora | Cox's Bazar | Cox'S Bazar Sadar |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 250 | [5 empty] | Completed | 21.06.2017
Cyclone Mora | Cox's Bazar | Teknaf |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 270 | [5 empty] | Completed | 24.07.2018
Cyclone Mora | Cox's Bazar | Maheshkhali |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 74 | [5 empty] | Completed | 22.06.2017
Cyclone Mora | Cox's Bazar | Cox'S Bazar Sadar |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 81 | [5 empty] | Completed | 24.07.2019
Cyclone Mora | Cox's Bazar | Ramu |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 5 | [5 empty] | Completed | 23.06.2017
Cyclone Mora | Cox's Bazar | Ukhia |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 70 | [5 empty] | Completed | 24.07.2020
Cyclone Mora | Bandarban | Naikhongchhari |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 300 | [5 empty] | Planned | 19.07.2017
Cyclone Mora | Bandarban | Lama |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 450 | [5 empty] | Planned | 19.07.2018
Cyclone Mora | Bandarban | Alikadam |  | UNDP | UNDP |  |  | Cash grant BDT 5,000 | 250 | [5 empty] | Planned | 19.07.2019
Cyclone Mora | Cox's Bazar | Maheshkhali | Bara Maheskhali | Islamic Relief Bangaldesh | Islamic Relief Bangaldesh | Islamic Relief UK |  | Cash Grant BDT 5,000 | 300 | [5 empty] | Completed | 10.07.17
Cyclone Mora | Cox's Bazar | Maheshkhali | Kutubjom | Islamic Relief Bangaldesh | Islamic Relief Bangaldesh | Islamic Relief UK |  | Cash Grant BDT 5,000 | 300 | [5 empty] | Completed | 10.07.17
Cyclone Mora | Cox's Bazar | Maheshkhali | Chhotamohes Khali | Islamic Relief Bangaldesh | Islamic Relief Bangaldesh | Islamic Relief UK |  | Cash Grant BDT 5,000 | 200 | [5 empty] | Completed | 10.07.17
Cyclone Mora | Cox's Bazar | Maheshkhali | Maheshkhali Paurashava | Islamic Relief Bangaldesh | Islamic Relief Bangaldesh | Islamic Relief UK |  | Cash Grant BDT 5,000 | 200 | [5 empty] | Completed | 10.07.17
Landslide | Bandarban | Thanchi | Bolipara | ActionAid Bangladesh | Bolipara Nari Kalyan Somity (BNKS) | START Fund |  | Cash Grant BDT 5,000 | 23 | [5 empty] | Ongoing | 24 June to 08 August
Landslide | Bandarban | Thanchi | Thanchi | ActionAid Bangladesh | Bolipara Nari Kalyan Somity (BNKS) | START Fund |  | Cash Grant BDT 5,000 | 15 | [5 empty] | Ongoing | 25 June to 08 August
Landslide | Bandarban | Thanchi | Tindu | ActionAid Bangladesh | Bolipara Nari Kalyan Somity (BNKS) | START Fund |  | Cash Grant BDT 5,000 | 37 | [5 empty] | Ongoing | 26 June to 08 August
Landslide | Rangamati | Rangamati Sadar | Municipality | ActionAid Bangladesh | Green Hill | START Fund |  | Cash Grant BDT 5,000 | 153 | [5 empty] | Ongoing | 27 June to 08 August
Landslide | Rangamati | Rangamati Sadar | Sapchari | ActionAid Bangladesh | Green Hill | START Fund |  | Cash Grant BDT 5,000 | 7 | [5 empty] | Ongoing | 28 June to 08 August
Landslide | Rangamati | Belai Chhari | Sadar | ActionAid Bangladesh | Green Hill | START Fund |  | Cash Grant BDT 4000 | 10 | [5 empty] | Ongoing | 29 June to 08 August
Landslide | Rangamati | Belai Chhari | Kangrachori | ActionAid Bangladesh | Green Hill | START Fund |  | Cash Grant BDT 4000 | 10 | [5 empty] | Ongoing | 30 June to 08 August
Landslide | Rangamati | Belai Chhari | Faruya | ActionAid Bangladesh | Green Hill | START Fund |  | Cash Grant BDT 4000 | 60 | [5 empty] | Ongoing | 31 June to 08 August
Cyclone Mora | Cox's Bazar | Kutubdia | Uttar Dhurung | Concern Worldwide | YPSA | START Fund |  | Cash Grant BDT 4000 | 680 | [5 empty] | Completed | June, 2017
Cyclone Mora | Cox's Bazar | Kutubdia | Ali Akbar Deil | Concern Worldwide | YPSA | START Fund |  | Cash Grant BDT 4000 | 560 | [5 empty] | Completed | June, 2017
Cyclone Mora | Cox's Bazar | Kutubdia | Baraghop | Concern Worldwide | YPSA | START Fund |  | Cash Grant BDT 4000 | 235 | [5 empty] | Completed | June, 2017
Cyclone Mora | Cox's Bazar | Kutubdia | Uttar Dhurung | Concern Worldwide | YPSA | Irish Aid |  | Cash Grant BDT 4000 | 560 | [5 empty] | Completed | June, 2017
Cyclone Mora | Cox's Bazar | Kutubdia | Ali Akbar Deil | Concern Worldwide | YPSA | Irish Aid |  | Cash Grant BDT 4000 | 470 | [5 empty] | Completed | July, 2017
Cyclone Mora | Cox's Bazar | Kutubdia | Baraghop | Concern Worldwide | YPSA | Irish Aid |  | Cash Grant BDT 4000 | 320 | [5 empty] | Completed | July, 2017
Cyclone Mora | Cox's Bazar | Kutubdia | Dakshin Dhurung | Concern Worldwide | YPSA | Irish Aid |  | Cash Grant BDT 4000 | 150 | [5 empty] | Completed | July, 2017
Cyclone Mora | Cox's Bazar | Teknaf | Sabrang | Solidarites International | Solidarites International | [5 empty] | Cash grant BDT 4000 | 589 |  |  | Completed | 20.06.2017 | Multi-purpose cash grant of 4000 BDT according to Cash Working Group
Cyclone Mora | Cox's Bazar | Teknaf | Sabrang | Solidarites International | Solidarites International | ECHO |  |  |  |  | Cash grant BDT 4000 | 589 |  |  | Planned | 01.09.2017 | Same beneficiaries as previous line (2nd instalment). Proposal approval pending
Cyclone Mora | Cox's Bazar | Teknaf |  | Solidarites International | Solidarites International | ECHO |  |  |  |  | Cash grant BDT 4000 | 1071 |  |  | Planned | 01.09.2017 | 2 instalments of 4000 BDT/month. Union will be defined following assessment beg of aug. Proposal approval pending
Cyclone Mora | Cox's Bazar | Teknaf |  | Solidarites International | Solidarites International | DFID |  |  |  |  | Cash grant BDT 4000 | 840 |  |  | Planned | 01.09.2017 | 2 instalments of 4000 BDT/month. Union will be defined following assessment beg of aug. Proposal approval pending
Cyclone Mora | Cox's Bazar | Kutubdia | Uttar Dhurung | Friendship | Friendship | Friendship Luxembourg | [6 empty] | Shelter Repairing | 15 | Completed | 22.06.2017
Cyclone Mora | Noakhali | Hatiya | Tamaruddin | Friendship | Friendship | Friendship Luxembourg | [6 empty] | Shelter Repairing | 15 | Ongoing | 15.08.2017
Cyclone Mora | Cox's Bazar | Chakaria | Badarkhali | Save the Children | MUKTI Cox | C&A Foundation | [6 empty] | Permanent Shelter constuction | 15 | Ongoing |  | 6 Months Program, Starting from 1July 2017
Cyclone Mora | Cox's Bazar | Chakaria | Kona Khali | Save the Children | MUKTI Cox | C&A Foundation | [6 empty] | Permanent Shelter constuction | 15 | Ongoing |  | 6 Months Program, Starting from 1July 2017
Cyclone Mora | Cox's Bazar | Chakaria | Damosia | Save the Children | MUKTI Cox | C&A Foundation | [6 empty] | Permanent Shelter constuction | 15 | Ongoing |  | 6 Months Program, Starting from 1July 2017
Landslide & Flash flood | Bandarban | Bandarban Sadar | Bandarban Paurashava | World Vision BD | BNKS | Start Fund & World Vision Int. | CI Sheet 2 Bindle per HH |  | 29 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Bandarban Paurashava | World Vision BD | BNKS | Start Fund & World Vision Int. |  | Cash grant BDT 5,000 | 226 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Bandarban | World Vision BD | BNKS | Start Fund & World Vision Int. | CI Sheet 2 Bindle per HH |  | 18 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Bandarban | World Vision BD | BNKS | Start Fund & World Vision Int. |  | Cash grant BDT 5,000 | 100 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Kuhalong | World Vision BD | BNKS | Start Fund & World Vision Int. | CI Sheet 2 Bindle per HH |  | 17 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Kuhalong | World Vision BD | BNKS | Start Fund & World Vision Int. |  | Cash grant BDT 5,000 | 220 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Swalak | World Vision BD | BNKS | Start Fund & World Vision Int. | CI Sheet 2 Bindle per HH |  | 15 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Swalak | World Vision BD | BNKS | Start Fund & World Vision Int. |  | Cash grant BDT 5,000 | 111 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Rajbila | World Vision BD | BNKS | Start Fund & World Vision Int. | CI Sheet 2 Bindle per HH |  | 16 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Rajbila | World Vision BD | BNKS | Start Fund & World Vision Int. |  | Cash grant BDT 5,000 | 167 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Tankabati | World Vision BD | BNKS | Start Fund & World Vision Int. | CI Sheet 2 Bindle per HH |  | 5 | [5 empty] | Completed | 2017-08-06
Landslide & Flash flood | Bandarban | Bandarban Sadar | Tankabati | World Vision BD | BNKS | Start Fund & World Vision Int. |  | Cash grant BDT 5,000 | 59 | [5 empty] | Completed | 2017-08-06