Where are we aiming? 
5 year plan of the GSC Urban Settlements WG: DRAFT 19 April 2018

|  | 2018 | 2019 |  | 2020 |  | 2021 |  | 2022 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GSC Urban Advocacy |  |  |  |  |  |  |  |  |  |
| Pursue opportunities for W/G to engage with global city networks: GSC to host a Humanitarian Urban Symposium (3 regions) |  |  | X |  | X |  | X |  |  |
| Guidance on effective S&S responses in urban contexts |  |  |  |  |  |  |  |  |  |
| Urban Settlement Approaches Case Study Compendium | X |  |  |  |  |  |  |  |  |
| Urban Settlement W/G best practice guide publication |  |  | X |  |  |  |  |  |  |
| Global/regional Learning events |  |  |  | X |  | X |  | X |  |
| Increased coordination and collaboration between clusters and implementing partners |  |  |  |  |  |  |  |  |  |
| W/G Urban settlement advocacy | X | X | X | X | X | X | X | X | X |
| Area-based Coordination |  |  |  |  |  |  |  |  |  |
| Area-based Coordination Module |  |  |  |  |  |  |  |  |  |
| Development of ABC Guidance | X | X |  |  |  |  |  |  |  |
| Area-based Coordination Pilots (3-5 months x 3) | X |  | X |  | X |  |  |  |  |
| Evaluation + Learning |  |  |  |  |  |  |  |  |  |
| AB Coordination Evaluation - (Pilot I+II+III) |  | X |  | X |  | X |  |  |  |
| Develop and publish ABC Concepts and Training module |  |  | X |  |  |  |  |  |  |
| Consultations and Dissemination |  |  |  |  |  |  |  |  |  |
| Coordinators' training (All clusters) . ABC component |  | X |  | X |  | X |  | X |  |
| Global Cluster Coordinators' Group Event (2 events) |  |  |  | X |  |  |  |  |  |
| Regional Workshop - (2 regions) |  |  | X |  |  | X |  |  |  |
| Operationalization of ABC (Guidance, training, dissemination) |  |  |  | X |  | X |  | X |  |
| Advocacy for operationalization (Various Forums | X | X | X | X | X | X | X | X | X |