## SC_Performance
17 PRIORITY MUNICIPALITIES - EMERGENCY SUPPORT - ONLY TARPS AND TENTS
PCODE_Mun |  | Location |  |  | Demographics |  | Damaged Houses (19/11/2013) |  |  | Displaced HH (19/11/2013) |  |  |  | Response (19/11/2013) |  | Activity | [11 empty] | Activity | Activity
|  | Municipality | # HH Census | # displaced HH | % displaced HH | Poverty rate | Total Damaged or destroyed Houses | Totally Destroyed | Partially Damaged Houses | #HH Inside Evac Centres | #HH Outside Evac Centres | Total HH Displaced | % of HH Displaced | # of HH assisted to date (roof coverage) | Current Coverage | Agencies present (or indicating plans) | [11 empty] | Comments | Planned to work in certain municipality but niet not start activity yet
[7 empty] | # | # | # | # | # | # | % | # | % | DSWD | PRC | CRS | PLAN | ShelB | WV | DAI/BMFI | Good Neighbors | Caritas | JICA | CofC | IOM | GREEN CELL IS LEAD FOR MUNICIPALITY
071204000 | 1 | Antequera | 3146 | 3178 | 101% | 36.8 | 3178 | 976 | 2202 | 0 | 0 | 0 |  | 1597 | 50.25% | 36 | 158 | 677 | 586 |  | 139 |  |  | 1 |  |  |  | PRC: to start distribution/ PLAN: ongoing +20 tents | Save the children
071206000 | 2 | Balilihan | 3725 | 1673 | 44.91% | 51.9 | 1673 | 111 | 1562 | 0 | 0 | 0 |  | 53 | 3.168% | [8 empty] | 53
071209000 | 3 | Buenavista | 5874 | 3282 | 55.87% | 55.9 | 3282 | 354 | 2928 | 0 | 0 | 0 |  | 1440 | 43.88% | 343 | 802 | [6 empty] | 295
071210000 | 4 | Calape | 6549 | 5589 | 85.34% | 40.4 | 5589 | 1225 | 4364 | 4 | 0 | 4 | 0.07157% | 2456 | 43.94% | 466 | 1092 |  | 443 | [5 empty] | 455 |  |  |  | Habitat for Humanity
071212000 | 5 | Carmen | 9468 | 3602 | 38.04% | 55.2 | 3602 | 287 | 3315 | 0 | 50 | 50 | 1.388% | 808 | 22.43% | 508 | [7 empty] | 300 |  |  |  |  | Habitat for Humanity
071213000 | 6 | Catigbian | 4929 | 4602 | 93.37% | 51.3 | 4602 | 209 | 4393 | 0 | 0 | 0 |  | 946 | 20.56% | 150 | 300 |  | 200 |  | 80 |  |  | 216 |  |  |  | PLAN: ongoing +35 tents
071214000 | 7 | Clarin | 4409 | 4255 | 96.51% | 39.2 | 4255 | 604 | 3651 | 118 | 69 | 187 | 4.395% | 1090 | 25.62% | 284 | 806 | [11 empty] | Adra
071215000 | 8 | Corella | 1673 | 552 | 32.99% | 32 | 552 | 15 | 537 | 0 | 0 | 0 |  | 24 | 4.348% | 24
071216000 | 9 | Cortes | 3323 | 2371 | 71.35% | 26.9 | 2371 | 416 | 1955 | 0 | 0 | 0 |  | 671 | 28.3% | 497 | [7 empty] | 174
071218000 | 10 | Danao | 3900 | 1207 | 30.95% | 62.1 | 1207 | 121 | 1086 | 6 | 0 | 6 | 0.4971% | 200 | 16.57% | [8 empty] | 200 |  |  |  |  | DSWD, World Vision
071224000 | 11 | Inabanga | 9406 | 6254 | 66.49% | 47.1 | 6254 | 691 | 5563 | 0 | 244 | 244 | 3.902% | 2299 | 36.76% | 414 | 690 | 775 | [5 empty] | 420 |  |  |  |  | Adra
071230000 | 12 | Loon | 9300 | 8190 | 88.06% | 38.8 | 8190 | 1820 | 6370 | 0 | 0 | 0 |  | 4488 | 54.8% | 949 | 2758 |  | 281 | 230 |  | 217 |  | 53 |  |  |  |  | Save the Children
071232000 | 13 | Maribojoc | 4452 | 4118 | 92.5% | 24.9 | 4118 | 1360 | 2758 | 62 | 29 | 91 | 2.21% | 2895 | 70.3% | 2014 | OG |  | 506 | 225 |  |  |  | 150 |  |  |  | PLAN: ongoing +41 tents | Habitat for Humanity, Save the Children
071236000 | 14 | Sagbayan | 4366 | 3894 | 89.19% | 48.8 | 3894 | 1066 | 2828 | 0 | 0 | 0 |  | 4176 | 107.2% | 518 | 282 | 1505 | [5 empty] | 321 | 1550 |  |  |  | Habitat for Humanity, World Vision
071237000 | 15 | San Isidro | 1983 | 1671 | 84.27% | 64 | 1671 | 311 | 1360 | 0 | 20 | 20 | 1.197% | 762 | 45.6% | 66 | 346 | [6 empty] | 350 |  |  |  |  | World Vision
071239000 | 16 | Sevilla | 2269 | 1249 | 55.05% | 52.2 | 1249 | 177 | 1072 | 0 | 0 | 0 |  | 0 | 0% | [13 empty] | ShelterBox
071245000 | 17 | Tubigon | 9756 | 4472 | 45.84% | 37.4 | 4472 | 755 | 3717 | 114 | 114 | 228 | 5.098% | 3815 | 85.31% | 479 | 1359 |  | 71 | 196 |  |  | 500 |  | 1210 |  |  | PLAN: ongoing +201 tents
|  | Total | 88528 | 60159 | 67.95% |  | 60159 | 10498 | 49661 | 304 | 526 | 830 | 1.38% | 27720 | 46.08%
[14 empty] | TOTAL/AGENCY |  | 6748 | 8593 | 2957 | 2087 | 651 | 219 | 217 | 500 | 2533 | 3215
OUTSIDE 17 PRIORITY AREAS - EMERGENCY SUPPORT - ONLY TARPS AND TENTS
PCODE_Mun |  | Location |  |  | Demographics |  | Damaged Houses (19/11/2013) | [6 empty] | Response (19/11/2013) |  | Activity
|  | Municipality | # HH Census | # displaced HH | % displaced HH | Poverty rate | Total Damaged or destroyed Houses | Totally Destroyed | Partially Damaged Houses | #HH Inside Evac Centres | #HH Outside Evac Centres | Total HH Displaced | % of HH Displaced | # of HH assisted to date (roof coverage) | Current Coverage | Agencies present (or indicating plans)
[7 empty] | # | # | # | # | # | # | % | # | % | DSWD | PRC | CRS | PLAN | ShelB | WV | DAI/BMFI | Good Neighbors | Caritas | JICA | CofC | IOM
| 1 | Baclayon | 4048 | 135 | 3.335% |  | 314 | 11 | 303 | [5 empty] | 0 | [11 empty] | 110
071207000 | 2 | Batuan | 2701 | 1038 | 38.43% | 46.8 | 1038 | 27 | 1011 |  |  |  |  | 1062 | 102.3% | 24 | [10 empty] | 1038
071217000 | 3 | Dagohoy | 4100 | 1036 | 25.27% | 56 | 1036 | 20 | 1016 |  |  |  |  | 1072 | 103.5% | 36 | [10 empty] | 1036
| 4 | Dauis | 8571 | 117 | 1.365% |  | 117 | 1 | 116 |  |  |  |  | 117 | 100% | [11 empty] | 117
071226000 | 5 | Getafe | 6037 | 1167 | 19.33% | 60.1 | 1176 | 64 | 1112 |  |  |  |  | 1226 | 104.3% | [8 empty] | 50 |  |  | 1176
| 6 | Guindulman | 6907 | 46 | 0.666% |  | 46 | 0 | 46 |  |  |  |  | 0 | 0%
071228000 | 7 | Loay | 3533 | 1094 | 30.97% | 28.4 | 1094 | 149 | 945 |  |  |  |  | 1118 | 102.2% | 24 | [10 empty] | 1094
071229000 | 8 | Loboc | 3544 | 1291 | 36.43% | 32.8 | 1291 | 120 | 1171 |  |  |  |  | 1291 | 100% | [11 empty] | 1291
| 9 | San Miguel | 5122 | 764 | 14.92% |  | 764 | 20 | 744 |  |  |  |  | 36 | 4.712% | 36
071240000 | 10 | Sierra Bullones | 5366 | 1416 | 26.39% | 54.4 | 1416 | 9 | 1407 |  |  |  |  | 1452 | 102.5% | 36 | [10 empty] | 1416
071241000 | 11 | Sikatuna | 1386 | 804 | 58.01% | 45.9 | 804 | 39 | 765 |  |  |  |  | 12 | 1.493% | 12
| 12 | Tagbilaran City | 21030 | 1967 | 9.353% | 11 | 1964 | 222 | 1742 | 0 | 40 | 40 |  | 1047 | 53.31% | 180 | [7 empty] | 267 |  |  | 600
|  | TOTAL BALANCE | 72345 | 10875 | 15.03% |  | 11060 | 682 | 10378 |  | 40 | 40 | 0.3678% | 8433 | 76.25%
[14 empty] | TOTAL/AGENCY |  | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317 | 0 | 0 | 7878
071201000 | 1 | Albuquerque | 2156 | 251 | 11.64% | 25.4 | 251 | 23 | 228 |  |  |  |  | 0 | 0% | [11 empty] | 251
071202000 | 2 | Alicia | 4842 | 740 | 15.28% | 53.7 | 740 | 24 | 716 |  |  |  |  | 48 | 6.486% | 48
071208000 | 3 | Bilar | 3715 | 562 | 15.13% | 47.9 | 562 | 16 | 546 | 0 | 54 | 54 |  | 204 | 36.3% | 204 | [10 empty] | 562
| 4 | Candijay | 6311 | 11 | 0.1743% |  | 11 | 0 | 11 | [5 empty] | 0%
071220000 | 5 | Dimiao | 3296 | 154 | 4.672% | 42.4 | 154 | 4 | 150 |  |  |  |  | 12 | 7.792% | 12 | [10 empty] | 154
| 6 | Duero | 3819 | 48 | 1.257% |  | 48 | 2 | 46 | [5 empty] | 0%
| 7 | Garcia-Hernandez | 5006 | 39 | 0.7791% |  | 39 | 4 | 35 | [5 empty] | 0% | [11 empty] | 39
071225000 | 8 | Jagna | 7076 | 180 | 2.544% |  | 180 | 4 | 176 |  |  |  |  | 0 | 0%
071227000 | 9 | Lila | 2397 | 138 | 5.757% | 42.6 | 138 | 1 | 137 |  |  |  |  | 0 | 0% | [11 empty] | 138
| 10 | Panglao | 6215 | 8 | 0.1287% |  | 8 | 1 | 7 | [5 empty] | 0%
071234000 | 11 | Pilar | 5841 | 885 | 15.15% | 67.1 | 885 | 103 | 782 |  |  |  |  | 24 | 2.712% | 24 | [10 empty] | 885
| 12 | Talibon | 13335 | 1663 | 12.47% |  | 1663 | 64 | 1599 | [5 empty] | 0% | [11 empty] | 1663
071244000 | 13 | Trinidad | 6264 | 492 | 7.854% | 56.6 | 492 | 37 | 455 |  |  |  |  | 51 | 10.37% | 51
071247000 | 14 | Valencia | 5994 | 399 | 6.657% |  | 399 | 4 | 395 |  |  |  |  | 0 | 0% | [11 empty] | 399
|  | TOTAL | 76267 | 5570 | 7.303% |  | 5570 | 287 | 5283 |  | 54 | 54 | 0.9695% | 339 | 6.086%
[14 empty] | TOTAL/AGENCY |  | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091
|  | TOTAL BOHOL | [13 empty] | DSWD | PRC | CRS | PLAN | ShelB | WV | DAI/BMFI | Good Neighbors | Caritas | JICA | CofC | IOM
|  | BOHOL TOTAL | 237140 | 76604 | 32.3% | 0 | 76789 | 11467 | 65322 | 304 | 620 | 924 | 1.206% | 36492 | 47.52% | 7435 | 8593 | 2957 | 2087 | 651 | 219 | 217 | 500 | 2850 | 3215 | 0 | 11969
[14 empty] | 28724 | [12 empty] | PLANNED
NOT INCLUDING THE 11,969 PLANNED DISTRIBUTION FROM IOM
40693
INCLUDING IOM DISTRIBUTION
ACTIVITIES AGAINST TARGETS - HOUSING DAMAGE & DISPLACED HOUSEHOLDS : 10/12/2013

## 1. Antequera
PRIORITY AREAS | 1
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  |  |  | PARTIALLY DAMAGED
Antequera | 3178 |  |  |  |  | 976 |  |  |  |  | 2202
LEAD AGENCY | PRC/IFRC
BARANGAY | [10 empty] | TO CHECK FOR DISTRIBUTION
DISTRIBUTED BY | DSWD | PRC | CRS | PLAN | ShelB | WV | Caritas | BMFI | TOTAL | Ongoing |  | AMOUNT
Bantolinao |  |  |  | 310 |  |  |  |  | 310 |  | Angilan
Bicahan |  |  | 163 | [5 empty] | 163 |  | Can-Omay
Bitaugan | [5 empty] | 65 |  |  | 65 |  | Ceiling
Bungahan |  |  | 130 | [5 empty] | 130 |  | Danao
Canlaas |  |  |  | 181 |  |  |  |  | 181 | 10 tents Plan | Danicop
Cansibuan |  |  | 147 | [5 empty] | 147 |  | Poblacion
Mag-Aso |  |  |  | 95 |  |  |  |  | 95 | 10 tents Plan | Quinapon-An
Tagubaas |  |  | 105 | [5 empty] | 105 |  | Santo Rosario
Ubojan |  |  | 132 | [5 empty] | 132 |  | Tabuan
Viga | [5 empty] | 74 |  |  | 74 |  | Tupas
OVERALL DISTRIBUTION | [6 empty] | 1 |  | 1 |  | Villa Aurora
TOTAL DISTRIBUTED | [8 empty] | 1403
% DISTRIBUTED | [8 empty] | 44.15%

## 2. Balilihan
PRIORITY AREAS |  | 2
MUNICIPALITY |  | TOTAL DAMAGED HOUSES | TOTALLY DAMAGED | PARTIALLY DAMAGED
Balilihan |  | 1673 | 111 | 1562
LEAD AGENCY |  | PRC/IFRC
BARANGAY
DISTRIBUTED | Caritas | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Baucan Norte
Baucan Sur
Boctol
Boyog Norte
Boyog Proper
Boyog Sur
Cabad
Candasig
Cantalid
Cantomimbo
Cogon
Datag Norte
Datag Sur
Del Carmen Este
Del Carmen Norte
Del Carmen Sur
Del Carmen Weste
Del Rosario
Dorol
Haguilanan Grande
Hanopol Este
Hanopol Norte
Hanopol Weste
Magsija
Maslog
Sagasa
Sal-Ing
San Isidro
San Roque
Santo Niño
Tagustusan
TOTAL PER BARANGAY | 53 | 53
TOTAL DISTRIBUTED |  | 53
% DISTRIBUTED |  | 3.168%

## 3. Buenavista
PRIORITY AREAS | 3
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
Buenavista | 3282 |  |  |  |  | 354 |  |  | 2928
LEAD AGENCY | PRC/IFRC
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | Caritas | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Asinan |  | 170 | [5 empty] | 170 | Anonang
Bato |  | 173 | [5 empty] | 173 | Bago
Cambuhat |  | 262 | [5 empty] | 262 | Baluarte
Hunan |  | 197 | [5 empty] | 197 | Bantuan
Bonotbonot
Bugaong
Cambus-Oc
Cangawa
Cantomugcad
Cantores
Cantuba
Catigbian
Cawag
Cruz
Dait
Eastern Cabul-An
Lapacan Norte
Lapacan Sur
Lubang
Lusong (Plateau)
Magkaya
Merryland
Nueva Granada
Nueva Montana
Overland
Panghabgan
Poblacion
Puting Bato
Rufo Hill
Sweetland
Western Cabul-An
OVERALL DISTRIBUTION | 343 | [5 empty] | 295 | 638
TOTAL DISTRIBUTED | [7 empty] | 1440
% DISTRIBUTED | [7 empty] | 43.88%

## 4. Calape
PRIORITY AREAS | 4
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  |  | PARTIALLY DAMAGED
Calape | 5589 |  |  |  |  | 1225 |  |  |  | 4364
LEAD AGENCY | Plan International
BARANGAY | DSWD | PRC | CRS | PLAN | ShelB | JICA | BMFI
DISTRIBUTED | [7 empty] | AMOUNT | Ongoing | TO CHECK FOR DISTRIBUTION | AMOUNT
Abucayan Norte |  | 279 |  |  |  | 86 |  | 365 |  | Abucayan Sur
Bentig |  | 290 | [5 empty] | 290 |  | Banlasan
Bonbon |  | 230 | [5 empty] | 230 |  | Calunasan
Binogawan |  |  |  | 100 |  |  |  | 100 |  | Camias
Cabudburan |  |  |  | 114 |  |  |  | 114 |  | Catmonan
Canguha |  |  |  | 49 |  |  |  | 49 |  | Desamparados
Cabayugan |  |  |  | 180 |  |  |  | 180 |  | Kahayag
Mandaug |  | 293 |  |  |  | 319 |  | 612 |  | Kinabag-An
San Isidro | [5 empty] | 30 |  | 30 |  | Labuon
Santa Cruz | [5 empty] | 20 |  | 20 |  | Lawis
Liboron
Lomboy
Lo-Oc
Lucob
Madangog
Magtongtong
Mantatao
Sampoangon
Sojoton
Talisay
Tinibgan
Tultugan
Ulbujan
OVERALL DISTRIBUTION | 446 | [6 empty] | 446
TOTAL DISTRIBUTED | [7 empty] | 2436
% DISTRIBUTED | [7 empty] | 43.59%

## 5. Carmen
PRIORITY AREAS | 5
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
Carmen | 3602 |  |  |  |  | 287 |  |  | 3315
LEAD AGENCY | DSWD
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | Caritas | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Alegria
Bicao
Buenavista
Buenos Aires
Calatrava
El Progreso
El Salvador
Guadalupe
Katipunan
La Libertad
La Paz
La Salvacion
La Victoria
Matin-Ao
Montehermoso
Montesuerte
Montesunting
Montevideo
Nueva Fuerza
Nueva Vida Este
Nueva Vida Norte
Nueva Vida Sur
Poblacion Norte
Poblacion Sur
Tambo-An
Vallehermoso
Villaflor
Villafuerte
Villarcayo
OVERALL DISTRIBUTION | 508 | [5 empty] | 300 | 808
TOTAL DISTRIBUTED | [7 empty] | 808
% DISTRIBUTED | [7 empty] | 22.43%

## 6. Catigbian
PRIORITY AREAS | 6
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  |  | PARTIALLY DAMAGED
Catigbian | 4602 |  |  |  |  | 209 |  |  |  | 4393
LEAD AGENCY | Plan International
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | Caritas | AMOUNT | Ongoing | TO CHECK FOR DISTRIBUTION | AMOUNT
Alegria
Baang |  | 300 | [5 empty] | 300 |  | Ambuan
Bagtic |  |  |  | 200 |  |  |  | 200 | 35 tents Plan | Bongbong
Causwagan Norte | [5 empty] | 80 |  | 80 |  | Cambailan
Candumayao
Hagbuaya
Haguilanan
Kang-Iras
Libertad Sur
Liboron
Mahayag Norte
Mahayag Sur
Maitum
Mantasida
Poblacion Weste
Poblacion
Rizal
Sinakayanan
Triple Union
OVERALL DISTRIBUTION | 150 | [5 empty] | 216 | 366
TOTAL DISTRIBUTED | [7 empty] | 946
% DISTRIBUTED | [7 empty] | 20.56%

## 7. Clarin
PRIORITY AREAS | 7
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
Clarin | 4255 |  |  |  |  | 604 |  |  | 3651
LEAD AGENCY | DSWD
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | BMFI | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Bonbon |  | 271 | [5 empty] | 271 | Bacani
Mataub |  | 146 | [5 empty] | 146 | Bogtongbod
Poblacion Norte |  | 157 | [5 empty] | 157 | Bontud
Tontunan |  | 140 | [5 empty] | 140 | Buacao
Villaflor |  | 92 | [5 empty] | 92 | Buangan
Cabog
Caboy
Caluwasan
Candajec
Cantoyoc
Comaang
Danahao
Katipunan
Lajog
Nahawan
Poblacion Centro
Poblacion Sur
Tangaran
Tubod
OVERALL DISTRIBUTION | 284 | [6 empty] | 284
TOTAL DISTRIBUTED | [7 empty] | 1090
% DISTRIBUTED | [7 empty] | 25.62%

## 8. Corella
PRIORITY AREAS | 8
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
Corella | 552 |  |  |  |  | 15 |  |  | 537
LEAD AGENCY | DSWD
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | BMFI | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Anislag
Canangca-An
Canapnapan
Cancatac
Pandol
Poblacion
Sambog
Tanday
OVERALL DISTRIBUTION | 24 | [6 empty] | 24
TOTAL DISTRIBUTED | [7 empty] | 24
% DISTRIBUTED | [7 empty] | 4.348%

## 9. Cortes
PRIORITY AREAS | 9
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
Cortes | 2371 |  |  |  |  | 416 |  |  | 1955
LEAD AGENCY | DSWD
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | Caritas | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
De La Paz
Fatima
Loreto
Lourdes
Malayo Norte
Malayo Sur
Monserrat
New Lourdes
Patrocinio
Poblacion
Rosario
Salvador
San Roque
Upper De La Paz
OVERALL DISTRIBUTION | 497 | [5 empty] | 174 | 671
TOTAL DISTRIBUTED | [7 empty] | 671
% DISTRIBUTED | [7 empty] | 28.3%

## 10. Danao
PRIORITY AREAS |  | 10
MUNICIPALITY |  | TOTAL DAMAGED HOUSES | TOTALLY DAMAGED | PARTIALLY DAMAGED
Danao |  | 1207 | 121 | 1086
LEAD AGENCY |  | PRC/IFRC
BARANGAY
DISTRIBUTED | Caritas | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Cabatuan
Cantubod
Carbon
Concepcion
Dagohoy
Hibale
Magtangtang
Nahud
Poblacion
Remedios
San Carlos
San Miguel
Santa Fe
Santo Niño
Tabok
Taming
Villa Anunciado
TOTAL PER BARANGAY | 200 | 200
TOTAL DISTRIBUTED |  | 200
% DISTRIBUTED |  | 16.57%

## 11. Inabanga
PRIORITY AREAS | 11
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
Inabanga | 6254 |  |  |  |  | 691 |  |  | 5563
LEAD AGENCY | PRC/IFRC
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | Caritas | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Baguhan |  | 107 | 120 |  |  |  |  | 227 | Anonang
Cagawasan |  | 152 |  |  |  |  | 15 | 167 | Badiang
Canlinte |  |  | 117 |  |  |  |  | 117 | Bahan
Datag |  | 140 | [5 empty] | 140 | Banahao
Ilaya |  | 86 | [5 empty] | 86 | Baogo
Liloan Norte |  | 11 | [5 empty] | 11 | Bugang
Liloan Sur | [8 empty] | Cagayan
Napo |  |  | 152 |  |  |  |  | 152 | Cambitoon
Riverside |  | 61 | 77 |  |  |  |  | 138 | Cawayan
Santo Rosario |  | 133 | 140 |  |  |  |  | 273 | Cogon
Sua |  |  | 169 |  |  |  |  | 169 | Cuaming
Dagnawan
Dagohoy
Dait Sur
Fatima
Hambongan
Ilaud
Ilihan
Lapacan Norte
Lapacan Sur
Lawis
Lomboy
Lonoy Cainisican
Lonoy Roma
Lutao
Luyo
Mabuhay
Maria Rosario
Nabuad
Ondol
Poblacion
Saa
San Isidro
San Jose
Santo Niño
Tambook
Tungod
Ubujan
U-Og
OVERALL DISTRIBUTION | 414 | [5 empty] | 405 | 819
TOTAL DISTRIBUTED | [7 empty] | 2299
% DISTRIBUTED | [7 empty] | 36.76%

## 12. Loon
PRIORITY AREAS | 12
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
Loon | 8190 |  |  |  |  | 1820 |  |  | 6370
LEAD AGENCY | Shelter Box
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | Caritas | BMFI | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Agsoso |  | 18 | [5 empty] | 18 | Badbad Occidental
Basac |  | 212 | [5 empty] | 212 | Badbad Oriental
Basdacu |  | 128 | [5 empty] | 128 | Bagacay Katipunan
Bugho |  |  |  | 71 |  |  |  | 71 | Bagacay Kawayan
Cabadug |  | 54 | [5 empty] | 54 | Bagacay Saong
Catagbacan Handig |  | 176 | [5 empty] | 176 | Bahi
Catagbacan Norte |  | 181 | [5 empty] | 181 | Basdio
Catagbacan Sur |  | 183 | [5 empty] | 183 | Biasong
Cuasi |  | 158 | [5 empty] | 158 | Bongco
Moto Norte |  | 75 | [5 empty] | 75 | Cabacongan
Moto Sur |  | 61 | [5 empty] | 61 | Cabug
Nagtuang |  |  |  | 115 |  |  |  | 115 | Calayugan Norte
Napo |  | 299 | [5 empty] | 299 | Calayugan Sur
Pig-Ot |  | 117 | [5 empty] | 117 | Cambaquiz
Quinobcoban |  | 41 | [5 empty] | 41 | Campatud
Song-On |  | 122 | [5 empty] | 122 | Candaigan
Tangnan |  | 130 | [5 empty] | 130 | Canhangdon Occidental
Tontonan |  | 129 | [5 empty] | 129 | Canhangdon Oriental
Tubuan |  |  |  | 95 |  |  |  | 95 | Canigaan
Canmaag
Canmanoc
Cansuagwit
Cansubayon
Cantam-Is Bago
Cantam-Is Baslay
Cantaongon
Cantumocad
Cogon Norte
Cogon Sur
Genomoan
Lintuan
Looc
Mocpoc Norte
Mocpoc Sur
Nueva Vida
Panangquilon
Pantudlan
Pondol
Sondol
Talisay
Tan-Awan
Taytay
Ticugan
Tiwi
Tubodacu
Tubodio
Ubayon
Ubojan
OVERALL DISTRIBUTION | 949 |  |  |  | 230 | 53 | 217 | 1449
TOTAL DISTRIBUTED | [7 empty] | 3814
% DISTRIBUTED | [7 empty] | 46.57%

## 13. Maribojoc
PRIORITY AREAS | 13
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  |  | PARTIALLY DAMAGED
Maribojoc | 4118 |  |  |  |  | 1360 |  |  |  | 2758
LEAD AGENCY | PRC/IFRC
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | Caritas | AMOUNT | Ongoing | TO CHECK FOR DISTRIBUTION | AMOUNT
Anislag |  |  |  |  | 58 |  |  | 58 |  | Agahay
Bayacabac |  |  |  |  | 7 |  |  | 7 |  | Aliguay
Busao |  |  |  |  | 1 |  |  | 1 |  | Bood
Cabawan |  |  |  | 228 |  |  |  | 228 | 17 tents Plan | Lagtangon
Candavid |  |  |  | 133 |  |  |  | 133 |  | Lincod
Dipatlong |  |  |  |  | 40 |  |  | 40 |  | Punta Cruz
Guiwanon |  |  |  |  | 1 |  |  | 1 |  | San Isidro
Jandig |  |  |  |  | 16 |  |  | 16 |  | San Vicente
Pagnitoan |  |  |  | 145 | 1 |  |  | 146 |  | Tinibgan
Poblacion |  |  |  |  | 50 |  |  | 50
Punsod |  |  |  |  | 1 |  |  | 1
San Roque (Aghao) |  |  |  |  | 16 |  |  | 16
Toril |  |  |  |  | 34 |  |  | 34 | 23 tents Plan
OVERALL DISTRIBUTION | 609 | [5 empty] | 150 | 759
TOTAL DISTRIBUTED | [7 empty] | 1490
% DISTRIBUTED | [7 empty] | 36.18%

## 14. Sagbayan
PRIORITY AREAS | 14
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
Sagbayan | 3894 |  |  |  |  | 1066 |  |  | 2828
LEAD AGENCY | PRC/IFRC
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | JICA | Caritas | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Kabasacan |  |  | 142 |  |  |  |  | 142 | Canmao
Katipunan |  | X | 175 |  |  |  |  | 175 | Canmaya Diot
Sagbayan Sur |  |  | 295 |  |  |  |  | 295 | Langtad
San Roque |  |  | 136 |  |  |  |  | 136 | Libertad Norte
San Vicente Norte |  | X | 190 |  |  |  |  | 190 | Libertad Sur
San Vicente Sur |  |  | 65 |  |  |  |  | 65 | Mantalongon
Santa Catalina |  |  | 220 |  |  |  |  | 220 | Poblacion
Ubojan |  |  | 282 |  |  |  |  | 282 | San Isidro
Kagawasan |  | X | [5 empty] | 0 | San Ramon
Poblacion |  | X |  |  |  | 680 |  | 680
San Agustin | [6 empty] | 19 | 19
Santa Cruz | [6 empty] | 20 | 20
Canmaya Centro | [6 empty] | 18 | 18
Calangahan | [6 empty] | 20 | 20
Dagnawan | [6 empty] | 10 | 10
San Antonio | [5 empty] | 870 |  | 870
OVERALL DISTRIBUTION | 518 | 282 |  |  |  |  | 234 | 1034
TOTAL DISTRIBUTED | [7 empty] | 4176
% DISTRIBUTED | [7 empty] | 107.2%

## 15. San Isidro
PRIORITY AREAS | 15
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  | PARTIALLY DAMAGED
San Isidro | 1671 |  |  |  |  | 311 |  |  | 1360
LEAD AGENCY | PRC/IFRC
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | WV | Caritas | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Cabanugan |  | 151 | [5 empty] | 151 | Abehilan
Cambansag |  | 159 | [5 empty] | 159 | Baryong Daan
Masonoy |  | 36 | [5 empty] | 36 | Baunos
Caimbang
Candungao
Cansague Norte
Cansague Sur
Causwagan Sur
Poblacion
OVERALL DISTRIBUTION | 66 | [5 empty] | 350 | 416
TOTAL DISTRIBUTED | [7 empty] | 762
% DISTRIBUTED | [7 empty] | 45.6%

## 16. Sevilla
PRIORITY AREAS | 16
MUNICIPALITY | TOTAL DAMAGED HOUSES | TOTALLY DAMAGED | PARTIALLY DAMAGED
Sevilla | 1249 | 177 | 1072
LEAD AGENCY | SHELTER BOX
BARANGAY
DISTRIBUTED | AMOUNT | TO CHECK FOR DISTRIBUTION | AMOUNT
Bayawahan
Cabancalan
Calinga-An
Calinginan Norte
Calinginan Sur
Cambagui
Ewon
Guinob-An
Lagtangan
Licolico
Lobgob
Magsaysay
Poblacion
TOTAL PER BARANGAY | 0
DISTRIBUTED BY DSWD IN MUNICIPALITY | 0
TOTAL DISTRIBUTED | 0
% DISTRIBUTED | 0%

## 17. Tubigon
PRIORITY AREAS | 17
MUNICIPALITY | TOTAL DAMAGED HOUSES |  |  |  |  | TOTALLY DAMAGED |  |  |  | PARTIALLY DAMAGED
Tubigon | 4472 |  |  |  |  | 755 |  |  |  | 3717
LEAD AGENCY | PLAN INTERNATIONAL
BARANGAY
DISTRIBUTED | DSWD | PRC | CRS | PLAN | ShelB | JICA | Good N | AMOUNT | ONGOING | TO CHECK FOR DISTRIBUTION | AMOUNT
Banlasan | [8 empty] | 8 tents by Plan | Bagongbanwa
Bosongon | [8 empty] | 9 tents by Plan | Batasan Island
Cabulihan |  |  |  |  | 42 |  |  | 42 | 75 tents by Plan | Bilangbilangan Island
Centro |  | 45 |  |  | 21 |  |  | 66 |  | Buenos Aires
Guiwanon | [7 empty] | 0 | 14 tents by Plan | Bunacan
Ilijan Sur |  |  |  |  | 5 |  |  | 5 | 5 tents by Plan | Cahayag
Macaas |  |  |  |  | 32 |  |  | 32 | 34 tents by Plan | Cawayanan
Panaytayon |  | 187 |  |  |  | 290 |  | 477 |  | Genonocan
Pinayagan Norte | [5 empty] | 520 |  | 520
Pinayagan Sur |  |  |  |  | 18 | 400 |  | 418 |  | Ilijan Norte
Pooc Occidental |  | 24 | [5 empty] | 24 |  | Libertad
Pooc Oriental |  | 564 | [5 empty] | 564 |  | Matabao
Potohan |  | 327 | [5 empty] | 327 |  | Mocaboc Island
Tan-Awan |  |  |  | 45 |  |  |  | 45 |  | Panadtaran
Tinangnan |  |  |  | 26 | 33 |  |  | 59 |  | Pandan
Ubojan |  | 5 |  |  | 45 |  |  | 50 | 41 tents by Plan | Pangapasan Island
Pinayagan Norte
Talenceras
Ubay Island
Villanueva
OVERALL DISTRIBUTION | 479 | 203 |  |  |  |  | 500 | 1182
TOTAL DISTRIBUTED | [7 empty] | 3811
% DISTRIBUTED | [7 empty] | 85.22%