## Sheet1
|  | Global Shelter Cluster |  |  |  |  | 18.04.2013
ShelterCluster.org
Coordinating Humanitarian Shelter
Working Group on Accountability
Background (this section needs to outline clearly what the context/background of the issues are or the gaps/needs to which the activities listed below relate. Refer to 2013 Thematic Priorities document)
Throughout 2012 the GSC advanced a number of initiatives that aimed at better articulating the impact of shelter cluster coordination and response activities. In doing so, members of the GSC Working Group (WG) on Assessing Impact identified the need to expand the scope of the group’s activities to encompass all elements of the humanitarian program cycle, from preparedness, to assessment and planning, to monitoring, reporting and evaluation. A number of guidelines have been developed and piloted at country level to this purpose, including assessment and indicator guidelines. In parallel, the Emergency Capacity Building (ECB) project has supported the shelter cluster throughout 2012 in strengthening capacities to integrate accountability to affected populations (AAP) in shelter programming. This has resulted in a number of country level accountability reviews and the development of various tools to support shelter practitioners in designing, implementing, and monitoring shelter programs that are accountable to those they aim to support. It was felt, however, that there are elements of accountability to and among other stakeholders that remain unaddressed. Additional work is needed to better facilitate the integration of AAP in shelter programs. The GSC 2013 priority focus area on Accountability brings together the work of the 2012 WG on Assessing Impact and the ECB initiative on AAP into a more integrated and holistic approach to accountable shelter coordination and programming.
Objective
The overall objective of the Working Group is increase the accountability of humanitarian shelter interventions towards affected populations and humanitarian stakeholders. This will be achieved throguh two specific objectives: 1. Strengthening of cluster information systems at country and global levels along the various stages of the program cycle. This would encompass data preparedness, assessments, planning and strategy development, monitoring, reporting, and impact evaluations. Priority outputs would include: a. Development and/or strengthening of guidelines and tools on data preparedness, assessments, planning and strategy development, monitoring, reporting and evaluations. b. Development of a related global MIS enabling to better capture information and data across the program cycle at the country level and its consolidation at the global level. c. Piloting and roll out of the outputs mentioned above at the country level, including the conduct of interagency assessments, enhanced strategy development, reporting, impact evaluations and the consolidation of all information in a dedicated MIS. 2. Facilitate better integration of Accountability to Affected Populations in shelter programs. The outputs above should support the requirements defined by the IASC in terms of performance and impact monitoring and accountability. The development of guidelines on impact evaluation should be accompanied by advocacy activities with donors on the need for extended timeframes for shelter impact evaluations, which take into consideration the longitudinal impact of humanitarian shelter response.
No. | Priority (High, Medium, Low) | Activity | Output/Result | Comments | By who (Lead, participants) | For when (Date) | Status (Finished, on-going, to be defined)
1 | High | Design and implementation/piloting of Shelter Information System encompassing the entire project cycle; and in line with IASC reference documentation | At least four rapid interagency shelter cluster assessments completed at country level, resulting in assessment reports and monitoring of the follow up | The interagency assessments will be facilitated by dedicated IMPACT teams seconded to country level clusters, in line with assessments conducted in 2012 | IMPACT, IOM, UNHCR, IFRC | November 2013 | Ongoing (two assessments completed in Philipines in 2013)
|  |  | Update the indicator guidelines and compendium (including baseline, progress and evaluation indicators) encompassing IASC and other reference material | Existing indicator guideline document should remain the single depository for shleter cluster indicators. Guidelines and related indicator list to be reviewed and updated | IOM, IMPACT, UNHCR, IFRC, UNHABITAT | June 2013 | To be defined
|  |  | Draft country level reporting guidelines and toolbox for (a) individual country cluster member agencies and (b) for the country shelter cluster as a whole | A reporting system for country level cluster members to be developed accoridng to the indicator list and using the MIS system (see below) | IOM, IMPACT, UNHCR, IFRC, UNHABITAT | July 2013 | To be defined
|  |  | A country cluster MIS system is developed to encompass the entire programme cycle (assessment, reporting/monitoring, evaluation). | A standard MIS system will be developed to enable capture of assessment, reporting and evaluation, as well as secondary data; as well as the display of data through dedicated portal | IMPACT, IFRC, UNHCR, IOM, UNHABITAT | July 2013 | To be defined
|  |  | Reporting guidelines and and MIS piloted in atleast one response |  | IMPACT, IFRC, IOM, UNHCR, IOM, UNHABITAT | November 2013 | To be defined
2 | High | To develop and pilot a methodology for country-level impact evaluations. This will build upon the ongoing and planned work by the UNHABITAT-led TAC on Shelter and Settlement Impact Evaluation. UNHCR has also developed ToRs for a consultancy to complement and expand that work as part of the work of the Accountability WG; in line with IASC's reference documentation. | One guideline and toolbox is drafted on evaluation on country level cluster outputs and outcomes, including: (a) performance of the cluster coordination team; (b) the influence of the cluster cooridnation team on partners' response; (c) the impact of the shelter cluster on the response. The evaluations are piloted in at least 2 responses | The activity will leverage on the tools and lessons learnt of related IFRC evaluations. Findings of evaluations will be linked to the MIS system and will feed into the impact evaluations (see activities above). UNHCR has developed and circulated a TOR for recruiting a dedicted staff for the activity. | UNHABITAT, UNHCR, IOM ACTED, IMPACT | August 2013 | Ongoing
|  |  | One guideline and toolbox is drafted on evaluation on the impact of sector-wide shelter response in a country. The impact evaluation is piloted in at least 1 response | The Activity will be conducted in the framework of the ongoing dedicated UNHabitat-led TAC, to which the majority of Accountability WG members already participate. Results of impact evaluations will be made available in the MIS system and related web portal to be developed by the WG (see above). The activity will focus on evaluating impact at teh end of a cluster cycle, infomring the impact of shleter interventions on the overall response and on the longer-term ecovery process. A fist pilot is planned in June 2013, prossibly in teh Philippines. | UNHCR, UNHABITAT, IOM, ACTED, IMPACT, | August 2013 | Ongoing
3 | High | Design template and guidance for incountry shelter strategy | Template with explicatory notes | The strategy templates should be developed in line with the timeline of the cluster deployments. Initially, for eg, shorter templates should be proposed to feed into the flash and revised flash appeals. All templates should enable the provision of information in a concise manner. The actvity will build on work by IFRC in the Philippines | IFRC, UNHCR, IOM, ACTED | July 2013 | Ongoing (based on Philippines)
4 | High | Develop recommendations and guidance on how to operationalise the Shelter Accountability resources document of the ECB project | Beneficiary Participation, Communications and Accountability issues integrated into the programme cycle of the clusters work | Rather than producing new documentation on the subject, the WG will facilitate the access to and use of the already existing best practices (HAP, Joint standard, etc) on humanitarian accountability by shleter cluster members. No specific downward accountability mechanisms (eg: complaint mechanisms) will be developed by teh shelter cluster, as these should be the responsibility of implementing agencies. On teh other hand, other activities to be implemented by the WG will directly enhance horizontal and upwards accountability of the cluster | IOM, IFRC | November 2013 | To be determined