## WWW summary
Bohol Earthquake - Who What Where and When
Households
Organisation | Municipality | Barangay | Type of shelter relief: | Specification of materials - size, type. Durable for at least 6mths | Number of items | Tarpaulines | Tents | Tool kits | NFI's | Status - planned, on going, complete | Start Date | Completed date | Comments
|  |  | tarpaulins, tents, NFI's, building materials, cash | [8 empty] | Completion date | Comments
Gap | [5 empty] | 39439
Total required | [5 empty] | 53439 |  |  |  | Assumes all damged and destroyed houehold need support
Total temporary shelter | [5 empty] | 14000 |  |  |  | Assumes most families need two tarpualins - this could vary
Total accounted for | [5 empty] | 12500 | 1500 | 225 | 9500
DSWD | TBC | TBC | Core tents | DSWD raid emergency shelter. Tarps - laminated sack, nails, wire and cash for work - 3 days for 3 ppl | 2000 | 2000 |  |  |  | On-going |  |  | Not part of longer term temp shelter. Plan to complete 2000 units by 26/10/13
Philippines Red Cross/IFRC | TBC | TBC | Tarpaulins | IFRC standard 6x4 tarps - 2 per family | 1000 | 500 |  |  |  | On-going | 2013-10-20
Philippines Red Cross/IFRC | TBC | TBC | Tarpaulins | IFRC standard 6x4 tarps - 2 per family | 10000 | 5000 |  |  |  | Planned | 2010-10-22 |  | Planned arrival date Wed 23 Oct
Philippines Red Cross/IFRC | TBC | TBC | Tents | IFRC family tent | 300 |  | 300 |  |  | Planned | TBC
Philippines Red Cross/IFRC |  |  | NFI sets | Plastic mats, etc | 1000 |  |  |  | 1000
World Vision | TBC | TBC | Tents | TBC - 8x10 | 200 |  | 200 |  |  | Planned | 2013-10-24
World Vision |  |  | Tarpaulins | TBC | TBC | TBC
World Vision |  |  | NFI | Plastic mats, etc | 8000 |  |  |  | 8000
Shelter box | Loon & Maribojoc…. |  | Tents | Shelter box tent | 1000 |  | 1000 |  |  | Planned | 2013-10-24
Shelter box |  |  | NFI | Shetler box NFI | 500 |  |  |  | 500 |  | TBC
Shelter box |  |  | Tool kits | Shelter box - carpentary tools | 225 |  |  | 225 |  |  | TBC
IOM | TBC | TBC | Tarpaulins | International standards - 2 per family | TBC | TBC |  |  |  | Planned | TBC
CRS | TBC | TBC | Tarpaulins | CRS A frame temp shelter Int standard - 6x4 tarps + nails + training/guidance | 1000 | 1000 |  |  |  | Planned | 2013-10-24
CRS |  |  | Tarpaulins | CRS A frame temp shelter Int standard - 6x4 tarps + nails + training/guidance | 2000 | 2000 |  |  |  | Planned | TBC
Plan |  |  | Tarpalins | TBC | 2000 | 1000 |  |  |  | Planned | TBC
Caritas |  |  | Tarpalins | TBC | 4000 | 2000 |  |  |  | Planned | TBC
Adra |  |  | Tarpalins | TBC | 2000 | 1000 |  |  |  | Planned | TBC
NDR |  |  | Tent +NFI | TBC | TBC |  | TBC |  | TBC | Planned | TBC
Helping hands |  |  |  | Deconstruction programme - save houses save lives
Save the Children
Habitat for Humanity |  |  |  | 9 temp hospitals
Care
Christian Aid
NGO's
Local groups
Private

## Agency by Municpality
PROVINCE/CITY/ MUNICIPALITY |  |  |  | Number of damaged houses |  |  | Implementing Agency by Municipality
|  |  | Brgys. | Total | Collapsed | Damaged
BOHOL |  | 1016259 | 906 | 52481 | 14236 | 38247
DSWD Affected Populations
1 | Calape | 30146 | 33 | 5500 |  | 5500 | DSWD, PLAN
2 | Carmen | 43579 | 29 | 5816 | 1215 | 4601 | Caritas, Habitat, DSWD
3 | Alicia | 22285 | 15 | 4387 | 884 | 3503
4 | Cortes | 15294 | 14 | 3450 |  | 3450
5 | Catigbian | 22686 | 22 | 4025 | 1188 | 2837 | DSWD, WVI
6 | Balilihan | 17147 | 31 | 2939 | 707 | 2232 | Habitat
7 | Batuan | 12431 | 15 | 999 | 54 | 945
8 | Loboc | 16312 | 28 | 1140 | 115 | 1025 | Habitat
9 | Sikatuna | 6380 | 10 | 1261 | 436 | 825 | Shelterbox
10 | Inabanga | 43291 | 50 | 1951 | 316 | 1635 | Caritas
11 | Sevilla | 10443 | 13 | 627 | 51 | 576 | Shelterbox
12 | San Isidro | 9125 | 12 | 519 | 127 | 392 | WVI
13 | Loon | 42800 | 67 | 2327 | 2014 | 313 | Shelterbox, PRC, Habitat, CRS, PLAN, DSWD
14 | Antequera | 14481 | 21 | 3150 | 3000 | 150 | CRS, PRCS, PLAN
15 | Buenavista | 27031 | 17 | 146 | 35 | 111 | Habitat
16 | Alburquerque | 9921 | 11 | 150 | 60 | 90
17 | Lila | 11985 | 18 | 102 | 3 | 99
18 | Getafe | 27788 | 24 | 1834 | 316 | 1518
19 | Dauis | 39448 | 12 | 43 | 2 | 41
20 | Duero | 17580 | 21 | 78 | 40 | 38
21 | Loay | 16261 | 24 | 139 | 109 | 30
22 | Garcia-Hernandez | 23038 | 10 | 21 | 1 | 20
23 | Talibon | 61373 | 22 | 53 | 33 | 20
24 | Danao | 17952 | 17 | 15 | 6 | 9 | WVI, Caritas, DSWD
25 | San Miguel | 23574 | 18 | 5 |  | 5
26 | Corella | 7699 | 8 | 13 | 13
27 | Sagbayan | 20091 | 24 | 2 | 2 | 2 | WVI, PRC, CRS, Habitat
28 | Maribojoc | 20491 | 22 | 3336 | 1906 | 1430 | Shelterbox, Habitat, PLAN
29 | Clarin | 20296 | 24
30 | Tubigon | 44902 | 34 | 6382 | 1395 | 4987 | Shelterbox-Plan, PRC
31 | Trinidad | 28828 | 20 | 1115 | 13 | 1102
32 | Ubay | 68578 | 9
33 | Valencia | 27586 | 35
34 | Panglao | 28603 | 10
35 | Pilar | 26887 | 21 | 350 | 22 | 328
36 | Jagna | 32566 | 33 | 180 | 4 | 176
37 | Guindulman | 31789 | 19
38 | Baclayon | 18630 | 17
39 | Bilar | 17098 | 19 | 281 | 25 | 256
40 | Dimiao | 15166 | 35 | 145 | 144 | 1
41 | Sierra Bullones | 24698 | 22
Note on G5: Customer: DSWD - terms - Totally damaged
Note on H5: Customer: DSWD - Terms- Partically Damaged

## Flash and CERF
|  | # | # | $ | $ | total $ | Rate $
| Agency | Emergency | Trans | Emergency | Trans
| Govt | 2000 |  |  |  | 0
| RCRC | 12000 |  |  |  | 0
0
Flash and Cerf action plan | [5 empty] | 0
| CRS | 9000 | 4000 | 554454 | 2500000 | 3054454 | 61.606
| WVI | 4239 |  | 700000 |  | 700000 | 165.1333
| Habitat for Humanity | 10000 |  | 1500000 |  | 1500000 | 150
| ADRA | 5300 |  | 500000 |  | 500000 | 94.3396
| IOM | 12000 |  | 5000000 |  | 5000000 | 416.6667
0
Outside action plan | [5 empty] | 0
| Plan | 1000 |  |  |  | 0
| Caritas | 1000 |  |  |  | 0
| Adra | 1000 |  |  |  | 0
0
Linkages | [5 empty] | 0
| Oxfam |  |  |  |  | 0
| UNDP |  |  |  |  | 0
0
| Totals | 57539 | 4000 | 8254454 | 2500000 | 10754454
Total damaged or destroyed |  | 53439
Not covered |  | -4100 | -7.672%