Version 20 August 2012

| Annex 1: L3 Cluster Activation Checklist for the first 30 days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| L3 Cluster Activation and Implementation checklist, the first three months |  |  |  |  |  | Days |  |  |  |  |  |  |  |  |  |  |  |  |  | Week |  | Month |  |
| Action | Deliverable | Location of action focus | Lead | Timing | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 3 | 4 | 2 | 3 |
| Pre-Declaration Stage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assess country level coordination capacity by Global CLA and Global Cluster in consultation with Partners and field offices | Input to ED meeting on existing in-country capacity | Global, consulting country and region | GCLA + GCC + Global Cluster Partners | within 48 hours | X |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency Directors meet for Initial analysis of context, capacity, response requirements and make proposals to IASC Principals | Proposal for IASC Principals' decision on emergency | Global | Emergency Directors | within 48 hours |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Transformative Agenda - Leadership |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IASC Principals (including GCLA) meet and determine level of emergency | Determination of Level 3 emergency status | Global | IASC Principals and CLA | within 48 hours |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Global Cluster Lead Agency / Global Cluster deploys 'L3 ready' cluster coordinator on 'no regrets' basis | staff in place | Global | GCC + GCLA | within 72 hours |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GCLA / Global Cluster deploys IM specialist(s) on 'no regrets' basis | staff in place | Global | GCC + GCLA | within 72 hours |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GCLA and Global Cluster Partners deploy additional technical staff for needs assessmnt, strategic planning and elaboration of flash appeal | staff in place | Global | GCLA + Global Cluster Partners | within 72 hours |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Global Cluster Lead Agency / Global Cluster provides briefing notes to the IASC Principal of GCLA on leadership arrangements, rapid response deployments and cluster coordination mechanisms | briefing note | Global, consulting country and region | GCLA + GCC | in 7-10 days |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Transformative Agenda - Coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Country office of GCLA reviews if there is a coordination gap for its sector | note of findings | Country | CLA | within 48 hours |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HCT meeting where arguments are discussed for cluster activation where there are gaps, including detail at subnational level and designation of (co-)leads | Verbal arguments in HCT meeting and record of meeting | Country | HCT + CLA | within 48 hours, review at 3 months |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |
| Cluster/sector inputs to MIRA Preliminary Scenario Definition | Sector needs analysis as input to the MIRA PSD | Country | Cluster IM + CC | within 72 hours |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cluster Coordinators identify priority projects and resource requirements for staffing, based on MIRA/PSD strategic response priorities, for initial CERF allocation | list of cluster staffing requirements, prioritised project needs, estimated costs | Country | CC + Partners | within 72 hours |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cluster (co) lead agency presents priority projects and cluster staffing requirements to HC, for initial CERF allocation by HC | list of cluster staffing requirements and prioritised project needs, estimated costs | Country | HCT + CLA | within 72 hours |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Core Function 1 - Provide platform to support service delivery | Activate cluster coordination meetings Meeting Agenda, minutes, actions points | Country | CLA + CC | within 72 hours, then daily for first two weeks and bi-weekly till 8 weeks |  |  |  | X |  |  |  | X |  |  |  |  |  |  | X |  | X | X | X |
| Core Function 1 - A mechanism to avoid duplication | Establish 4W database | Country | IM | <72 hours, update as required |  |  |  | X |  |  |  | X |  |  |  |  |  |  | X |  | X | X | X |
| Core Function 2 - Sectoral needs assessment and gap analysis | Report on needs and gaps (for sector and as input to MIRA, initial strategic plan, initial flash appeal, MIRA report at 14 days, revised flash appeal, etc) | Country | CC + IM | <72 hrs, update within 5 days, further update <14 days |  |  |  | X |  | X |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Core Function 2 - Analysis for response, including cross cutting issues | Report on response analysis (for sector and as input to MIRA, initial strategic plan, initial flash appeal, MIRA report at 14 days, revised flash appeal, etc) | Country | CC | <72 hrs, update within 5 days, further update <14 days |  |  |  | X |  | X |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Core Function 2 - Prioritisation, grounded in resposne analysis | Defined priorities (also as input to MIRA PSD, HCT initial strategic plan, etc) | Country | CC + Partners | < 72 hours, update within 5 days |  |  |  | X |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Transformative Agenda - Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Core Function 3 - Develop sectoral plan | Sectoral plan, with objectives and indicators | Country | CC + Partners | within 5 days |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Core Function 3 - Cluster coordinators provide input to the HC initial strategic plan | sector input to initial strategic plan covering the first 3 months, including objectives and indicators | Country | CC + Partners | as of day 3, within 5 days |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Core Function 3 - Cluster Coordinator review final draft Initial strategic plan | final feedback to the HCT initial strategic plan | Country | CC + CLA | within 5 days |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Core Function 3 - Application and adherence to existing standards and guidelines | Promotion of standards and good practice | Country | CC + Partners | <72 hours and periodic update |  |  |  |  |  | X |  |  |  |  |  |  |  |  | X |  | X |  | X |
| Core Function 3 - Clarify funding requirements | Cluster budgets in flash appeal, CAP, ERF/CHF, CERF | Country | CC + IM | as per document timeline |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  | X |  | X |
| Core Function 4 - Identify Advocacy concerns | Input to HC/HCT messaging | Country | CC + IM | within 5 days and periodic as required |  |  |  |  |  | X |  |  |  |  |  |  |  |  | X |  | X |  | X |
| Core Function 4 - Undertake advocacy activities on behalf of cluster partners and affected population | Press release/Sitreps | Country | CC + Partners | at least twice per week for first two months |  |  |  |  | X |  |  |  | X |  |  | X |  |  | X | X | X | X | X |
| Core Function 5 - Cluster Coordinator reports to CLA on progress and achievements towards cluster objectives, based on defined indicators | Cluster/sector response monitoring and progress report | Country | CC + IM | weekly as of day 7 |  |  |  |  |  |  |  | X |  |  |  |  |  |  | X | X | X | X | X |
| Core Function 5 - Cluster Lead Agency reports to HC on progress and achievements towards cluster objectives, based on defined indicators | Cluster/sector progress report (as contribution to the humanitarian dashboard) | Country | CLA | weekly as of day 7 |  |  |  |  |  |  |  | X |  |  |  |  |  |  | X | X | X | X | X |
| Core Function 5 - Cluster coordinator facilitates consensus among operational partners on incorporating core Commitments on Accountability to Affected Populations. | CAAP integrated in partner programming | Country | CC + Partners | as of day 5 |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Core Function 6 - Contingency planning /preparedness for recurrent disasters whenever feasible and relevant | Review existing contingency/preparedness plan and update as required (or develop new ones as required) | Country | CC + Partners | after 3 months, review every six months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |