## Sheet1
| Global Shelter Cluster | [5 empty] | 26-03-2013
ShelterCluster.org
Coordinating Humanitarian Shelter
ENHANCED COHERENCE
Background (this section needs to outline clearly what the context/background of the issues are or the gaps/needs to which the activities listed below relate. Refer to 2013 Thematic Priorities document)
This area of priority was already identified last year and a working group was created to address it in 2012. Some of the outputs were completed, some remained as a draft. Thus in 2013 the existing drafts will be finalised and continued support to ongoing activities that cotribute towards coherence and develop new activities.
Objective
The objective of the working group is to enhancing shelter cluster coherence is to increase the predictability of country-level shelter clusters by establishing common methodologies, definitions, tools, roles and responsibilities.
No. | Priority (High, Medium, Low) | Activity | Output/Result | GSC Strategy Outcome/s (Refer to GSC strategy outcome numbers) | By who (Lead, participants) | For when (Date) | Status (Finished, on-going, to be defined)
Finalising 2012 drafts
1 | High (finalise drafts from 2012) | Boundaries with other clusters WASH | Tables explaining how the GSC shares responsibilities with the WASH, | 2.1 / 3.6 | UNHCR/CRS, HfH, IOM,IFRC,LightF, CARE | 2013-05-08 | onging
2 | High (finalise drafts from 2012) | Minimum requirements for country-level cluster leads and services to be provided | Table with the minimum requirements and services that country-level leads should provide | 2.2 | UNHCR/CRS, HfH, IOM,IFRC,LightF, CARE | 2013-05-08 | onging
3 | High (finalise drafts from 2012) | Cluster leads and funding mechanisms | The document provides recommendations on the relation between country-level shelter cluster leads and funding for shelter programs. | 1.6 / 3.1 | UNHCR/CRS, HfH, IOM,IFRC,LightF, CARE | 2013-05-08 | onging
4 | High (finalise drafts from 2012) | Guidance on dealing with Cross-cutting issues | Practical recommendations for shelter practitioners on how to address Gender, Protection, HIV, Environment and SGBV | 1.2 | UNHCR/CRS, HfH, IOM,IFRC,LightF, CARE | 2013-05-08 | onging
5 | High (continue development) | Boundaries with other clusters Early Recovery | Tables explaining how the GSC shares responsibilities with ER network, | 1.8 / 3.8 | CRS/HfH/ UNHABITAT | 2013-06-08 | onging
6 | High (continue development) | Boundaries with other clusters CCCM | Tables explaining how the GSC shares responsibilities with CCCM cluster | 2.1 / 3.6 | IOM/UNHCR | 2013-06-08 | onging
New work for 2013
7 | High | Enhance shelter cluster relation with national actors | Provide guidance on how to better link with national and local government, national level shelter and settlement practitioners, national professional bodies, national academia, and others. | 1.9 | UNHCR | 2013-07-08 | TBD
8 | High | Guidance on scope of country-level shelter clusters | Guidance on country-level shelter clusters’ role in emergency and longer term shelter and other issues based on the document of scope of the GSC. | 3.7 | IFRC /UNHCR | 2013-07-08 | TBD
9 | Medium | Integrated response | Provide guidance on how to include integrated planning of infraestructures, urban planning, and other related issues. | 1.2 / 1.8 | CRS/Light F | 2013-09-08 | TBD
10 | Medium | Preparedness at country level. | The document explains how the GSC can support preparedness in countries where country-level shelter clusters are not activated but disasters are likely to happen. | 1.4 / 3.8
11 | Medium | Criteria for handing over cluster coordination after emergency phase | (to be developed) | 1.8
12 | Medium | Linkages between the GSC and the country-level shelter clusters | (to be developed) | 2.1 / 2.2
13 | Medium | The SCT and ToRs for country-level shelter cluster positions | (to be developed) | 1.2