## Slide 1
UNHCR Syria
IDP Response – October 2012
UNHCR Syria – IDP Response
October 2012

## Slide 2
Context
Damascus in July 2012

## Slide 3
Context
Increasing numbers of IDPs: (1.2 m to 2.5 m)
Urban displacement
pattern
Volatile environment
& insecurity
Government–led response
Access and bureaucracy
Role of the Syrian Arab Red Crescent (SARC)
Impact of situation on staff
Impact of Sanctions

## Slide 4: UNHCR’s IDP response strategy
Addressing life-saving needs
Building on UNHCR Syria’s strengths: partnerships, programmes for refugees, field presence
Enhancing IDP community participation
Integration in the inter-agency response

## Slide 5: UNHCR and the Syria Humanitarian response plan (SHRP)
Chair of the NFI/Shelter working group
Co-chair of :
  the Community Services working group
  the Mental Health/ Psychosocial Support sub-working group
10 projects
7 sectors of the SHRP
40% of targeted SHRP displaced population
12% of SHRP financial requirements

## Slide 6: UNHCR IDP response – Activities

## Slide 7
Homs
Aleppo
Raqqah
Rural Damascus
Hassakeh
Deir Ezzor
Hama
Idleb
Dera’a
As Suweida
Lattakia
Tartous
Al Qunaytirah
DAMASCUS
Hama
Aleppo
Homs
Hassakeh
Deir Ezzor
Al Raqqah
Dera’a
UNHCR office/staff
NFIs
Health
Shelter visits
Cash
Comm. Services/
psychosocial support
Al Nabek
Tartous
UNHCR IDP Response Activities – Delivery by location (Oct. 2012)

## Slide 8: Winterization – “Keeping families warm”
UNHCR plastic sheeting used for improvised partitioning in communal shelters

## Slide 9: Winterization
Three components:
  NFI distribution
  Rehabilitation of communal shelters
  Financial Assistance
Time frame: 3 months
$ 32.4 m or 78% of financial requirements

## Slide 10: Winterization- NFI
Objective: 500,000 IDPs
Progress to date:
  Delivery to 200,000 IDPs
  Order for add. 125,000 IDPs
Concept:
  Enhanced winterized NFI package
  Family-based package
Constraints:
  Supply chain (local market)
  Procurement process
  Timely funding

## Slide 11: NFI Distribution - 08 October 2012
500,000
450.000
400,000
350,000
300,000
250,000
200,000
150,000
100,000
50,000
0
2012 July August September October November December Jan.
2013
Individuals served
SHRP target 2012 500,000
Progress to date Projected
90 Day Plan.
Oct. – Dec. 2012
Increased rate of NFI
Procurement and Delivery
200,000 IDPs
served to date
NFI for add. 125,000 IDPs up to 325,000 IDPs under procurement (funds available)
Urgent Winterization Needs
NFI for add. 175,000 IDPs
(Funds sought)
USD 8.2 million needed

## Slide 12: L:
Homs
Aleppo
Raqqah
Rural Damascus
Hassakeh
Deir Ezzor
Hama
Idleb
Dera’a
As Suweida
Lattakia
Tartous
Al Qunaytirah
DAMASCUS
Hama
Aleppo
Homs
Deir Ezzor
UNHCR office/staff
Access/ Assistance
ongoing
Other reported areas
of displacement
Movement s of
populations
NFI Assistance Planning Figures (individuals)
UNHCR IDP response – NFI assistance planning figures – October 2012
Al Nabek
Dera’a
Hassakeh
Al Raqqah
Tartous
Locations and movements indicative. Verification ongoing.
50,000
25,000
20,000
70,000
80,000
50,000
75,000
5,000
125,000
Close Rural Damascus
25,000
Approximate 2012 Movements and displacement figures in Syria
TOTAL:
500,000 Individuals
(100,000 families)

## Slide 13: Winterization- NFI

## Slide 14: Winterization – Cash Assistance
Distribution of cash assistance to IDPs in Al Nabek. August 2012

## Slide 15: Winterization – Cash Assistance
Objective:
40,000 families
(200,000 IDPs)
Progress to date:
Delivery to 3,300 families out of 5,200 in Al Nabek
Preparations for roll-out to Hassakeh (target: 8,500 families)
Concept:
One-time assistance for needs unmet through standard winterized NFI package
Builds on UNHCR’s refugee cash assistance experience
Constraint: Authorization to travel to distribution site (Al Nabek)
USD 1.6 million needed

## Slide 16: Winterization - Rehabilitation of Communal Shelters
Newly built school hosting IDPs in front of UNHCR office, Damascus

## Slide 17: Winterization - Rehabilitation of Communal Shelters
To initially rehabilitate 120 shelters
Light construction required – partitioning, walls, doors, windows
Heating only in communal areas. Water, sanitation and communal kitchens
Community services/ protection
Data / information on Government’s plans and all sites.
Objective
Concept

## Slide 18: Winterization - Rehabilitation of Communal Shelters
Progress to date:
UNHCR actively visiting communal shelters (70)
Progress made with the Ministry of Local Administration (MoLA)
Constraints:
New type of project
List of communal shelters to rehabilitate
USD 1.8 million needed
Displaced living in a classroom,
Al Nabek

## Slide 20: Health
Constraints:
Access to health facilities
Long procurement process and increasing international procurement
Overstretching capacity of partners
Objective:
Ensure access to
primary health care
for 130,000 IDPs and
emergency referrals
Concept:
Essential drugs, consultations, lab. tests & referrals
Life-saving medical equipment to health facilities
Support provided mainly through SARC polyclinics and mobile clinics in IDP receiving areas
Progress to date:
Comprehensive primary healthcare to 28,000 IDPs through SARC (June-Sep.).
63,600 medical acts (consultations, lab. tests & drugs)
Procurement of medical equipment in progress.

## Slide 21: Community Services
Support to women & children
Objective:
Provide psychosocial and legal support to 100,000 vulnerable IDP women and children
Progress to date:
Field visits: identification, counseling, assistance and referrals
124 trained Syrian volunteers provide psychological first aid
Child protection and recreational support
Development of community centres
Constraints:
Nature of the work

## Slide 22: Education
“Back to school” project
Objective:
Improved school attendance of 57,000 IDP children
Progress to date:
Procurement of individual primary school kits and of 12th grade book sets
Coordination with other partners to avoid duplication
Constraints:
Finalization of distribution arrangements

## Slide 23: WASH
Objective:
Support &
complement
activities in main
areas of
intervention
Concept:
Water tankers to
support SARC & IDP
areas; Water project
in Hassakeh through
the Governorate
Progress to date:
Ongoing procurement
of 4 water tankers
Hassakeh Governorate

## Slide 24
Logistics and Security
NFI warehouses in SARC Distribution Centre,
Al Nabek

## Slide 25: Logistics and Security
Objective:
Facilitate the distribution and monitoring of assistance
Logistics:
Provide free-of-
charge logistics support (warehouses & transport means)
to partners
Staff Security:
Provide adequate vehicles for field visits, in compliance with UN security requirements

## Slide 26: Coordination
UN Inter-agency response
Long and well-established partnerships:
  SARC
  Authorities
  Local NGOs
  Governorate of Hassakeh

## Slide 27
Field assessment and monitoring
Community services visit to IDP family (Al Nabek, June 2012)

## Slide 28: UNHCR’s Implementation and Monitoring Capacity
Large team (350 staff, including 22 int. currently in the country)
IDP Unit established within UNHCR Damascus
Field presence: Aleppo, Hassakeh, Al Nabek
Recruitment of additional staff for Damascus and field
Recruitment of 21 field monitors
Establishment of Syrian outreach volunteers network planned

## Slide 29
Approx. USD 20 million received (50% of requirements)
Constraint: Urgent need for fresh funds to beat procurement deadlines and coming winter.
UNHCR Syria country level support:
A portion of earmarked contributions for the “Syria Situation” (for Syrian IDPs & Syrian refugees) also benefits UNHCR Syria:
Thank you!
Funding
Syria ERF