Status

| Strategy Status | Version | Status | Effective date | Next revision |
| --- | --- | --- | --- | --- |
|  | Final-Draft 1 | to be reviewed by cluster | 15/12/13 | Final |

Shelter Cluster Structure

| Response name | Bohol Earthquake, 2013 |
| --- | --- |
| Government lead agency and contact | Agency: Provincial Office /Provincial Engineers Office Name: Eng. Ben Redulla Email: benredz@yahoo.com Mobile: 09 999 932 807 Name: Ms Liza Quirog Email: lizaquirog65@yahoo.com Mobile: 09 173 246 600 |
| Cluster co lead Agency | IFRC |
| Cluster Coordinator Contact | Name: Birgit Vaes Email: coord.bohol@sheltercluster.org Mobile: 09 183 438 466 |
| Co-leads | Office of the Provincial Social Welfare And Development |
| Strategic Advisory Group (SAG) - Agencies | Preliminary draft: CRS, Habitat for Humanity, IOM, IFRC/PRCS, WVI, ADRA, BERN, Good Neighbours Int Final draft: IFRC/PRC, DSWD, IOM |
| Endorsing Cluster partner Members | ADRA, All Hands Volunteers, AusAid, Bangol Bohol, BEDRN, BMFI, Care, Caritas, Cong. Arthur Yaps Office, COSE, Couples of Christ, CRS, Disaster Assistance International, BLDF, ECHO, German RC, Good Neighbours Int, Habitat for Humanity, Handicap International, Helpage International, IDEA, IFRC, ILO, IOM, JICA, LDS, Oxfam, Plan International, PRC, Process Bohol Bangon, Save the Children, Shelter Box, Social Action Centre, Spanish Red Cross, UN Habitat, UNDP,UNICEF, USAID, World Bank, World Vision Philippines, Interaction, Holyname University, Tesda, PEO, |
| Relevant Technical Working Groups (TWiGs) | WG1 : REACH assessment |
|  | WG2 : Technical standards, structural assessment WG3 : Minimum standards for progressive core shelter WG 4: Demolishing and debris management WG 5: Minimum standards for beneficiary selection criteria WG 6: Repair and retrofitting of houses |

Situation and context

| Situation | On 15 October 2013 morning, a magnitude 7.2 earthquake struck Central Visayas in the Philippines. The Philippine Institute of Volcanology and Seismology (PHIVOLCS) reported that quake’s epicentre was located in the municipality of Sagbayan on Bohol Island, with an approximate depth of 32 kilometres. The quake is said to be the strongest to have hit the Central Visayas islands in more than 20 years. The earthquake caused landslides and extensive damage to housing, hospitals, schools, infrastructure and utilities with more than 76,700 houses severely damaged or destroyed. There were 223 casualties. More than 344,300 people were initially displaced. The authorities in Bohol and Cebu declared a state of calamity and the government has indicated that it will accept international assistance. Two months after the disaster less than 3,085 people are still living in evacuation camps. The rest are living outside their homes, afraid that further quakes will bring down buildings. Most of the people living in camps have no means of returning back to their original site since these sites are situated in hazardous areas. |
| --- | --- |
| Country Strategic Response Plan (SRP) Objectives | The HCT will provide targeted support to complement Government’s response capacity and address the urgent humanitarian needs of the most vulnerable people affected by the Bohol earthquake. Priority needs as articulated by the national disaster management authority are: - Coordination - Emergency shelter, including tents - Early recovery, including debris removal, rehabilitation of public building and demolition of condemned structures - WASH with a focus on sustainable access to clean drinking water, provision of hygiene kits, and portable toilets - Education, including temporary learning spaces - Food - Logistics, with mobile storage units, warehousing and transport assistance Further, the HCT identified health, psychosocial support, camp coordination and camp management (CCCM), nutrition, protection, livelihoods and agriculture as critical for the humanitarian relief and recovery. On 21 Oct the Humanitarian Coordinator stated the goal of the humanitarian was ‘to make a meaningful difference for the people most in need, in time, with the least capacity to recover on their own.’ On 9 Dec the focus of the humanitarian activity is shifting from immediate relief to early recovery. - Priority needs include reconstruction and repair of damaged houses and rehabilitation of basic services. - With ongoing response to other emergencies in the country, agencies report resource constraints for comprehensive action in earthquake affected areas. |
| Cluster Objectives | Objective 1: Facilitate the production and distribution of adequate emergency shelter solutions and NFI’s from cluster partners and Government agencies which meet recognized humanitarian standards within two weeks after the disaster. Output indicators; Outcome indicators. 1.1 Number/% of HHs having received emergency shelter assistance; - Number/% of HHs that are satisfied with the emergency shelter support received from humanitarian agencies. 1.2 Number /% of HHs having received non-food items; 1.2 Number/% of HHs satisfied with non-food items assistance received from humanitarian agencies. 1.3 Number/% of HHs having received adequate shelter without external support; 1.3 Number/% of HHs satisfied with shelter without having received external support. Objective 2: Facilitate the production and implementation of adequate early recovery shelter solutions which facilitate self-recovery through technical guidance from cluster partners and Government agencies which meet recognized humanitarian standards within six weeks after the disaster. Output indicators; Outcome indicators. 1.1 Number/% of HHs having received a progressive core shelter in-kind (materials/vouchers/cash); - Number/% of HHs that are satisfied with the progressive core shelter support received from humanitarian agencies. 1.2 Number /% of HHs having assistance in- kind (materials/voucher/cash) to repair/rehabilitate their house; 1.2 Number/% of HHs satisfied with the repair/rehabilitation assistance received from humanitarian agencies. 1.3 Number/% of HHs having received technical support from humanitarian agencies or government agencies; 1.3 Number/% of HHs satisfied with the technical support received.. Objective 3: Facilitate the development of adequate IEC materials and standards for a demolishing toolkit regarding demolishing and debris management. Output indicators; Outcome indicators. 1.1 Number/% of HHs having received adequate IEC materials in regards to demolishing and debris management; - Number/% of HHs that are found the material in regards to demolishing and debris management useful. 1.2 Number/% of HHs having received a demolishing toolkit.; 1.2 Number/% of HHs who utilized the demolishing toolkit and managed the debris on site in an adequate way.. |
| Assessments | - HCT Rapid Needs Assessment 21st Oct 21 - Provincial Government and DSWD reporting to NDRRM – reported in situation reports twice daily, held on http://www.ndrrmc.gov.ph/ - Individual agency rapid assessments - REACH assessment – assessment complete by 7th, final report received on 25th November - Analysing of DAFAC list by DSWD on municipality level - Structural damage assessment by municipality engineers |
| Monitoring and Evaluation | - Agencies report to cluster weekly, cluster will collate data, and share at Cluster meetings and via www.sheltercluster.org website. - For the accountability to the beneficiaries a grievance mechanism will be implemented. HHs can contact one dedicated person at each LGU to deliver their complaints, a system to provide answers within an agreed amount of time will also be put in place. |

Key issues and recommendations

| Key issues | The following are some of the key issues identified at the time of writing. Also listed are possible mitigation measures which are recommended to the cluster partners for activities or for advocacy. |
| --- | --- |

| Key issues | Recommendations during emergency phase | Recommendations at start of early recovery phase |
| --- | --- | --- |
| - Urgent need for emergency shelter from the humanitarian sector that compliments what’s already provided by local government, private organisations, community based organisations and civil society in general, the amount and quality of which is not available. | - The cluster should be aware that where families are living under short term emergency materials, e.g. local agricultural tarps, etc., for an extended period of time these materials will need to be replaced. | - No second round of tarps distribution will be executed, only current gaps will be filled, since Agencies have ended or will end the emergency phase around the 15th of December and move into the early recovery phase. |
| - Access to reliable and consistent data both from the Government and the humanitarian sector which can be used to identify accurately needs and gaps in the response. | - Carry out a detailed assessment – REACH. - Agencies should validate data at Barangay level and feed that information back to the cluster and govt. | - Analysing of DAFAC card by DSWD on municipality level ongoing to be finalized mid-December - Agencies will use data from DSWD DAFAC card, this represents most vulnerable HHs. - Municipality engineers will undertake a structural damage assessment. - All data will be gathered in one general database (including DROMIC, NHA and DAFAC card data) managed on Provincial level by BICTU. |
| - Affected communities move quickly into their own early recovery. Agencies are slow to bring in emergency materials. | - Agencies should be rapid with their emergency response and quickly adjust their response to take account of the communities’ early recovery. - While agencies procure a respond with emergency items they should in parallel support affected families who have already started their own recovery – consider demolition, debris removal and recycling, repair, reconstruction, transitional shelter options, etc. | - Besides prepositioning tarps/tents repair toolkits should be prepositioned. |
| - There will be damaged houses which are unsafe to repair, but the families may repair them. This will make them even more vulnerable against future similar or lesser intensity earthquakes. | - Agencies should raise awareness of unsafe houses. - Advocate and support Gov. with appropriate structural assessment or surveys. | - The structural damage assessment by Municipality engineers started on 25th of November. - IEC is developed to inform HH that an engineer will come and assess the house. |
| - Possible need for transitional shelter phase for those who cannot return immediately due to major damage or government restriction on return. Period of this phase will depend on alternative sheltering options and access to safe sites. |  | - Agencies should agree common standard and approach to transitional shelter solutions. - Agencies should consider all transitional options : - Alternative transitional sites in existing structures private or public using privacy partitions including wash facilities - Replacement of the tents by PRC on evacuation areas selected and agreed on by the Government. - Provision of tents/tarps by PRC if original plot is not in danger zone or on save relative’s plot - Renting solutions are not working in rural areas, but could be used in urban areas. Agencies on the group are currently not providing a rental solution as an option. - Bunkhouses - Advocate for Government to have clear direction on resettlement planning , MGB needs to provide certification for safe build zone on targeted resettlement sides - Municipalities decide on declaring non-build zones and provisions of relocation areas. - Once resettlements sites are identified progressive core house construction can start |
| - The funding required to support the transitional phase may reduce the amount available to support full recovery. | - The transitional shelter phase should as much as possible also support full recovery. For example materials used to construct transitional shelters can also be incorporated in a permanent solution. | - The transitional phase will only be used for HHs living in hazard zones and cannot return to their original plot and where no immediate permanent relocation solution is found. - All new build structures will be progressive core houses, build according to the minimum standards a developed by the shelter cluster. - For repair of houses Agencies will provide materials/cash and technical advice to complete a save repair according to the build back better methodology |
| - A lack of clear understanding of what the full recovery would be and who would support it. | - Clarify with the Government what the recovery strategy will be. - Advocate for Government support to full recovery | - Gov. approved the draft shelter strategy mid-November. - The Gov. is in favour of moving from emergency phase immediately to recovery, selecting the progressive core house solution supports this statement |
| - Lack of funding recovery by donor community | - Clarify and confirm needs by detailed assessment and petition donors as appropriate. | - Due to typhoon Yolanda a lot of the Agencies have left and redirected their assistance to the Yolanda affected areas. |
| - Probable requirement for permanent relocations due to hazard mapping by Mines and Geoscience Bureau. | - Advocate for rapid production of hazard maps and declaration by Gov. of no build zone. - Advocate with Gov. and agencies to ensure all proposed relocations are acceptable by affected communities, taking into account their cultural, social and physical needs. - Advocate with Gov. and agencies to ensure all relocations are fully developed with physical infrastructure and social services. | - The hazard maps were made available mid Nov. - The declaration of no build zone is related to the certificates given by MGB for safe build zones. - It will be the responsibility of the Municipality to declare areas as hazard and attached to this no-build zone. - Relocation areas also need to be identified by the Municipality. Several municipalities have already identified these zones and have requested DSWD to implement progressive core house construction. |
| - Agencies may give different quality and value of relief or transitional solutions to same affected communities. | - The cluster should set and agree standards for each phase of the response. - Agencies should take responsibility for specific Barangays and ensure their needs are fully covered and the response is equitable and adequate. - An agency should be identified as the ‘lead agency’ for each Municipality. They should take on coordination responsibility with other agencies working in the Municipalities and local Government to ensure equitable and adequate response in line with the cluster agreed standards. They should also report on met needs and gaps. | - Minimum standards are developed for progressive core houses. - Minimum standards are being developed for repairs of houses. - In each municipality max 3 Agencies will be allowed to work, and only one agency per barangay for identical support. - Per municipality a data manager from the LGU will be trained to maintain the beneficiary list, all Agencies need to provide updated information to this data manger. These database mangers will be support for IM by IOM. - BICTU will manage the master list on Provincial level. |
| - Market capacity – inflation, supply. Prompt the shortage of materials. | - Coordinate with early recovery cluster - Where agencies use cash methodologies they should ensure they support the local markets to respond. - If required advocate for an EMMA. | - Working together with Bohol Chamber of Commerce. They will be responsible to maintain the prices of materials and if needed can purchase material in bulk from other provinces. |
| - Environmental impact - there may be a large demand for nippa plam, timber, coco lumber, etc, | - Coordinate with early recovery cluster Work with the Govt environmental agencies to identify restrictions on harvesting/using natural materials for each phase of the response. - If required advocate for an environmental impact assessment | - Buy material in bulk from other provinces if local supply is not sufficient or would harm small scale industry (e.g. bamboo basket production, coconut oil production) - If possible local market will be supported as much as possible. |
| - Environmental impact - there may be a requirement to dispose of building waste/rubble. - There may be hazardous materials such as asbestos which needs to be disposed of. | - Coordinate with early recovery cluster. - Work with municipal and Provincial Government on identifying appropriate and legal waste management solutions. | - UNPD is developing a waste management plan in coordination with the Government |

Definitions

| Target groups definitions | The following are the definitions of case loads. |
| --- | --- |

| # | Current location | House status | Total Fam. | Notes |
| --- | --- | --- | --- | --- |
|  | Evacuation centre – this refers to space around a public building or public space in the central part of a town or villages. It does not refer to a building. | - Displaced - Informal camp - Urban or rural | 586 | As from 16/11/13 IOM DTM in 6 municipalities. |
|  | Community space – this refers to families camped in small clusters close to their collapsed or damaged houses | - Displaced - Informal camps - Urban and rural | 748 | As from 16/11/13 IOM DTM in 7municipalities. |
|  | Home base – this refers to being adjacent to the location of the collapsed house. | - Non displaced | 75,455 | As from 12/12/13 DROMIC data, checking ongoing |
|  | Host families – with or close to relatives. | - Displaced | no figure available | It’s important not to confuse host families with normal multiple families living within the same household. This data is not available. No Agency is tracking this type of displacement. |
|  | Relocations - where houses has been demarked as located in hazardous zones by the Mines and Geoscience Bureau, families will be relocated to safe zones. | - Displaced - Formal - Rural | Can only be known after no build zones are identified | Final number will be subject to hazard mapping. Other significant hazards are landslides, sink holes and fault lines. Local Government needs to declare no building zone. |
|  |  | Total | 76,789 | As from 12/12/13 DROMIC data, checking ongoing |

| Damage definitions | The following are the definitions of housing damage. |
| --- | --- |

| # | Damage definitions | House status | Total | Notes |
| --- | --- | --- | --- | --- |
|  | Totally destroyed | - Collapsed - Not habitable | 11,467 | - DAFAC card checking by DSWD ongoing - Structural damage assessment ongoing |
|  | Major damage | - Not habitable. - Structural integrity compromised. - Cannot be repaired. | 65,322 | - Only after structural damage assessment is finalized the differentiation between major and partially damaged will be made |
|  | Partial damage | - Structural integrity not compromised. - Can be repaired |  |  |
|  | No damage | - No damage | TBC | - Structural damage assessment will define the houses with no damages |
|  |  | Total | 76,789 |  |

| Housing stock definitions | The following are the definitions of housing stock. See annex 2 for images of each definition’s |
| --- | --- |

| # | House type definitions | Total | Notes |
| --- | --- | --- | --- |
| 1 | Single story. Timber and bamboo frame. Timber and bamboo cladding. Nippa palm roof |  |  |
| 2 | Single story. Timber frame. Timber cladding. CGI roof. |  |  |
| 3 | Single story. Timber frame. Part low masonry part timber cladding. CGI roof. |  |  |
| 4 | Single story. Reinforced concrete frame. Masonry walls. CGI roof. |  |  |
| 5 | Two story. Ground floor reinforced concrete frame and masonry walls. First floor timber frame and timber cladding. CGI roof. |  |  |
| 6 | Two or more story. Ground floor and first floor reinforced concrete frame and masonry walls. CGI roof or flat reinforced concrete roof |  |  |
| 7 | Apartment two or more story reinforced concrete frame. |  |  |

| Vulnerability definitions | The following are the definitions of any vulnerability specific to the shelter needs over and above those considered as standard, e.g. single headed female households, elderly, people with disabilities, etc. |
| --- | --- |

| # | Individuals Total | Notes |
| --- | --- | --- |
|  | For many families the house is the main asset possible built up over many years of savings, remittance from overseas. However, at this time the family may not have an income which represents their physical asset. As such, they will not have the capacity to recovery to a similar standard of living. | Most vulnerable targeting should consider economic profiling rather than asset profile. |
|  | Families who had used their house as equity to borrow money. Now they have negative equity. |  |
|  | Land tenure – most will not have land tenure documentation. However, they may have tax declarations on the land. This is locally considered sufficient as right to abide. | As per minimum standards for beneficiary selection criteria: - Possession of a guarantee of ownership or permanent or long term occupancy of at least 10 years for 100% masonry houses and 5 years for houses in light materials on the lot on which to build the progressive core shelter unit. Land occupancy permissions should be signed by the owner of the land and witnessed by the barangay authority. - In case the recipient of the repair assistance doesn’t own the house the proposed intervention needs to be agreed on by the owner of the house. If applicable this intervention doesn’t implicate any increase of rent for the next 2 years as result of this intervention. |
|  | One parent works abroad and provides the main source of income come from overseas remittances. The second parent is at home supporting the recovery on their own. |  |
| # | Groups | Notes |
|  | Ethnic groups – none recorded at this time. | Should check for any ethnic groups. |

Response Plan

| Target Groups |  | Estimated Total Caseload | Emergency Activities (up to 6 weeks – if applicable) |  | Recovery Activities (up to 12 months – if applicable) |  | Targets/ Assumptions/Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target #HH | Approved Interventions and Standards | Target #HH | Approved Interventions and Standards |  |
| Displaced | HH located in Evacuation centre | 13,500 | 3000 | INT1 |  |  | HHs will have returned to PoO in early recovery phase. Will be considered as per Non Displaced table. |
|  |  |  | 8000 | INT 2 |  |  |  |
|  |  |  | 500 | INT 4 |  |  |  |
|  |  |  | 2000 | INT 10 |  |  |  |
|  | Community space, unplanned camp | 16,000 | 3000 | INT1 |  |  |  |
|  |  |  | 10000 | INT 2 |  |  |  |
|  |  |  | 1000 | INT 4 |  |  |  |
|  |  |  | 2000 | INT 10 |  |  |  |
|  | Relocation: HH living in hazard zones/ incorporated to camps during emergency phase | 2,013 |  |  | 55 | INT 5 | Incorporated in camp population during emergency phase. HHs can’t return to PoO due to no-build zone. Will be relocated when land is available. During intermediary phase transitional options will be provided. |
|  |  |  |  |  | 170 | INT 6 |  |
|  |  |  |  |  |  | INT 7 |  |
|  |  |  |  |  |  | INT 8 |  |
|  |  |  |  |  |  | INT 9 |  |
|  |  |  |  |  | 894 | INT 11 |  |
|  |  |  |  |  | 894 | INT 16 | HH in relocation area or on new land due to living in hazard area |
|  | SUBTOTAL |  |  |  |  |  |  |
| Non Displaced | Host families requiring assistance |  |  | INT 2 |  | INT 15 | These numbers have not been tracked by any organization |
|  |  |  |  | INT 4 |  |  |  |
|  |  |  |  | INT 10 |  |  |  |
|  | Home based: HH with totally/major damaged houses | 39,360 | 2000 | INT 1 | 14,180 | INT 11 | HHs from evacuation centres and unplanned camps have returned to PoO in early recovery phase |
|  |  |  | 5000 | INT 2 | 3000 | INT 12 |  |
|  |  |  | 500 | INT 4 | 11,180 | INT 16 |  |
|  |  |  | 3500 | INT 10 |  |  |  |
|  | Home based: HH with partially damaged houses | 131,648 | 2500 | INT 1 | 60,039 | INT 11 | HHs from evacuation centres and unplanned camps have returned to PoO in early recovery phase |
|  |  |  | 5500 | INT 2 | 60,039 | INT 13 |  |
|  |  |  | 120 | INT 3 |  | INT 14 |  |
|  |  |  | 500 | INT 4 |  |  |  |
|  |  |  | 2950 | INT 10 |  |  |  |
|  | SUBTOTAL |  | 52,070 |  | 150,451 |  |  |
| TOTAL CASELOAD |  | 202,521 |  |  |  |  |  |

Technical Standards and Intervention Types

| INT# | Intervention Name | Description/Specification | Value | Notes and standards |
| --- | --- | --- | --- | --- |
| EMERGENCY RESPONSE |  |  |  |  |
| INT 01 | Immediate household level or family level | Emergency shelter solutions provided immediately following the Earthquake provided by local government, private organisations, faith based organisations, community based organisations and civil society in general. Design life not less than 1-2 months. | 2000 to 5000PHP | Materials delivered do not necessarily comply with acceptable standards in size and quality. To be monitored and upgraded as deemed necessary. |
| INT 02 | Emergency shelter solutions – household level or family level | Provide standard tarpaulin to those who are unable to stay in their own house, both displaced and non-displaced. Provide IEC material in fixing and tying tarpaulins and demonstrate options for salvage materials in making structure Design life: 6 months | 2000 to 5000PHP | Sphere standards, acceptable quality tarpaulins standards apply, (IFRC, UNHCR, UNICEF, ICRC, MSF, and OXFAM), see annex two |
| INT 03 | Additional Shelter Materials | Provide materials, including additional tarpaulins, timber, consumables & tools for improving durability and functionality of emergency shelters. Cash or vouchers can be provided in lieu of materials following analysis of market capacity. Design life: 6 months | 2000 to 5000PHP | Targeted for families who are unable to inhabit their own house for 1-2 months This intervention type was not utilized, will be covered by INT 13. Since 1.5 month after disaster Gov. is moving into early recovery phase. |
| INT 04 | Tents | Provide tents to families who are unable to build emergency shelter and are only expected to be displaced from their house for maximum 3 months. Design Life 3 months | 5000 to 20000PHP | Tents provide basic shelter but have limited capacity to be improved to provide more comfortable shelter in the long term |
| TRANSITIONAL PHASE ONLY FOR HHs THAT ARE LIVING IN HAZARD ZONES AND CAN’T BE RELOCATED WITHIN 4 MONTHS AFTER THE DISASTER HAPPENED |  |  |  |  |
| INT 05 | Bunkhouses | As per Government of Philippines specification |  | Sphere Guidelines If no other solution can be identified bunkhouses will be constructed. |
| INT 06 | Progressive core shelter for transitional phase | For vulnerable families with either totally damaged houses or certified as beyond repair assistance to be provided is transitional shelter TS, either home based, community based or evacuation centre. TS designs should be based on local materials and designed to allow owners to enhance, extend and relocate if required. Cash or vouchers may be more practical as part of the response following market analysis Progressive solution, shelter built on a temporary site but must be constructed in such a way that it can be moved once the permanent relocation area is available. | 33,00000 to 55,0000 | Philippines Sphere Guidelines, environmental guidelines – responsible use of natural materials, market analysis, WASH & Educational support, According to minimum standards as developed by the shelter cluster. |
| INT 07 | Hosted Family Support | Identify why hosted cannot return to PoO. Vulnerable families and those traumatised by the event may be better served by living in a host family environment. |  | This intervention type is currently not being implemented by any of the Agencies |
| INT 08 | Rental Assistance | Families identified as vulnerable and are unable to stay home based, community based or evacuation centres and need shelter solution for 1-3 months whilst repairing shelter | TBC following revision of damage numbers | Analyse market available, limit rental amount to prevent adverse effect on current market. This intervention type is currently not being implemented by any of the Agencies. Not common in rural areas, lack of available houses optional for urban areas, organization on the ground are not willing to provide rental sub |
| INT 09 | Alternative transitional sites | Alternative transitional sites in existing structures private or public using privacy partitions including wash facilities | TBD | Depending on availability of existing structures. |
| RECOVERY SUPPORT |  |  |  |  |
| INT 10 | NFI’s | Based on needs assessment, identify NFI’s such as blankets, mosquito nets, kitchen sets, hygiene kits or cash/voucher | TWIG to provide guidance | Was done under emergency phase, will not be repeated during recovery phase. |
| INT 11 | Technical Guidance | Provide tradespersons in barangays to provide technical guidance for - Improving emergency shelter - undertaking repairs to damaged houses - construction of progressive core shelter - demolishing and debris management Promote the Build Back Safer principle |  | Different TWiGs will be held and IEC materials developed. Tesda is undertaking construction trainings on municipality level. |
| INT 12 | Recovery Tool Kit | Provide communities with basic tools to help demolish, salvage and start reconstruction. Support for families to demolition their destroyed houses and clean their sites. |  | - Tools identified by TWIG as appropriate for demolition, salvage and reconstruction. Can be used afterwards as tools for livelihoods. Kits to be communal tools, with consumables to be renew by agencies if community unable to do so. - IEC for demolishing and debris management is developed and shared |
| INT 13 | House repair - Timber | Identify basic materials required to repair timber framed houses to allow families to return to Place of Origin, PoO Cash or vouchers may be more practical as part of the response following market analysis | 10,000 PHP to 15,000 PHP | - A TWIG and training will be held in cooperation with ‘Build change” and will also develop the IEC for the housing repair. - NHA is giving 10,000PHP to partially damaged houses, during TWIG the real cost for housing repair will be identified. |
| INT 14 | House repair - Masonry | Identify basic materials required to repair concrete/masonry houses to allow families to return to Place of Origin, PoO. Cash or vouchers may be more practical as part of the response following market analysis | TBD | - A TWIG and training will be held in cooperation with ‘Build change” and will also develop the IEC for the housing repair. - NHA is giving 10,000PHP to partially damaged houses, during TWIG the real cost for housing repair will be identified. - No Agencies are currently undertaking the repair of concrete houses |
| INT 15 | Host Family Support | Appeal for community support to identify families willing to host displaced populations. Support can be provided in terms of: - building materials to enhance existing shelter space - NFI’s - Cash or vouchers to supplement additional costs - WASH assistance to verify capacity of existing facilities Proposed Time frame 2-3 Months maximum | 20000PHP | - Provides stable environment for persons affected by the trauma of the disaster. Supplementary items may be required to enable persons to be comfortably hosted for a period of time Worked out in coordination with other clusters. |
| INT 16 | Progressive core house /Permanent Dwelling | All houses constructed will be progressive core houses of minimum 18m2 as per shelter cluster minimum standards. All houses will be upgradable. | 33,000 to 70,000 PHP | - Habit for Humanity is building 70,000 PHP core houses if plastered these houses will be classified as permanent dwellings |

Programme

| Shelter activities time line | Below is the proposed activity programme for the emergency and early recovery responses for shelter. This is indicative only. However, it’s understood DSWD have requested the emergency distributions to be complete by 15th Nov. However, due to the delay caused by Typhoon Yolanda the emergency distribution will be extended until mid-December. As from December all Agencies should have prepared their early recovery plans. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase | Activities | 15-Oct | 21-Oct | 28-Oct | 04-Nov | 11-Nov | 18-Nov | 25-Nov | 02-Dec | 09-Dec | 16-Dec | 23-Dec | 30-Dec | 06-Jan |
|  | Season |  |  |  | Typhoon Yolanda |  |  |  |  |  |  |  |  |  |
|  | Flash appeal |  |  |  |  |  |  |  |  |  |  | Rev. |  |  |
| EMERGENCY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INT 01 | Outside standards tarps |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INT 02 | Sphere standards tarps |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INT 03 | Shelter kit |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INT 04 | Tents |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Filling gaps |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TRANSITIONAL | Solutions as per INT |  |  |  |  |  |  |  |  | Until relocation areas are identified and construction finalized |  |  |  |  |
| EARLY RECOVERY | DAFAC card by DSWD |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Structural damage assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INT 10 | NFI’s |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INT 11 | Technical Guidance |  |  |  |  |  |  |  |  |  | Until end of programs |  |  |  |
| INT 12 | Recovery Tool Kit |  |  |  |  |  |  |  |  |  | 12 months |  |  |  |
| INT 13 | House repair - Timber |  |  |  |  |  |  |  |  |  | 12 months |  |  |  |
| INT 14 | House repair - Masonry |  |  |  |  |  |  |  |  |  | 12 months |  |  |  |
| INT 15 | Host Family Support |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INT 16 | Progressive core house /Permanent Dwelling |  |  |  |  |  |  |  |  |  | Up to 2 years |  |  |  |

Inter cluster coordination

| Inter cluster |  | Below are listed the relevant clusters and how they interact with the shelter cluster. |  |  |
| --- | --- | --- | --- | --- |
| Cluster | Lead-Agency | Co-Lead | NGAs | Comments |
| Coordination | Information & Coordination Mgt Secreteriat | OCHA | DILG | - Siterps, shelter advocacy, FA, SRP, inter cluster coordination, advocacy with Government. |
| CCCM | OPSWD | IOM/UNHCR | DSWD | - Support NFI’s and shelter needs in evacuation centers – formal and informal. - Support Displaced Tracking Matrix, beneficiary lists and data on vulnerable groups |
| WASH | PHO | UNICEF | DOH | - Ensure individual shelter sites have WASH facilities. |
| Early Recovery | PPDO | UNDP | NEDA | - Materials from damaged or destroyed houses are required to support the building of emergency and maybe transitional shelters. Promote recycling materials from the damaged or destroyed houses. - Many houses are damaged beyond repair and will need to be demolished. A strategy will have to be defined how these and the destroyed houses can be demolished, materials salvaged and or recycled to maximize the advantage to the beneficiary. - House damage structural assessments to confirm what’s repairable and what needed to be demolished. - There is a requirement for hazard mapping to be complete by MGB. This will probably result in a number of relocations sites. - Support physical, social and commercial development of relocation sites. - Support enforcement of housing, building codes relevant to the area. |
| Logistics | PGSO | WFP |  | - Transportation, storage, supply chain, customs clearance, security of movement and humanitarian access. - Support agencies and donors in their efforts to bring stock to the affected areas and distribute. |
| Education | GO-EDC | UNICEF/St C | Dep. ED | - Some school playgrounds are being used as camps. - Advocate for camps to be closed and families to return to their place of origin as soon as possible - subject to hazard mapping exercise. |
| Telecom | TARSIER 117 | WFP | OCD | - NA |
| Food security | OPSWD | WFP/FAO | NFA | - Food distribution points maybe used as a reason for families to remain displaced. - Advocate for camps to be closed and families to return to their place of origin as soon as possible - subject to hazard mapping exercise. |
| Health | PHO | WHO | DOH | - Families may have to remain under tarpaulins or in tents for several months which include the rainy season. This will have an impact on health. - Promote the reduction of incidence of disease by advocating for the provision of appropriate shelter and NFI and shelter guidance. - Monitor with the Health cluster and identify impact/trends and take action to mitigate. |
| Nutrition | OPA | UNICEF | NNC | - Information on vulnerable groups through therapeutic feeding data |
| Protection | OPSWD | UNICEF/UNHCR | PNP | - Loss of documentation, HLP, GBV, female and child headed households, elderly and disabled, vulnerability data, relocations and evictions. |
| Livelihood | OPA | ILO | TESDA | - Emergency employment activities through cash for work - Skills training and capacity development |
| Infra | PEO |  | DPWH | - Only on Gov. level |
| Environmental | GO-BEMO |  | DENR | - Only on Gov. level |

Lead agencies by Municipalities

| Lead agencies |  | This table illustrates which Agencies has been working where during the emergency phase. Lead agencies are identified for each municipality. (are in bold and red) The function of the Municipality lead agency is to provide some field level coordination and feed back to the cluster on issues, needs, gaps, etc. Each of the 17 priority Municipalities identified by DSWD will have a lead agency. The lead agencies for the early recovery phase will be identified once all recovery plans are finalized. |  |
| --- | --- | --- | --- |
| # | Priority Municipality |  | Agency |
| 1 | Antequera |  | DSWD, PRC, CRS, PLAN INT, WORLD VISION, CARITAS |
| 2 | Balilihan |  | PRC, CARITAS |
| 3 | Buenavista |  | DSWD, PRC, CARITAS |
| 4 | Calape |  | DSWD, PRC, PLAN INT, JICA |
| 5 | Carmen |  | DSWD, CARITAS |
| 6 | Catigbian |  | DSWD, PRC, PLAN INT, WORLD VISION, CARITAS |
| 7 | Clarin |  | DSWD, PRC, |
| 8 | Corella |  | DSWD |
| 9 | Cortes |  | DSWD, CARITAS |
| 10 | Danao |  | PRC, Caritas |
| 11 | Inabanga |  | DSWD, PRC, CRS, CARITAS |
| 12 | Loon |  | DSWD, PRC, PLAN INT, SHELTERBOX, DAI/BMFI, CARITAS |
| 13 | Maribojoc |  | DSWD, PRC, PLAN INT, SHELTERBOX, CARITAS |
| 14 | Sagbayan |  | DSWD, PRC, CRS, CARITAS,JICA |
| 15 | San Isidro |  | DSWD, PRC, CARITAS |
| 16 | Sevilla |  | PRC |
| 17 | Tubigon |  | DSWD, PRC, PLAN INT, SHELTERBOX, GOOD NEIGHBORS, JICA |
| # | Balance Municipality |  | Agency |
| 1 | Baclayon |  | IOM |
| 2 | Batuan |  | DSWD, IOM |
| 3 | Dagohoy |  | IOM |
| 4 | Dauis |  | IOM |
| 5 | Getafe |  | IOM, CARITAS |
| 6 | Guindulman |  |  |
| 7 | Loay |  | IOM |
| 8 | Loboc |  | IOM |
| 9 | San Miguel |  | DSWD |
| 10 | Sierra Bullones |  | DSWD, IOM |
| 11 | Sikatuna |  | DSWD |
| 12 | Tagbilaran City |  | DSWD ,CARITAS, IOM |

Response structures 
The national and provincial government structures and the humanitarian community where they are related to the shelter response are recorded below:

Resource mobilisation

The following are appeals which have been launched and include a shelter component:

| Mechanism | Appealed for shelter | Current coverage | Notes |
| --- | --- | --- | --- |
| Flash | $9.7 million Funding requested |  | Total for all sectors US$46.8 million, funding requested |
| CERF |  | $1.4m |  |
| Agencies |  |  |  |
| IFRC |  |  |  |

Annex material:  (to be included in “Detailed Shelter Strategy”)

- Guiding Principles and Policies

- Gender, disability, age, GBV, HIV/AIDS Guidance

- Environment Guidance

- Landmines

- HLP checklist

Annex 1: Guiding Principles and Policies

Refer to the UN Guiding Principles on Internal Displacement: The provision of temporary housing is to be guided by relevant international standards particularly the UN Guiding Principles on Internal Displacement.  These principles are integrated into these suggestions and are summarised below.  It is the responsibility of the aid community to support Government in meeting its obligations to the affected population.  Further information is available from the UN, including practical steps to assist with implementation.

Annex 2 :  House definitions  Annex 3: Cross Cutting issues

The commitments to older people – by Help age

The UN Principles for Older Persons (UN General Assembly resolution 46/91) calls for ensuring the independence, participation, care, self-fulfilment and dignity of older people. It specifically states that older people should have access to basic services including shelter.

The background

Shelter is a basic human right for people of all ages, but for older people, the sense of security and comfort that a home provides is particularly important. Losing their home in a disaster or conflict therefore has a profound psychological impact, particularly on the “oldest old” (people above 80 years). Suitable housing for older people is crucial to ensure a dignified life. When managing a shelter programme, it is essential to identify and address the needs of vulnerable older people and engage them in decision-making, in order for age-appropriate decisions to be taken.

Key action points to address

- Sensitise and provide training to your team on the importance of collecting data on older people, disaggregated by sex and age.

- Make your assessment tools age-friendly by including questions on the needs and capacities of older people.

- Conduct focus group discussions and individual interviews with both older men and women in various age groups.

- Ensure that your assessments include the most vulnerable older people – isolated older people, those with health problems, those aged 80 and above and skipped generation households

- (Where the middle generation is absent). See Action point 3.

- Identify what already works around accessibility, inclusion and participation of older people and what needs improving.

- Adapt your communication style to suit older people.

- Provide opportunities for older people to hold positions of responsibility and be represented on community-based committees.

- Increase opportunities for individual choice and problem solving by involving older people and their families and communities in issues such as land rights and construction.

- Ensure that older people are engaged in complaints mechanisms and project monitoring procedures.

- Target older people, especially the most vulnerable, in the process of selecting those to receive shelter assistance and in all stages of a humanitarian response.

- Ensure that isolated or housebound older people are aware of the selection process and are able to participate in it.

- Assess, through discussion with older people and their families and community, the support systems that are available to them and how these have been affected by the emergency.

- Take steps to ensure that the community acknowledges the risks and vulnerabilities of older members and that the community is supported to address these.

- Adhere to national and international standards for durable and accessible shelter construction.

- Ensure a culturally acceptable and age-friendly layout and design.

- Incorporate features that allow older people to enter and exit their shelters easily.

- Ensure that the shelter is not too far from water sources, healthcare centres, cyclone shelters or community centres and other facilities; that older people do not feel isolated or unsafe; and that they can evacuate their shelter easily.

- Ensure that non-slip floors and handrails are installed as appropriate; and that shelters are weather-proofed and winterisation kits distributed in good time.

- Recognise that people become less mobile with age: provide access to water sources and raised beds, adequate lighting and ventilation; and opportunities to adapt the shelter to meet future needs, including home-based livelihood activities.

- Ensure that older people’s issues and data are included on the agenda of shelter cluster meetings.

- Put in place a system of monitoring and evaluation among partners and local government, so that there is a continuous flow of feedback and direction on ageing issues, and disseminate good practice and lessons learned through relevant channels, including the shelter cluster.

- Coordinate and promote partnership with other clusters (Watsan, Health, Livelihood, Protection, Camp Coordination and Camp Management) to link older people to different services.

- Link your programmes to those addressing other vulnerable groups such as children, women and people with disabilities. There are overlaps between these groups – for example, many older people care for children or have disabilities.

Action point 1: Understand the needs and capacities of older people

Action point 2: Ensure that older people participate and are represented

Action point 3: Target vulnerable older people

Action point 4: Incorporate age-friendly features in both household and community shelters

Action point 5: Promote coordination, cooperation and sharing
 The commitments to Protection – source UNFPA

MOU with ILO

Livelihood Cluster’s approach to livelihood recovery and development

Livelihood interventions in disaster-affected areas/humanitarian situations generate immediate employment and help identify other livelihood options for affected households. Responses within the livelihoods cluster will utilize a local resource-based approach where affected communities will be involved.  It is aligned with the principles of Decent Work and focused on short-term community activities that include but are not limited to infrastructure repair and restoration that will transition to longer-term employment and better access to other livelihood options. There is a need to support and develop traditional forms of livelihood that are often destroyed in such situations, but there is also a need to develop and improve local economies and livelihood opportunities. The members of the Livelihood cluster agree to practice and advocate the observance of decent work principles in undertaking activities, including the following:

- debris clearing through cash-for-work (CfW), or other such activities which are needed, inclusive and quick to roll-out to provide immediate income to households;

- provision of onsite training to beneficiary workers during repair, reconstruction and rehabilitation of infrastructure to address expected demand for skilled workers;

- organization, capacity building and registration of workers with appropriate government agencies to acquire the legal personality to be engaged as local community contractors for the repair and rehabilitation of community assets and facilities and other emergency employment activities;

- engagement of community contractors to demonstrate capacity to address labor market demands emanating from new investment priorities by public and private development entities.

Partner organizations including local government units and the communities will take an active role in the entire process. This approach has successfully been used in Typhoon Sendong-affected areas in Cagayan de Oro and Iligan with four community contractors engaged to provide construction services for the repair and restoration of government elementary and high school facilities.

Implementing CfW for short-term employment

Cash-for-work for one member of affected households should run for approximately 15 days (dependent on the nature and situation of the disaster). The following requirements comply with international and national standards to decent work and should be adopted by all actors carrying out CfW, or similar activities:

- 75% of the regional minimum wage, to be confirmed  with the Department of Labor and Employment (DOLE) and the Department for Social Welfare and Development (DSWD) at the national level cluster, will be adopted at local level (see DSWD Administrative Order 15, p2). Similarly, this  uniform wage rate will be adopted for cash-for-work projects by all implementing agencies.

- Occupational safety and health standards will be strictly observed. Workers for debris clearing, dredging, de-clogging and other construction related workwill be required to wear appropriate protective gears such as hand gloves, boots or working footwears, masks and  hats. Other CfW work will have to identify approriate Personal Protective Equipment that will ensure safety of its workers.

- Selection criteria will include, among others, households headed by women, families with pregnant and lactating women, family members with disability, or families with multiple vulnerabilities as defined by the DSWD displacement form. Equal opportunities for women and men will be promoted during the livelihood assistance orientations; taking into consideration different skill sets, needs, vulnerabilities and responsibilities of affected women and men. This will also take into account the best interests of children and ensure the prohibition of the Worst forms of Child Labour. Noone aged under 16 years of age will be selected for such work and that those aged 16-18 will only be selected in exceptional circumstances, where such work will not interfere with their studies and will not be physically strenuous or hazardous.

- A registered nurse, to be permanently stationed at the project site, will be available to provide first aid and other services for the workers.  The standard will be one  nurse to an average of 150 workers.

- Work conditions will be monitored regularly to ensure that participants are safe from exploitation, sexual abuse and harassment. All implementing partners shall ensure that all its employees and personnel comply with the provisions of ST/SGB/2003/13 entitled “Special Measures for Protection from Sexual Exploitation and Sexual Abuse”.

- Social protection benefits such as one-year accident insurance or six-month PhilHealth coverage will be extended to workers.

The members of the Livelihood Cluster agree on the following in undertaking responses during humanitarian or disaster situations.

- Adoption of minimum standards for cash-for-work projects related with adoption of a uniform local daily wage rate, occupational safety and health, and social protection (see above).

- Close coordination among organizations carrying out cash-for-work and livelihood related projects and the local coordinating structures

Proper coordination is crucial to ensure optimal use of limited resources, avoiding duplication of coverage areas and worker beneficiaries. Attendance by all actors involved in livelihoods or CfW activities at the Livelihoods Cluster, both nationally and regionally/locally, or at the very least alerting the cluster of intended activities (based on the 3W matrix) is strongly recommended.

- Need for barangay level key information from all affected areas

Key information, such as skills inventories among affected residents, current conditions of community infrastructure and/or presence of community-based organizations will guide development and application of appropriate interventions in prioritized project sites that will benefit targeted households and the community as a whole.

- Utilization and recovery of debris and maximization of local resources and supply chains

Support to Women-Friendly Space (WFS) Facilitators and Child Minding

Republic Act no. 9231: An act providing for the elimination of the worst forms of child labor and affording stronger protection for the working child, amending for this purpose Republic act no. 7610 as amended, otherwise known as the “Special protection of children against child abuse, exploitation and discrimination act.”

Available at http://daccess-dds-ny.un.org/doc/UNDOC/GEN/N03/550/40/PDF/N0355040.pdf?OpenElement