Emergency Shelter

$10,890,997 Funding requirement

Contact Information: Patrick Elliott (patrick.elliott@ifrc.org; +63-9084011218)

At the moment over 53,000 houses are reported as severely damaged or destroyed. Families live in the open, under cramped, hastily built makeshift structures from thin used tarps and other salvaged materials that provide inadequate shelter. Shelter materials are scarce as businesses remain closed due to damage.

The shelter cluster deployed the REACH  assessment team in support of the government to determine the specific shelter needs of men and women of different ages and with different vulnerabilities . The cluster will focus on immediate  life- saving shelter interventions.  35,000 families will be provided with plastic sheeting or tents, some tools and fixings and basic NFI’s.  This should provide adequate shelter through the imminent rainy season so at least 3 months. Longer term solutions will also be required. To complement  the government’s contribution of 5000PHP for a damaged  and 10,000 PHP for a destroyed house, the cluster also targets 5000 vulnerable families for transitional shelter. Damage assessment for housing safety, technical assistance and training to women and men will be provided in implementing safer earthquake resistant building practices.

| Name | INTERNATIONAL ORGANIZATION FOR MIGRATION |  |
| --- | --- | --- |
| Headquarters | Geneva (Switzerland) |  |
| Website | www.iom.int |  |
| HQ Contact | Carol San Miguel, Donor Relations Division, drd@iom.int |  |
| Philippines Contact | Marco Boasso, Chief of Mission, mboasso@iom.int |  |
| Clusters / Sectors | CCCM/NFI/Shelter |  |
| Objective | IOM, as global cluster lead in the IASC Camp Coordination and Camp Management (CCCM) for internally displaced persons (IDPs), promotes durable solutions for IDP communities and local authorities within a migration crisis operations framework. Our approach integrates gender and rights-based orientation, climate-smart risk reduction objectives including migration as adaptation strategy. In the Philippines, IOM is the co-lead agency for emergency shelter. |  |
| Presence, staff |  |  |
| Name |  |  |
| Headquarters | World Vision Philippines |  |
| Website | www.worldvision.org.ph |  |
| HQ Contact |  |  |
| Philippines Contact | Ernie Macabenta; Ernie_Macabenta@wvi.org- Associate Director for Operations, Visayas |  |
| Clusters / Sectors | Shelter and NFIs |  |
| Objective | The target number of families for the entire emergency response is 11,000 families. For this proposal, World Vision proposes a total of 4,239 families for the provision of non-food items and tents in the Municipality of Sagbayan, Danao and San Isidro. Target families will include those families whose: - House is damaged beyond repair/not livable/structural design is compromised - living without tents or adequate shelter to protect them from rains and wind those still living without tents or adequate shelter Ways will be explored so that affected families are also able to contribute to identifying criteria for selection of beneficiaries. |  |
| Presence, staff | Florelyn “Bebeth” Tiu: +639178179911: bebeth_tiu@wvi.org World Vision Development Foundation, Inc. 389 Quezon Avenue, 1104 Quezon City, Philippines |  |

| Name | Habitat for Humanity International |  |
| --- | --- | --- |
| Headquarters | Habitat for Humanity Philippines |  |
| Website | www.habitat.org.ph |  |
| HQ Contact | Charlie Ayco; charlie.ayco@habitat.org.ph (independent) |  |
| Philippines Contact | Charlie Ayco; charlie.ayco@habitat.org.ph; +62-905-2547645 |  |
| Clusters / Sectors | Shelter |  |
| Objective | The project objective is to determine the structural integrity and safety status of affected houses. Develop the local capacity to provide emergency shelters at scale, providing shelter for 10,000 families. |  |
| Presence, staff | Habitat for Humanity Philippines, 3f Paseo 111 Building, Paseo de Roxas corner Legazpi Streets. Makati City, Metro Manila Philippines: Tel. (+632) 846-2177 |  |
| Name |  |  |
| Headquarters | ADRA Philippines HQ - Adventist Development and Relief Agency Philippines (ADRA) Foundation Inc |  |
| Website | www.adra.ph |  |
| HQ Contact | Cindy Bankhead the Program/Country Director- +63 917 586 7106: cindy@adra.ph: |  |
| Philippines Contact | Jelome Manalu & Moises Musico |  |
| Clusters / Sectors | Shelter and NFIs |  |
| Objective | To provide immediate, effective and efficient relief assistance to meet shelter needs of 5,300 families /approx. 26,500 people in Bohol at the end of the emergency response project. |  |
| Presence, staff | PO Box 25 JP Rizal, Sabutan; Silang, Cavite Philippines 4118 |  |
| Name | Catholic Relief Services |  |
| Headquarters | Baltimore (USA) |  |
| Website | www.crs.org |  |
| HQ Contact | Jennifer Holst, Public Donor Liaison, Jennifer.holst@crs.org, +1-410-9517394 |  |
| Philippines Contact | Joseph Curry, Country Representative, josephcurry@crs.org, +63-917544-4277 |  |
| Clusters / Sectors | WASH & Shelter |  |
| Objective | CRS approaches its emergency response programming through a framework of saving lives, supporting livelihoods and strengthening civil society. From the very beginning of a disaster, CRS works with the affected community with the ultimate goal of moving from relief to reconstruction. CRS adheres to international standards to the greatest extent possible in all of its emergency work to ensure that disaster-affected populations are at least able to meet their basic right to live a life with dignity. CRS works directly with affected communities and local partners to help restore and strengthen their pre-disaster capacities. |  |
| Presence, staff | Country Office in Manila, field offices in Davao, Tagum, Cateel and recently established in Tagbilaran. Total staff of 98 national staff and 4 international staff. |  |
| Name | Shelter Box |  |
| Headquarters | Shelter Box UK |  |
| Website | www.shelterbox..org / shelterboxphilippines@gmail.com |  |
| HQ Contact | Shelter Box; International, Unit 1A, Water- Ma-Trout, Helston City, Cornwall, TR13 OLW, UK |  |
| Philippines Contact | Sonny Ongkiko - Shelter Box Response Manager - Philippines Disaster Relief joseongkiko@yahoo.com: +0917 3232361 |  |
| Clusters / Sectors | Shelter tents and NFIs |  |
| Objective | 1040 emergency tent and NFIs (500) |  |
| Presence, staff | Sonny Ongkiko |  |