| DOHUK IDP Shelter/NFI Coordination Meeting-DMC Conference Room |  |
| --- | --- |
| #### Meeting Subject: | IDP DOHUK Shelter/NFI Coordination Meeting |
| #### Time & place of meeting: | 01/December/ 2014, 10.00, DMC Conference Room |
| Meeting Chaired by: | UNHCR: Sophia Glazunova |
| Minutes Prepared by: | UNHCR: Abdifatah Gure |
| #### Present | UNHCR, IFRC, PWJ, UNFPA, FRC, MEDAIR, UNOCHA, IOM, REACH, GIZ, GRC, LWF, CAPNI, ZOA, Tear fund, NRC, IRC, Save the children, IRC, NRC, Samiritans Purse, MSF, Operations Mercy, UNAMI, WVI, ASB, Harikar, |
| #### Absences: |  |
| #### Additional distribution: |  |

Objectives & Agenda

- Updates from the Immediate Response Plan meeting held on Sunday 23rd Nov.:

- NFI/Winterization updates from agencies

- Shelter

- A.O.B

1)         Updates from the Immediate Response Plan meeting held on Sunday 23rd Nov.:

Key Highlights:

- The IPR meeting focused on areas such as;

- Shelter and NFIs

- Health

- WASH

- Education (Protection was not planned within IPR)

- 82,000 IDPs (14,712 families) were accommodated in camps as of 15 November 2014.

- 2,764 tents were provided by cluster agencies to temporary informal settlements

- 160,000 IDPs will be accommodated in camps currently in place or under construction by the end of the year.  Majority of the camps are expected to be fully populated by 31 December 2014.

- Preparations for non-camp shelter interventions have commenced targeting 4,500 families/27,000 IDP individuals, living in unfinished or abandoned buildings;

- In addition, 6,000 sealing off kits are available for interventions in skeleton and unfinished buildings (further information will be provided upon if necessary

2)	NFI/Winterization updates from agencies

UNHCR:

- Distribution of phase II Winterization is ongoing for both camps and Non camps

- The Phase II comprise the distribution of Heating stoves and Kerosene Jerry cans for Non- camps and

- Distribution of Insulation kits for UNHCR camps and tented settlements

PWJ:

- Planning to distribute winter clothes for the Non-camp IDPS

- 6,000 winter cloths expected by Mid-December.

- Electricity is now connected to all tents in Bersive2

LWF:

- Planning to distribute Kitchen sets, Hygiene kits and Individual clothing’s in Amedia district.

- The target is 200 Families.

- LWF will coordinate with NRC who is also working in Amedia District.

REACH:

- Carried out distribution of Kerosene and kerosene jerry cans for 332 Families in Sheekan.

- 40 liters of kerosene per family.

CAPNI:

- Water heaters connection in Kanimase Christian villages

- 102 Families are also targeted for the same in Barmane and Sersink

- 320 Kerosene heaters are also planned for distribution.

French Red Cross:

- Finalizing voucher for cloths for sharia villages.

- 1, 400 Families is targeted by this program

UNFPA:

- Started distribution of cloths and Hygiene kits in Akre.

- Plans to continue the distributions in Akre, Zakho and Amedia town.

- 1600 dignity kits and 4,200 Winterization female cloths is the general target distribution.

Tear Fund:

- 500 Winterization and sealing off kits for Batel and Semel districts.

- Cash assistance program is ongoing

IRC:

- Plan for 3000 winterization packages for Khanke and semel

- unconditional cash for 1600 families in Sheekhan district

Save the Children:

- Plans to distribute Hygiene kits for all sharia camp families

- Planning to do the distribution of Kerosene for Amedi Centre in Amedi district.

Samaritan Purse

- Plans to do Jacket distribution within Dohuk town

- Expecting shipment of 300,000 shoes for distribution. Initially camps will be targeted, then non-camp population. Assistance for distribution in governmental camps is needed.

World Vision:

- 750 Families reached with Winterization Kits

- Plans to do Cash assistance for 1050 families within Dohuk.

3)              Shelter Updates:

- Daudia camp  (UNHABITAT/UNDP/IOM) – 60% completed

- Relocation to Karbato is ongoing with 925 Families as 30th Nov

- Bajed Kandala- 2136 Families

- Bersive1- 1772 Families

- Bersive2 – 670 Families

- UNHCR IS Planning for Crush stone/gravelling in Garmawa and Khanke camps.

- A total 16,889 Families are currently living in Camps in Dohuk.

- Shelter working group shall meet on 04.12.2014 to ensure coordination on shelter Winterization response program I.e. sealing off kits and upgrade on unfinished building

4.             A.O.B

Fuel:

- Government started distribution of kerosene for the IDPS. 100 liters of kerosene per family. Total allocation from the central Iraqi government is 5,700,000 liters, i.e. 57,000 IDP families have to be covered with 100 liters of kerosene.

- UNHCR and IOM are also planning to do kerosene distribution. UNHCR will distribute 200litres of kerosene per family, altogether 18,000 families. Empty barrels will be provided accordingly. The distribution will target the camps population.

Note// Action point:

- UNFPA to discuss further with management on commitment of a focal person for cloths distribution on behalf of the cluster.

- Cash Informal working group meeting is scheduled for Monday 4PM at OCHA Office

- Non-Camp Shelter TWG meeting is scheduled on Thursday, December 04, 2014

- UNHCR to share DIM data with CAPNI.