

Emergency Shelter Cluster Minutes

Koshi river floods, Nepal
Coordination Meeting 24th December 2008.

Venue: CDO Office, Sunsari District

Agenda item # 1: Introduction of participants


	Presentation
	In attendance were 8 participants from different organizations.

	 Durga Pd Bhandari (CDO),Tara Devi Gurung (NRCS/ESC), Rashmi Manandhar (HFHI-Nepal/ESC), Ambar Bhandari (NRCS), Tom Acharya (President, NRCS Sunsari District), Rajesh Shrestha (UNICEF), Mustak Ansari (President, Nahar Chowk CMC), Israfil Ansari (Member, Nahar Chowk CMC)


Agenda item # 3: Review of Previous Minutes
	
	

	There was no discussion on this topic.


Agenda item # 3: Gap Filling

	Discussion
	ESC team highlighted  gaps in lighting

	Though DUDBC is installing electric light in some camps (Lauki Custom Camps, Rotary Shelter Boxes, Mahendra Highway Camp C and Madhuvan Cattle Shed Camp), there is still gap in lights for other Camps except in Jhumka. 


	Action Items
	Person Responsible
	Deadline

	Agencies to reflect on program activities and report if they are able to fill gaps.

	All 
	6th January 2009



Agenda item # 5: Update from ESC Members

	Discussion
	All ESC member organizations are requested to share any issues and plans 

	CDO confirmed the following:

· Electric light will be provided to every camp through DUDBC.
· DDRC is going to distribute 800Nrs for the HH which has maximum 3 members, 1000Nrs for 3-5 members and 1500Nrs for the HH which has more than 5 members for the month of Mangsir.
· DUDBC will distribute wages for 4 people per HH to the IDPs who have built their huts by themselves in all the camps of Nahar Chowk, Kumiyahi Judgunj, Pashchim Kushaha Dam. This will be done together with the DDRC money distribution.
· The IDPs having pink slip only will get assistance from now onwards.

NRCS informed that:
· Action Aid/NRCS has distributed money for 4 bamboos (280Nrs)/ HH in all the Camps of Kumiyahi, Judgunj, Rayentole, Urautole, Partitole and Mahendra Highway Camp C.
· Action Aid/NRCS will not distribute money to the Nahar Chowk Camp as they have already got bamboos from NRCS but they will get wages from DUDBC. This was confirmed by CDO.

	
	
	


Agenda item # 4: Shelter and camps
	
	

	· Return Package will start when the money is issued from the Government. CDO believes 100% people will return then. More discussion will be done when situation arises otherwise.


	Action Items
	Person Responsible
	Deadline

	
	
	


Agenda item # 5: AOB

	Discussion
	

	· UNICEF raised the issue of security in the camps.
· Some Indian IDPs are living in Nahar Chowk Camp.

	
	
	

	
	
	


	Next meeting
	Wednesday 7th January 2008, ~11:00 am at DDC Meeting Hall before the General Coordination meeting.



[image: image1]
[image: image2.jpg]EMERGENCY SHELTER CLUSTER SUNSARI

Mesting Attendance List
Date:3] 122008
‘Agency Name. Name Position Thobile umber Ermal aadress Sipatire
NRCSESC [Tar Do Gurung _|ESC P Offcer | oe00e7541_esc i sun@grai com. 5
= [Ambar Bhardari__[Rebel Oficer SaeiTe0]__ [shandaran@yacocon
774 —NepaVESC_[ashl Manandrer_[Archisc SBataE808 [nwicrwsofhgns o o
[Vogesh riwia@pion-
P Negst [Yogesh Niaua 842029408 _|rssrators com
oW HiNepal _|Ania Adkon 51010624 |hanva@gmaticom.
Sove the hidren_[Tuisi Pd Gurung 5004302015 [lourun@samcidianorg
[Sove oo chiron__[Avun Kusmar Nahalo GESa021612__[amanio@savchidien a0
[oweeem [Ciandra Jurg Rare 651104502 [ccomicc@graticon.

UNCCET Rajesh Shiesfa | WRH GOV 5502550073

NEZS [em gl Aelood] docaporoan] 9842038747
T ugta NahaT] A 10978 &
gaval| A I 4842424460

200 vg%lua‘ < v | 95LI0dG%e ﬁ,

o[sfhe -2 670 B 7o)




