Emergency Shelter Cluster Meeting Ziarat

Meeting Notes (Draft)

Venue:- District Nazims Office                          Timing:- 7:30pm                     Dated:- 15/01/2009

	Chair             DCO Ziarat
	Sohail ur Rehman

	Co Chair        ESC Information Manager
	Jan Willem Wegdam

	Participants

	Adeel Ahmed                           Islamic Relief

Aamir K Shah                          Islamic Relief

Aasiya Dilawar                        Nawee Sahar

Siddique Panizai                      Nawee Sahar

Irfan Khan                               PRCS

Gul Hassan Durrani                TWO

Naseer Shah                            UN HABITAT
	Syed Nasrullah Shah       Focal Person District                                                                                            Government

Naqeeb Kakar                 WIPRO

Qaiser Khan Kakar          WIPRO

Mehmood Haqani            Ummah Welfare Trust

M Hamayoun Kasi           ESC         

	Agenda:-

Introduction

Brief overview by ESC

Progress Sharing by organizations

Areas Allocation to Organizations 

Issues/Problems if any faced by any organization

AOB

Next Meeting

	Discussion
	Decision / Suggested Action Point

	· ESC Information Manager shared the over all progress and situation over view.

· Emergency phase will end up in the first week of February.

· BRDRS has started assessment in the areas of Ahmedoon without information & coordination to the ESC or District Government.

· ICRC has planned the distribution of additional 230 shelters among the affected population of Ahmedoon, Gogi & Tangi areas.

· Children Health & Education Fund

· Shelters allocation to Health facilities

· IDSP has provided shelters in District Pishin.

· Progress of the organizations shared 

· Beneficiary Lists to be provided by organizations to the District Government.
	· 30000 normal tents, 8800 shelters & 8000 Winterized tents provided so far.

· Early recovery & rehabilitation phase will be coordinated by UN-HABITAT & ESC will hand over the coordination task to UN-HABITAT.

· ESC has taken over the issue with BRDRS and has invited them to the ESC Meeting at Ziarat, where they will be allocated the areas as per need to the affected population.

· The issue raised by the District Government focal person in the last meeting has been taken up with ICRC and it has planned to distribute 230 additional shelters to resolve the issue with in 3 days.

· CHAEF has planned 112 shelters (yet to be confirmed).

· UN-HABITAT will provide 50 shelters to the affected health facilities and lists and location of the facilities to be provided by the Health Cluster in coordination with District Government.

· During the last ESC meeting at Quetta it came to the knowledge of ESC that 25 shelters have been installed by the IDSP in pishin.

· Satisfaction showed by the chair over the progress of the organizations

· It was once again requested to the organizations working on shelter provision to provide the beneficiary lists as to ensure the applications received from the affected population demanding for shelters are justified or not ESC was requested by the chair to support in this regard to ensure the lists provided by the organizations.


Vote of Thanks: - The DCO in the thanked all the participants and their organizations for their valuable contribution to this humanitarian cause.
Next Meeting: - As per plan (every Monday & Thursday, 7:30pm)
