DISASTER OPERATION TYPHOON SENDONG

 SHELTER CLUSTER SPECIAL MEETING
MINUTES OF THE MEETING
2nd Floor Conference Room

DSWD Field Office 10, Cagayan de Oro City

DECEMBER 31, 2011

ATTENDANCE:

ATTY. DULFIE TOBIAS- SHALIM

- DSWD CO

BING MORDENO 



- BMFI


FR. PERSEUS CABUNOC 


- MT. CARMEL


ROSEMARIE CONDE 


- DSWD FO 10


NORMA FERNANDEZ


- CSWD


NESTOR OCAMPO



- DENR PENRO


JUDY FERNANDEZ



- NHA


JASPER LLANDERAL


- IOM


REY MASTYO
   


- DSWD CO

FR. NATHAN LEWIS


- SAC CDO

            AGUSTILO OBSIOMA


- DENR


FLORENTINO MENDER


- AFP ENGRS


HILARIO ABBTUSA


- HABITAT BUIDERS


ISIDRO BORJA



- CITY GOVT


BEVERLY BRIONES


- EMP/CPDO


NILO CASTANARES


- DILG

PRELIMINARY:
The meeting started at about 9:00 o’ clock in the morning at mini – conference room of DSWD Field Office 10. The meeting was presided over by OIC Regional Director, Atty. Dulfie Tobias Shalim of DSWD Field Office 10.      
AREAS OF CONCERNS RAISED DURING THE MEETING:
	AREAS OF CONCERN
	RECOMMENDATION/REMARKS

	TRANSFER  OF THE EVACUEES TO THE RELOCATION SITE  
	Initially there were 2,587 Families ready for transfer from evacuation center to relocation site. 
It was suggested that a clear guidelines should be created in moving the evacuees from the evacuation centers.       

	DATA IN THE EVACUATION CENTER 
	The DSWD together with the CSWD and Xavier University will set down to come up with one Family Access Card and the aggregate data as to number of families to be relocated with identification of PWDs, and Children.   

	INVENTORY OF TENTS/ BUNKHOUSES AND RELOCATION SITE
	Commitment updates of tents for temporary shelter were as follows:

Calaanan:

408 – Rotary Club International/Shelter Box
904 – DSWD

Lumbia:

660 –Red Cross

12 Bunkhouses -  DSWD
Additional relocation site for temporary shelter considered were:

Carmen Church 

    20 Tents – Plan International 
Agusan 
   20 Tents – Plan International  

 

	PERMANENT SHELTER  
	P203,070,000 Funds is allocated for 2, 900 houses for Permanent Shelter at cost 70,000 per house from DSWD.   

	RESUMPTION OF CLASSES
	DepEd announced that classes will resume on January 3, 2012 as scheduled.  The classes will resume in alternative places like sport center and covered court for the conduct of class without moving the evacuees out of the school.    

	UPDATES 
	Updates on Shelter should be shared through email to the members of the Shelter Cluster 

	MEETING SCHEDULE
	RDRRMC will meet on January 3, 2012 at 9:00 o’ clock in the morning and Shelter Cluster will meet on January 3, 2012 at 3:00 o’ clock in the afternoon. 


There being no other matter to be discussed the meeting adjourned at111:30 in the morning. 

Prepared by:

DEOCELYN G. SABUCDALAO

                  Admin Clerk 

Approved by:

  
  Atty. DULFIE TOBIAS-SHALIM 

                      OIC Regional Director 


PAGE  
2

