DISASTER OPERATION TYPHOON SENDONG

ILIGAN CITY

SHELTER CLUSTER MEETING

MINUTES OF THE MEETING

Crystal Inn, Iligan City

March 7, 2012

ATTENDANCE:

Atty. Araceli F. Solamillo		-DSWD FO10

Coun.Bong Abragan			- LGU

Dir. Grace Saniel			- HUDCC

Genenso G. Abellaneser		- NHA -10

Glo Lapina				- UNICEF/Educ. Cluster

Armien Alorro			- SP-Siao

Wang Loreto				- UNICEF/Educ. Cluster

Reynaldo Roque			- CMO-HRO

Domi A. Restor			- GK

Evelyn Madrio			- DSWD FO10

Elsie N. Sabuero			- SMMI

Lee Michael Capangpangan		- SMMI

Aida R. Abarquez			- SMMI

Corazon B. Derro			- ECOWEB

Dandy Sayana			- ECOWEB

Mustafa Deron			- DPWH

Maminta D. Papaladum		- DENR

Grace Joy O. Saquilabon		- CSWDO

Reynato S. Cano			- IFRC

Kate Dani				- Wash Cluster

Peregrina Lamayo			- CSWD

Ben Aspera				- IOM

Jerry Requillo				- Save the Children

Johurien Pagarighu			- LGU

Jocelyn P. Maguyans			- CSWD

Kasnif Siddiqi			- OCHA

Noriwina D. Eclarinal		- PRC

Nur-aian R. Caridad			- Red Cross

Frances La Victoria			- PRC

Cesar Y. Yamuta			- CAD Office

Maria Gemma Dalena		- UNDP

Camilla Reyes Pante			- Handicap Int’l

Alyassar Sulog			- Handicap Int’l

Rosemarie P. Conde			- DSWD FO10

Evelyn Madrio 			- DSWD FO10

Deocelyn G. Sabucdalao                   - DSWD FO10

PRELIMINARY:

The meeting started with an invocation by Evelyn Madrio of DSWD FO10about 9:30 in the morning at DSWD Operation Center, Isabel Village, Pala-o, Iligan City.The meeting was presided by RD Araceli F. Solamillo of DSWD Field Office 10.

MEETING PROPER:

- Reading of the Minutes of the Previous Meeting

- The minutes of the previous meeting held last March 2, 2012 at Crystal Inn, Iligan City was read and duly approved and seconded.

| AGENDA | RECOMMENDATION/REMARKS |
| --- | --- |
| Identification of No-build Zone | -RD Solamillo presented the Sangguniang Panglungsod Resolution on the areas declared as danger zone by the Local Government Unit of Iligan City. She emphasized on section 4, Coverage of the Prohibition. The specific areas classified and declared as danger zone were as follows: 1.) Barangay Santiago specifically Purok 2, 3, 4, 5, 6, 7, 8 and 13 which is classified by MGB as highly susceptible to flooding. 2.) Barangay Santiago particularly Puroks 1, 9, 10, 11 and 12 which according to MGB report, development should be restricted. 3.) All the Puroks in Bayug Island, Barangay Hinaplanon specifically Puroks 1, 2, 4, 5, 6, 7, 8 and 9 which is classified by the MGB as highly susceptible to flooding. 4.) Four (4) Puroks adjacent in Brgy. Sta. Filomena particularly Puroks Duranta A and B, Ilang-ilang and San Francisco which is adjacent to Bayug Island classified by the MGB as highly susceptible to flooding. - According to Councilor Bong Abragan that there is an amended resolution on danger zone endorsed by the Sangguniang Panglungsod last Monday, March 5, 2012 in which section 5 stated “Residential Settlement and occupancy in the “danger zones” is prohibited and unlawful andthe word unlawful was deleted.This will allow the land owner to still enjoy the privilege as the owner except habitation is prohibited.A copy will be provided next meeting. - On the areas declared as danger zone, no building permit for residential will be issued, no assistance will be given and no electricity and water will be provided for those who will insist in constructing their houses in the area. They will be constructing at their own risk. - RD Solamilloalso informed that there is a mandate on the identification of no-build zone. The law stated that 20 meters from the river bank and 5 meters from the creek considered as no-build. It was suggested to secure a copy of the law next meeting. - There are also areas were not included in the declaration of danger zone which considered high risk. - For the areas declared danger zone the people settled in the area has to be relocated. - For the areas declared as danger zone may not be permanent since on areas which mitigating devices can be installedthe law may be lifted upon compliance of the mitigating devices. |
| Map of the Area Badly Affected | - RD Solamillo also presented the Map on the areas badly affected in Iligan City. -It was suggested to have a Geohazard Map with markings on boundaries of the areas covered on the areas declared as danger zone. But a concern was raised on the availability of Geologist since there are only three (3) Geologists in DENR Region 10. The two (2) Geologists were sent to Negros Oriental and only one left in Region 10. It was then suggested to request to the Honorable Secretary of DENR for additional Geologist for Iligan City in the conduct survey and assessment of the areas. |
| Result of the Post Disaster Needs Assessment Submitted to the President | RD Solamillo presented the result of the Post Disater Needs Assessment conducted last February 18, 2012 in Pryce Plaza Hotel, Cagayan de Oro City which was submitted to President Benigno Aquino Jr. Thisis for the information of everybody. |
| Updates from the Members | REDCROSS -They will put up 1000 Core Shelter in Iligan City and the target area is in Upper Hinaplanon. -They have on-going revalidation of the identified beneficiaries. -They already distributed quotations for the initial 100 units. On Site Committee - Agreed to provide modified shelter assistance on the areas considered safe. - The outcome of the validation will be the basis for requesting additional funding for the shelter assistance. -Culture and religion were also taking into consideration such as having two or more wives of our Muslim brothers in which each wife is entitled of one shelter. Permanent Shelter Committee -Problem is the acquisition of the Land. -There are five (5) sites identified Sta. Elena, Luinab, Mandulog, Digkilaan, Abuno, and two additional from NHA Dalipuga and Upper Hinaplanon. DPWH -Handling the mobilization in the site development. -On-going proper embarking of Sta. Elena and Mandulog Sites. - Provided equipment and manpower and startedthe site development. NHA - Take charge of the planning and design LGU -Take charge of the coordination |

ISSUES AND CONCERN RAISED DURING THE MEETING

| AREAS OF CONCERN | RECOMMENDATION/REMARKS |
| --- | --- |
| Recovered Logs | -According to DENR only 60% of the logs will be generated and can be used since the some of the logs were damaged. It was estimated to generate about 700,000 board feet from the donated logs. -IOM requested for the logs to be used in Typhoon Sendong in Lanao del Sur, the Education Cluster requested for the logs for the repair of the school used as Evacuation Center and also Red Cross requested for the logs for construction of their shelter for Typhoon Sendong victims. -RD Solamillo clarified that the logs will be used for shelter, damaged schools, chairs and tables affected by Typhoon Sendong. The logs will exclusively be used for Iligan City victims of the said disaster. -It was suggested to have guidelines in prioritization and allocation of the logs. |
| Construction of Bunkhouses | - IOM is willing to construct bunkhouses as transitional homes from Evacuation Center to Permanent sites. - LGU will identify open spaces and areas within the relocation site for the bunkhouses. |
| Provision of Shelter Kits | - There is on-going distribution of Shelter Kits in some affected areas by IOM, PRC and Habitat for Humanity. The cost of Shelter Kits provided were as follows: IOM - P 7,000 PRC – P 5,000 HABITAT FOR HUMANITY – P 3,000 - It was suggested to avoid duplication in the provision of Shelter Kits to the IDPs of Typhoon Sendong, Technical Working Group for the said purpose will meet after the Shelter Cluster meeting to discuss and agree on the areas where they will provide Shelter Kits. |

- Other Matters

- It was agreed during the meeting that the regular schedule of the Shelter Cluster Meeting in Iligan City will be every Wednesday at 9:00 o’ clock in the morning.

There being no other matter to be discussed, the meeting adjourned at about 11:30 in the morning.

Prepared by:

DEOCELYN G. SABUCDALAO

Admin Clerk

DSWD Field Office 10

Approved by:

ATTY. ARACELI F. SOLAMILLO, CESO III

Regional Director

DSWD Field Office 10