## Sheet2
Annex 1 _ Sector Minimum Preparedness Actions (MPA)

## All Sectors MPA
All Sectors - Minimum Preparedness Actions (MPA)
Sector or Cluster | Activity | Status |  |  | Due Date | Lead
|  | Completed | Ongoing | Not Started
Camp Management and Camp Coordination Cluster | Communicate with national, region/state government entities on CCCM practices and responsibilities in the events of event/large scale displacement | ü |  |  | n/a | CCCM Cluster, Partner IOM
Camp Management and Camp Coordination Cluster | CCCM training for Government on post natural disaster settings, “principles and approaches” | ü |  |  | n/a | CCCM Cluster, Partner IOM
Camp Management and Camp Coordination Cluster | Monthly updated list online of Cluster participants (www.shelternficccmmyanmar.org) | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Every two months data/analysis on CCCM coverage (www.shelternficccmmyanmar.org) | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Focal points for Camp Management assessments with awareness of standards, shared wih partners | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | All partners aware of overall CCCM strategy, standards (including cross-cutting issues), especially issues related to vulnerable groups | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Collect and analyse information on populations likely to be more vulnerable |  | ü |  | Sept. 2014 | CCCM Cluster
Camp Management and Camp Coordination Cluster | Agree on data management, data sharing mechanisms and protocols, rapid assessment tools and reporting formats | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Evaluate overall performance of the Cluster | ü |  |  | n/a | Global CCCM Cluster
Early Recovery Sector (ER) | Updated contact list of sector participants shared at list twice per year | ü |  |  |  | UNDP
Early Recovery Sector (ER) | Focal points for joint assessments with sector expertise identified, shared with partners and updated twice per year | ü |  |  |  | UNDP
Early Recovery Sector (ER) | Response funding sources ad mechanisms identified and listed |  |  | ü | 2014-07-01
Early Recovery Sector (ER) | ER multi sector assessment tool developed and sector members trained |  |  | ü | 2014-07-01 | UNDP
Early Recovery Sector (ER) | Training to government counterparts, sector members and cluster/sector leads on conflict sensitivity |  |  | ü | Aug. 2014 | UNDP
Education in Emergencies (EiE) | National level education coordination mechanism and roles and responsibilities (individual and organizational) clarified – ETWG vs. EiE Sector Coordination Group |  | ü |  | 2014-07-01 | EiE Sector Leads: UNICEF, SCI
Education in Emergencies (EiE) | Government focal points and mechanisms identified and included/incorporated into the EiE coordination mechanism |  | ü |  | 2014-07-01 | EiE Sector
Education in Emergencies (EiE) | Updated sector contact list shared regularly (March, June, September, December) | ü |  |  | n/a | EiE Sector
Education in Emergencies (EiE) | Focal points for joint assessments with expertise and experience identified from sector partners, listed and updated quarterly (March, June, September, December) | ü |  |  | n/a | EiE Sector
Education in Emergencies (EiE) | Sector stockpiles available in country listed and updated regularly (March, June, September, December), and supply chain identified for rapid procurement and delivery | ü |  |  | n/a | EiE Sector
Education in Emergencies (EiE) | Available sector seed and response funding sources and mechanisms identified, listed and notified (updated bi-annually - March and September) (taking into account flash appeal funding opportunities in the case of emergency) | ü |  |  | n/a | EiE Sector
Education in Emergencies (EiE) | EiE section of a multi-sectoral rapid initial assessment (MS-IRA) tool developed and agreed. | ü |  |  | n/a | EiE Sector
Education in Emergencies (EiE) | EiE specific rapid assessment tool developed and agreed by sector |  | ü |  | 2014-07-01 | EiE Sector
Education in Emergencies (EiE) | Identified EiE assessment focal points trained in use of assessment tools |  |  | ü | 2014-07-01 | EiE Sector
Education in Emergencies (EiE) | Minimum emergency education assistance package, in line with INEE Minimum Standards (and current programming) agreed by sector and documented |  | ü |  | 2014-07-01 | EiE Sector
Education in Emergencies (EiE) | Sector cross-cutting issues (gender, conflict sensitivity, inclusive education, child rights, protection, PSS) and strategies to be included in check-lists. Updated and shared bi-annually (April and October) |  | ü |  | 2014-07-01 | EiE Sector
Education in Emergencies (EiE) | Education in emergencies response capacity amongst key partners (in emergency-prone areas and nationally) assessed. Plans to fill capacity gaps developed |  | ü |  | Aug. 2014 | EiE Sector
Food Sector | Udpated contact list of sector participants shared at list twice per year | ü |  |  | n/a | WFP
Food Sector | Updated list of government counterparts (national and local levels) shared | ü |  |  | n/a | WFP
Food Sector | Sector stockpiles available in country identified, updated at least twice per year and shared with partners, and supply chain identified for rapid procurement and delivery | ü |  |  | n/a | WFP
Food Sector | Focal points for joint assessments with sector expertise identified, shared with partners and updated twice per year | ü |  |  | n/a | WFP
Food Sector | Agreed joint-assessment formats put in place | ü |  |  | n/a | WFP
Food Sector | Training of joint-assessments on agreed formats |  | ü |  | June | WFP
Food Sector | Agreed minimum assistance package, in line with Sphere Standards | ü |  |  | n/a | WFP
Food Sector | Information management and reporting focal points identified | ü |  |  | n/a | WFP
Food Sector | Cross-cutting issues identified, shared with partners and included within the activities in check-lists | ü |  |  | n/a | WFP
Food Sector | Sector check list of inmediate actions after disaster | ü |  |  | n/a | WFP
Food Sector | Sector check list of actions within two weeks | ü |  |  | n/a | WFP
Food Sector | Emergency preparedness and response food sector simulation exercise? (awaiting HCT plan for SimEx in September) |  | ü
Health Cluster | Update contact list of sector participants share with the sector partners | ü |  |  | n/a | Health Cluster
Health Cluster | Focal points for joint assessments with sector expertise identified and shared with partners | ü |  |  | n/a | Health Cluster
Logistics Sector | Update of contact list of sector participants shared at list twice per year | ü |  |  | Oct. 2014 | WFP
Logistics Sector | Review rosters of Local Transporters, Customs clearing agents, Non Food Item suppliers, etc. | ü |  |  | Sept. 2014 | WFP
Logistics Sector | Review SOPs for logistics activities such as customs and port clearance, transport, warehouse management |  | ü |  | 2014-07-01 | WFP
Logistics Sector | Update and review on the stock level of emergency operational equipment | ü |  |  | 2014-07-01 | WFP
Logistics Sector | Review Logistics Capacity Assessment (LCA) – online |  | ü |  | Sept. 2014 | WFP
Logistics Sector | Trainings for emergency operation (i.e.WH management, MSU erection, logistics cluster, etc.) |  | ü |  | Dec. 2014 | WFP
Non Food Items Cluster | Establish responsibilities and coordination mechanisms between the Government and NFI partner agencies to coordinate effectively |  | ü |  | Aug. 2014 | NFI Cluster
Non Food Items Cluster | Monthly updated list online of Cluster participants (www.shelternficccmmyanmar.org) | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Every two months data/analysis on NFI coverage (www.shelternficccmmyanmar.org) | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Focal points for joint assessments with awareness of NFI standards, shared wih partners and updated 3 times per year |  | ü |  | 2014-06-01 | NFI Cluster
Non Food Items Cluster | Clarify total NFI contigency supplies for entire Cluster, updated 3 times per year |  | ü |  | 2014-06-01 | NFI Cluster
Non Food Items Cluster | All partners aware of overall NFI strategy, including cross-cutting issues | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Collect and analyse information on populations likely to be affected, and identify likely scenarios and responses |  | ü |  | 2014-06-01 | NFI Cluster
Non Food Items Cluster | With NFI partner agencies agree on minimum NFI standards in-line with prioritised criteria | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Arrange procurement of contingency supplies, as required | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Agree on data management, data sharing mechanisms and protocols, rapid assessment tools and reporting formats |  | ü |  | 2014-06-01 | NFI Cluster
Non Food Items Cluster | Coordinate with transport agents to identify stanby capacities/quantities/delivery time for emergency NFI distributions |  |  | ü | 2014-06-01 | NFI Cluster
Non Food Items Cluster | Assess warehousing capacities against minimum agreed contingency requirements |  | ü |  | 2014-06-01 | NFI Cluster
Nutrition Sector | Updated contact list of sector participants shared at least twice per year | ü |  |  | n/a | UNICEF
Nutrition Sector | Focal points for joint assessments with sector expertise identified, shared with partners and updated twice per year |  | ü |  | Sept. 2014 | UNICEF
Nutrition Sector | Preposition of supplies for nutrition response for under-fives and pregnant/lactating women | ü |  |  | n/a | UNICEF
Nutrition Sector | Sector stockpiles available in country identified, updated at least twice per year and shared with partners, and supply chain identified for rapid procurement and delivery |  | ü |  | Sept. 2014 | UNICEF
Nutrition Sector | Capacity building/training provided to partners on identified gaps |  | ü |  | Oct. 2014 | UNICEF
Nutrition Sector | Mapping (3W) of partners, including UN agencies, MoH and I/NGOs | ü |  |  | n/a | UNICEF
Nutrition Sector | Adapt generic tools recommended by Global Nutrition Cluster such as the ‘Rapid assessment matrix’, SMART and standard tools for Myanmar context and endorsethrough sector/cluster | ü |  |  | n/a | UNICEF
Nutrition Sector | Ensure availability of standard protocols for community-based and in-patient management of acute malnutrition |  | ü |  | Sept. 2014 | UNICEF
Nutrition Sector | Support a multi-sectoral rapid assessment mechanism and format that includes priority nutrition information. | ü |  |  | n/a | UNICEF
Protection Sector | Maintain and update Protection working group, Child Protection and GBV sub-working groups contact lists at national and sub-national levels | ü |  |  | n/a | UNHCR, UNFPA, UNICEF
Protection Sector | Consolidate and keep up to-date contacts of key focal points within line ministries at the state and township level | ü |  |  | n/a | UNHCR, UNICEF, UNFPA
Protection Sector | Ensure data protection and security protocols are in place for each protection-related case management agency, in case of evacuation of personnel |  |  | ü | 2014-06-01 | UNHCR, UNFPA, UNICEF
Protection Sector | Harmonize CP Case Management Form and agree on a Child Protection Information Management System, (CPIMS) emergency template |  | ü |  | 2014-06-01 | UNICEF (SCI)
Protection Sector | Initiate emergency GBV IMS: emergency intake forms and information sharing protocols |  | ü |  | 2014-06-01 | UNFPA, UNHCR
Protection Sector | Identify Protection WG, CP and GBV SWG members with relevant language and technical skills willing to take part in the inter-agency rapid assessment teams |  | ü |  | 2014-06-01 | UNHCR, UNFPA, UNICEF
Protection Sector | Disseminate the revised MIRA form and specific protection related questions/observations for Protection Sector/CP/GBV Sub Sector members at national and sub-national level. |  | ü |  | 2014-06-01 | UNHCR
Protection Sector | Develop and disseminate a protection action sheets (addressing Gender/GBV/CP/Elderly/Disabled issues) per sector to mitigate potential risks in the delivery of broader humanitarian assistance |  | ü |  | 2014-06-01 | UNHCR, UNICEF, UNFPA, GenCap
Protection Sector | Finalize key messages on prevention of separation in emergencies for communities and translate them into relevant languages |  | ü |  | 2014-06-01 | UNICEF, UNHCR
Protection Sector | Unaccompanied and separated children (UASC) working group field- testing the UASC framework |  | ü |  | 2014-06-01 | UNICEF (MRCS)
Protection Sector | Disseminate CP Inter-Agency Minimum Standards |  |  | ü | 2014-06-01 | UNICEF
Protection Sector | Develop “emergency” referral protocols for acute and protracted emergency contexts. | ü |  |  | n/a | UNFPA
Protection Sector | Develop and disseminate protection emergency ‘Toolkit’ to include safety audit tools, rapid assessment/focus group questions. Include guidance notes on child protection, GBV and main protection issues in emergencies. |  | ü |  | 2014-06-01
Protection Sector | Consolidate and keep updated protection-related itemsstockpiles (as per stock pile list) available in country |  | ü |  | 2014-06-01 | UNHCR, UNFPA, UNICEF
Protection Sector | Train Protection Sector, GBV and CP Sub-Sector members on the use of the Protection Incident Monitoring Form, child protection intake form, GBV intake form. |  | ü |  | 2014-06-01 | UNHCR, UNICEFUNFPA
Protection Sector | Ensure Protection Sector GBV and CP Sub-sector members at national and sub-national level are briefed on Protection from Sexual Violence and Abuse (PSEA) and are able to inform communities on complaint mechanisms and immediate assistance |  |  |  | 2014-06-01 | UNHCR,UNICEF, UNFPA, GenCap
Emergency Telecommunications Sector | Organize regular local working group meetings with inter-agencies ICT focals | ü |  |  | n/a | WFP
Emergency Telecommunications Sector | Update the contact list of ICT focals from agencies twice per year | ü |  |  | n/a | WFP
Emergency Telecommunications Sector | Update and share the status of Data and Telecomm infrastructure service and equipment of agencies in country and prepositioning if required. |  | ü |  | 2014-07-01 | WFP
Emergency Telecommunications Sector | Get the countrywide UN radio license from the government |  | ü |  | End of 2014 | WFP/UNDSS
Emergency Telecommunications Sector | Regular update of the countrywide staff contract list, callsigns and the emergency communication equipment training to the users | ü |  |  | n/a | UNDSS
Emergency Telecommunications Sector | To organize emergency telecomm training for ICT staff in country to be ready for rapid response |  |  | ü | Oct. 2014 | WFP
Shelter Cluster | Monthly updated list online of Cluster participants (www.shelternficccmmyanmar.org) | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Updated site plans online for key/vulnerable IDP communities (www.shelternficccmmyanmar.org) | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Focal points for joint assessments with awareness of emergency shelter | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Clarify total emergency shelter contigency supplies for entire Cluster, updated 3 times per year |  | ü |  | 2014-06-01 | Shelter Cluster
Shelter Cluster | All partners aware of overall shelter strategy, including types of emergency shelter intervention, minimum standards and cross-cutting issues | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Collect and analyse information on populations likely to be affected, and identify likely scenarios and responses |  | ü |  | Aug. 2014 | Shelter Cluster
Shelter Cluster | Arrange procurement of contingency supplies, as required | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Agree on data management, data sharing mechanisms and protocols, rapid assessment tools and reporting formats | ü |  |  | n/a | Shelter Cluster
WASH Cluster | Updated contact list of sector participants shared at least twice per year | ü |  |  | n/a | WASH Cluster
WASH Cluster | Public Information management system in place | ü |  |  | n/a | WASH Cluster /MIMU
WASH Cluster | Develop reporting mechanism and template for situation report | ü |  |  | n/a | WASH Cluster
WASH Cluster | Share mechanism with Regional Emergency Cluster Advisor (RECA) and Global cluster for specific support activation | ü |  |  | n/a | RECA
WASH Cluster | Define proper linkage with Government (contact list, preliminary meeting,…) |  | ü |  | 2014-06-01 | WaSH Cluster / OCHA
WASH Cluster | Cross-cutting issues identified, shared with partners and included in check-lists | ü |  |  | n/a | WASH Cluster
WASH Cluster | Wash stockpiles available with national coverage, updated at least twice per year and shared with partners, and supply chain identified for rapid procurement and delivery |  | ü |  | June 2014 | WASH Cluster
WASH Cluster | Focal points for joint assessments with WaSH expertise identified, shared with partners and updated twice per year | ü |  |  | n/a | WASH Cluster
WASH Cluster | Consolidate MIRA quick assessment in coordination with OCHA | ü |  |  | n/a | WASH Cluster
WASH Cluster | Agreed minimum assistance package with associated technical standard (design and EIC) | ü |  |  | n/a | WASH Cluster
WASH Cluster | Capacity building/training to partners on identified gaps provided: UNICEF emergency training national and technical training to be organized |  | ü |  | 2014-07-01 | WASH Cluster
WASH Cluster | Cross-cutting issues identified, shared with partners and included in check-lists | ü |  |  | n/a | WASH Cluster

## CCCM
CCCM Cluster - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilise camp management needs assessment team(s) | CCCM Cluster | CCCM cluster partners | 7 days (maximum) | NFI, Shelter & Protection
If population relocated, assess camp management needs | CCCM Cluster | CCCM cluster partners | 5 days (maximum) | NFI, Shelter & Protection
Immediately after disaster
Mobilise camp management assessment team | CCCM Cluster | Cluster partners | 72hrs | NFI, Shelter& Protection
Conduct rapid assessments of camp management needs of affected population, which can include security threats/risks, access to affected areas and logistical needs | CCCM Cluster | Cluster partners | 72hrs | NFI, Shelter & Protection
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | CCCM Cluster | Cluster partners | 7 days | NFI, Shelter & Protection
Organise regular coordination meetings, which can include liaising with appropriate government counterpart at national and sub-state level | CCCM Cluster | Cluster partners | 48hrs | NFI, Shelter & Protection
Attend national and state ICC meeting(s) | CCCM Cluster | OCHA | 48hrs | Sectors/Clusters
Within two weeks
Deploy additional staff from emergency rosters | CCCM Cluster | IOM | 14 days
If appropriate, adjust plan/strategy | CCCM Cluster |  | 14 days
Support the formulation of draft appeals involving all relevant partners | CCCM Cluster |  | 14days

## ER
Early Recover Sector - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Confirm with government coordination structures at both the national and state level | UNDP | Sector partners | Immediately
Support Sectors/clusters readiness for emergency response alongside government engagement | UNDP |  | Immediately | Sectors/clusters
Work closely with ER global cluster and UNDP HQ to identify a standby SURGE capacity | UNDP | Sector partners
Provide updated information of ER and DRR WG contacts including government counterparts | UNDP | Sector partners |  | Sector/cluster
Support RRDto prepare for coordination of emergency response | UNDP | Sector partners |  | DRR WG
Prepare for rapid assessment including on trainings on assessment tools etc. | UNDP
Immediately after disaster
Convene first national level combined meeting between the ER sector and DRR working group | UNDP | Sector partners,DRR WG | 24hrs | Sectors/clusters,DRR WG
Activate surge deployment | UNDP
Work side by side with relevant government coordinating body, RRD, to plan and coordinate for disaster response for inclusion in Flash Appeals | UNDP | Sector partners | 24 to 36 hrs
Support sectors/clusters to identify opportunities for recovery interventions | UNDP | Sector/Cluster | 24 to 36 hrs
Rapid assessment of impact on local governance arrangements and their capacity to coordinate and manage emergency response | UNDP | Government, DDR WG | 48hrs
Within two weeks
Preliminary ER needs assessment including impact on livelihoods, agriculture, fisheries, communication, infrastructure, access to basic services and local governance | UNDP | Sector partners | 7 to 10 days
Prepare ER assessment reports; clearly identify needs and funds required | UNDP | Sector partners | 7 to 10 days
Develop preliminary ER Sector work plan (Short term Plan) | UNDP | Sector partners | 7 to 10 days
Develop an integrated medium term cross sector plan (3-6 months) | UNDP | Sector Partners | 14 + days | Sectors/clusters
Surge capacity is deployed based on sector workplan–short/ medium term deployment | UNDP |  | 10 to 14 days
SupportRRD to set-up coordination mechanism of recovery assistance | UNDP | Sector partners | 7 to 10 days | DRR WG
Prepare concept notes/proposals for fund raising | UNDP | Sector Partners | 10 to 14 days
Organize a donor meeting collectively with other sector/cluster and government | UNDP | Secotr/cluster | 10 to 14 days

## Education
Education in Emergencies Sector - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Re-confirm the coordination structure and roles and responsibilities (individuals and agencies) for the coming emergency | EiE Sector | UNICEF, SCI, MOE, Sector partners | Immediately | Education (non-EiE), WaSH,
Re-confirm in-country EiE sector contact list, surge capacity and focal points and staff experienced and skilled in assessments. | EiE Sector | UNICEF, SCI, MOE, Sector partners | Immediately | Education (non-EiE)
Establish current regional EiE surge capacity able to deploy additional support if needed | EiE Sector | MOE, Sector partners | Immediately | Education (non-EiE)
Re-confirm sector stockpiles available in country and delivery times | EiE Sector | MOE, Sector partners | Immediately
Encourage and support EiE Sector partners to prime their national (and if necessary regional) supply pipelines | EiE Sector | MOE, Sector partners | Immediately
Re-confirm available sector seed and response funding and ensure application procedures clear and, where possible, pre-completed | EiE Sector | MOE, Sector partners, OCHA, Donors | Immediately | WaSH, Child Protection
Encourage and support EiE Sector partners to prime their internal funding mechanisms (and map potential allocations) | EiE Sector | MOE, Sector partners, OCHA, Donors | Immediately | WaSH, Child Protection
Where necessary and feasible, organize training of national-level surge staff in response and assessment (incl. agreed tools) in preparation for potential deployment to the field. | EiE Sector | MOE, Sector partners | Immediately | All sectors but esp. WaSH, Child Protection
Immediately after disaster
Convene first national level coordination meeting with sector partners and MOE | EiE Sector | UNICEF, SCI | 24hrs | Education (non EiE), Sectors/Clusters
Ensure education is represented and recognized at national level coordination and response planning forum | EiE Sector | MOE, Sector partners | 24hrs | Education (non EiE), Sectors/Clusters
Coordinate the mobilization and deployment of pre-identified sector surge capacity for initial response activities, including those experienced and skilled in joint assessments | EiE Sector | UNICEF, SCI, MOE, Sector partners | 24 to 36hrs | Education (non EiE), Sectors/Clusters
Coordinate the mobilization and deployment of pre-identified sector stockpiles available in country | EiE Sector | UNICEF, SCI, MOE, Sector partners | 36 to 48hrs | Sectors/Clusters
If necessary, support partners in securing additional education stocks from pre-identified suppliers for rapid procurement and delivery | EiE Sector | UNICEF, SCI, MOE, Sector partners | 36 to 48hrs | Sectors/Clusters
Record and coordinate funding applications by sector partners. | EiE Sector | UNICEF, SCI | 48 to 72hrs | Sectors/Clusters, but esp. WaSH and Child Protection
If necessary, support partners in their identification of and applications for initial seed-funding in line with the priorities identified at the field level (taking into account flash appeal funding opportunities available in case of emergency) | EiE Sector | MOE, Sector partners, Donors | 48 to 72hrs | Sectors/Clusters, but esp. WaSH and Child Protection
Support field-level coordination mechanisms in coordinating, processing and analyzing the education part of the initial multi-sector and agency rapid assessment and disseminate results. | EiE Sector | UNICEF, SCI, MOE, Sector partners | 3 to 7 days | Sectors/Clusters
Within two weeks
Support the field-level EiE Sector in development of sector response plans and strategies (including locations and methods of delivery, participation of affected communities and logistical arrangements). | EiE Sector | UNICEF, SCI, MOE, Sector partners | 7 to 10 days | Sectors/Clusters, but esp. WaSH, Child Protection
If necessary, coordinate partner’s needs for additional education response surge capacity, working with field-level EiE sector coordinator. If necessary request information management support from the region or Education Cluster in order to effectively manage growing pool of information, and demand for information for fundraising and proposals. | EiE Sector | UNICEF, SCI, MOE, Sector partners | 10 to 14 days | Education (non-EiE)
Where necessary, support the field-level EiE Sector in the preparation, conduct and analysis of a comprehensive joint education sector needs and damage assessments in the affected communities. | EiE Sector | UNICEF, SCI, MOE, Sector partners | 14 days + | Education (non-EiE)
Support the field-level EiE sector in updating plans and developing new proposals based on comprehensive education assessment data and analysis (to build on initial response plans and concept notes). | EiE Sector | UNICEF, SCI, MOE, Sector partners | 14 days + | Sectors/Clusters, but esp. WaSH, Child Protection

## Food
Food Sector - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Obtain weather forecast/early warning info from various sources | OCHA, WFP | Sector partners | 5 days before | Sectors/clusters
Check available food stocks in country | WFP | Sector partners | 4 days before
Review transport routes (access, safety, capacity, etc) | WFP | Sector partners | 4 days before
Convene coordination meetings (information sharing and preparedness) | WFP | Sector partners, OCHA | 3 days before | Sectors/clusters
Select assessment members to be deployed | WFP | Sector partners | 3 days before
Inmediately after disaster
Convene coordination meetings (partners, government); government to share its plans and capacity | WFP | Sector partners | 24hrs
Develop initial assessment plans (including logistics arrangements) | WFP | Sector partners | 24hrs
Deploy initial assessment team(s) (multi-sector/cluster) | OCHA | Sector partners | 48hrs | Sectors/clusters
Confirm with govt on number of beneficiaries and agree on the number | OCHA, WFP | Sectors/clusters | 48 to 72hrs | Sectors/clusters
Check existing stocks (and additional supplies) | WFP | Sector partners | 24hrs
Deploy food distribution team | WFP | Sector partners | 48 to 72hrs
Deliver food assistance | WFP | Sector partners | 72 hrs
Food distribution | WFP | Sector partners | 72 hrs
Follow-up meetings (partners, government) | WFP | Sector partners | 96 hrs | Sectors/clusters
Within two weeks
Plan more detailed assessment (as required) | WFP | Sector partners | Day 5
Deploy assessment team(s) | WFP | Sector partners | Day 6
Check available stocks | WFP | Sector partners | Day 7
Convene coordination meetings (partners, government); government to share its plans and capacity | WFP | Sector partners | Day 8
Deliver food or cash assistance | WFP | Sector partners | Day 9
Food distribution | WFP | Sector partners | Day 9
Follow-up meetings (partners, government) | WFP | Sector partners | Day 12 | Sectors/clusters

## Health
Health Cluster - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Update and share 3W and contact list with relevant partners | Health Cluster | Cluster partners | Within 24hrs | WaSH & Nutrition
Initiate emergency coordination meeting | Health Cluster | Cluster partners | Within 24hrs | WaSH & Nutrition
Check with all partners on the pre-positioning and stock-piling of medical supplies and equipment including medicines and vaccines, hygiene and dignity kits, reproductive health kits and medication for treatment of trauma /acute /chronic diseases. | Health Cluster | Cluster partners | Within 24hrs | WaSH & Nutrition
Immediately after disaster
Designate the WHO emergency focal point and partner agencies focal points and share contact details with all relevant parties | Health Cluster | Cluster partners | 24hrs
Ensure a continuous presence at the site of the emergency and make initial contact with local authorities and partners | Health Cluster | Cluster partners | 48hrs | WaSH & Nutrition
Negotiate access and clearances with government, where relevant, on behalf of health sector partners | Health Cluster | Cluster partners | 48hrs
Make widely available the preliminary health sector analysis based on the most recent event risk assessment | Health Cluster | Cluster partners | 48hrs | WaSH & Nutrition
Compile and produce the first situation report, media brief and other communications and advocacy products | Health Cluster | Cluster partners | 48hrs | WaSH & Nutrition
Ensure the arrival in-country of a team of experienced professionals to reinforce or replace the repurposed WCO staff | Health Cluster | Cluster partners | Day 4
Establish and deliver emergency administrative, human resources, finance, grant management and logistics services | Health Cluster | Cluster partners | Day 4
Establish health sector/cluster leadership and coordination; conduct a health sector/cluster meeting; update the 4W matrix | Health Cluster | Cluster partners | Day 4 | WaSH & Nutrition
Represent WHO and the health sector/cluster at meetings of the UN Country Team (UNCT), Humanitarian Country Team (HCT), inter-sector/cluster coordination and other relevant sectors/clusters | Health Cluster |  | Day 4
Use preliminary health sector analysis to identify major health risks and health sector objectives and priorities | Health Cluster | Cluster partners | Day 4
Engage health sector partners to participate in a joint health assessment as part of a multisectoral process | Health Cluster | Cluster partners | Day 4
Develop a flexible, short-term health sector response strategy and action plan | Health Cluster | Cluster partners | Day 5
Within two weeks
Develop a funding appeal | Health Cluster | Cluster partners | 1 week | WaSH & Nutrition
Provide technical assistance | Health Cluster | Cluster partners | 1 week | WaSH & Nutrition
Adapt/strengthen a surveillance and early warning system and produce the first weekly epidemiological bulletin | Health Cluster | Cluster partners | 1 week | WaSH & Nutrition
Promote and monitor the application of protocols, health standards, methodologies, tools and best practices | Health Cluster | Cluster partners | 1 week | WaSH & Nutrition
Compile and produce a second situation report, media brief and other communications and advocacy products | Health Cluster | Cluster partners | 1 week | WaSH & Nutrition
Monitor and share relevant information for decision-making on health indicators, using appropriate parameters or measurement | Health Cluster | Cluster partners | 1 week | WaSH & Nutrition
Monitor the response of the health sector and address gaps | Health Cluster | Cluster partners | 1 week | WaSH & Nutrition
Make widely available the results of the joint health assessment | Health Cluster | Cluster partners | 2 weeks | WaSH & Nutrition

## Logistic
Logistics Sector - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Ad-hoc sector (cluster) meetings to share the information and updage regularly | WFP |  | Immediately
Support Sectors/clusters assess readiness for emergency response | WFP |  | Immediately
Provide updated information of logistics sector contacts | WFP |  | Immediately
Immediately after disaster
Prepare for coordination of emergency response. | WFP |  | Immediately
Activate Logistic cluster if requested by HC/HCT | WFP | Sector partners | 2 to 3 days
Rapid assessment of Logistics Capacity Assessment of affected areas | WFP | Sector partners | 1 to 3 days | Sectors/Clusters
Identify required funding source | WFP | Sector partners | 1 to 7 days
Draw Logistics Network for affected areas/populations | WFP | Sector partners | 1 to 7 days
Within two weeks
Coordinate with authorities concerned and obtain permission for logistics operation | WFP | Sector partners | 1 to 7 days
Identifying needs of logistics services | WFP | Sector partners | 5 to 7 days
Contract with service providers | WFP | Sector partners | 5 to 7 days
Set up MSUs and warehouse equipments at affected areas | WFP | Sector partners | 5 to 7 days
Deployment of trained/experienced staffs | WFP | Sector partners | 1 to 2 week

## NFI
Non Foof Items Cluster (NFI) - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilise NFI needs assessment team | NFI Cluster | Cluster members | 5 days (maximum) | Shelter, CCCM & WaSH Clusters
If population relocated, NFI distribution in advance of event | NFI Cluster | Cluster members | 5 days (maximum) | Shelter, CCCM &WaSH Clusters
Mobilise NFI needs assessment support | NFI Cluster | Cluster members | 5 days (maximum) | Shelter, CCCM & WaSH Clusters
Immediately after disaster
Mobilise assessment team, which includes evaluation of need for intersector assessment, led by OCHA | NFI Cluster | Cluster members | 72hrs | Shelter, CCCM & WaSH Clusters
Conduct rapid assessments of NFI needs for affected population, which can include security threats/risks, access to affected areas and logistical needs | NFI Cluster | Cluster members | 3 days | Shelter, CCCM & WaSH Clusters
Distribute NFI core kits from contingency stock and any additional relief items demanded due to weather conditions and/or emergency circumstances | NFI Cluster | Cluster members | 7 days | Shelter, CCCM & WaSH Clusters
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | NFI Cluster | Cluster members | 7 days | Shelter, CCCM & WaSH Clusters
Organise regular coordination meetings, which can include liaising with appropriate government counterpart at national and state level | NFI Cluster | Cluster members | 48hrs | Shelter, CCCM & WaSH Clusters
Attend at national and sub-national level ICC meeting | NFI Cluster | OCHA | 48 to 72hrs | Shelter, CCCM & WaSH Clusters
Within two weeks
Initiate procurement to supplement deliveries if initial distrbutions inadquate | NFI Cluster | Cluster members | 7 to 10 days
Deploy additional staff from emergency rosters | NFI Cluster | IFRC | 14 days
If appropriate, adjust plan/strategy | NFI Cluster |  | 14 days
Support the formulation of draft appeals involving all relevant partners | NFI Cluster |  | 14 days

## Nutrition
Nutrition Sector - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Verify existing stocks of essential supplies including RUTF, fortified nutritional products including blended food, and micronutrient supplements and identify resources for gaps | UNICEF | National Nutrition Centre (NNC) (MoH), Myanmar Nutrition Technical Network (MNTN)
Verify existing stocks of essential supplies including RUTF, fortified nutritional products including blended food, and micronutrient supplements and identify resources for gaps | UNICEF | National Nutrition Centre (NNC) (MoH), Myanmar Nutrition Technical Network (MNTN) | 3 days | Food, Health
Strengthen/confirm existing coordination mechanisms or, if unavailable, create them in collaboration with national authorities to ensure that the humanitarian response is timely and coordinated, and that it conforms to humanitarian principles and agreed-upon standards and benchmarks. | UNICEF | NNC, MNTN | 5 days | Food, Health
Immediately after disaster
Conduct meeting for inter-agency coordination (Myanmar Nutrition Technical Network) which comprises NNC/MoH and other nutrition partners | UNICEF | NNC/MoH, MNTN | 24hrs.
Ensure and establish effective coordination mechanism among nutrition partners, including Myanmar Nutrition technical Network members | UNICEF | NNC/MoH, MNTN | 24hrs.
Undertake a multi-sectoral rapid assessment, including key priority information for nutrition | UNICEF | NNC/MoH, MNTN | 48 to 72hrs and within 1 to 2 weeks | Food, Health, WaSH
Within two weeks
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | UNICEF | NNC/MoH, MNTN | 7 days | Food, Health, WASH
Organize coordination meeting, which can include liaising with appropriate government counterpart at national, State/Division and township level | UNICEF | NNC/MoH, MNTN | 7 days
Support existing nutrition implementation structure for emergency response | UNICEF | NNC/MoH, MNTN | 2 weeks
If necessary, initiate a rapid assessment of acute malnutrition and influencing factors, and of the status of existing nutrition facilities and capacities, including human resources and supplies | UNICEF | NNC/MoH, MNTN | 2 weeks+ | Food, Health, WASH
Monitor nutritional status by coordinating and establishing a nutritional surveillance system with partner agencies (technical and financial support, strengthening of existing surveillance units) | UNICEF | NNC/MoH, MNTN | 2 weeks
Nutrition sector/cluster identifies needs and financial resources required for required activities among partners | UNICEF | NNC/MoH, MNTN | 2 weeks
Take part ininter-cluster coordination | UNICEF | NNC/MoH, MNTN | 2 weeks | Food, Health, WASH
Identify and transmit supply inputs to UNICEF Supply and Logistics | UNICEF | NNC/MoH, MNTN | 2 weeks
If necessary, deploy additional staff from emergency rosters | UNICEF | NNC/MoH, MNTN | 2 weeks
Support the formulation of draft appeals involving all relevant partners | UNICEF | NNC/MoH, MNTN | 2 weeks

## Protection
Protection Sector - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilise assessment team / team members to participate in the initial multi sector rapid assessment | UNHCR | UNICEF, UNFPA | 3 days | Sectors/Clusters
Update and share 3W and contact list with relevant partners | UNHCR | UNICEF, UNFPA | 3 days
Immediately after disaster
Mobilise assessment team / team members to participate in the initial multi sector rapid assessment | UNHCR | UNICEF, UNFPA, DRC | Immediate | Sectors/Clusters
Convene coordination meetings with relevant sector members and attend inter-sector coordination meetings | UNHCR | Protection Sector CP and GBV sub-sectors | 24 to 36hrs | Shelter, CCCM &WaSH
Activate response teams from the Protection Sector national standby emergency list (GBV emergency response teams, family separation screening teams, etc) | UNHCR, UNICEF, UNFPA | Protection Sector CP and GBV sub-sectors | Immediate | Health , CCCM
Activate emergency GBV response referral protocols (ensuring safe access to health and PSS support for survivors) | UNFPA | IRC, MSF-H | 48 hours | Health
Establish of interim care facilities, especially in locations of displacement/relocation | UNICEF, UNHCR, UNFPA | SCI, ICRC, IRC, MRCS, IMC, HelAge | 72 hours | Shelter/CCCM
Within two weeks
Conduct technical protection assessment and safety audits (to identify and mitigate additional risks across sectors) | UNHCR, UNFPA, UNICEF | Protection WG, CP and GBV SWG | 1 week | WaSH, Shelter, CCCM, Health and Food
Deploy response teams from the Protection WG (GBV emergency response teams, family separation screening teams, etc) | UNHCR, UNICEF, UNFPA | Protection Sector, CP and GBV sub-sectors | 1 week
Map main protection issues and provide for and assist solutions | UNHCR, UNICEF, UNFPA | Protection Sector, CP and GBV sub-sectors | 1 to 2 weeks | Sectors/Clusters
Map available services for GBV response | UNFPA | GBV sub-sector | 2 weeks | Health, Child Protection
Conduct tracing and family reunification for UASC & referral to interim care | UNICEF | ICRC | 1 week | CCCM
Conduct tracing and family reunification for elderly and persons with disabilities | UNHCR | MRCS, ICRC, HelAge | 1 week | WASH, Shelter, CCCM, Health
Establish child friendly spaces and outreach in host communities and in locations of displacement/relocation | UNICEF | SCI, DRC | 1 week | CCCM, GBV
Establish safe spaces and outreach for women, girls and survivors of GBV in locations of displacement/relocation | UNFPA | IRC, IMC | 1 week | CCCM, Child Protection
Establish case referral and management system specific to children at risk, survivors of GBV and other types protection violations | UNHCR,UNFPA, UNICEF | Protection Sector, CP and GBV sub-sectors | 2 weeks | Health, Food, Nutrition, CCCM, NFI
Activate protection information management systems including protection incident monitoring, child protection, GBV. In the context of armed conflict ensure that information on grave violations against children is reported to the CTFMR. | UNHCR, UNFPA, UNICEF | Protection Sector, CP and GBV sub-sectors | 2 weeks | Health, CCCM
Distribute protection related items as needed | UNFPA, UNHCR, UNICEF | Protection Sector, CP and GBV sub-sectors | 1 week | CCCM, Health
Develop and disseminate key protection messages addressing the situation of particularly vulnerable populations, grave violations against children, violations of human rights and humanitarian law, etc. | UNHCR, UNFPA, UNICEF | Protection Sector, CP and GBV sub-sectors | 1 to 2 weeks | Sectors/Clusters

## Emergency Telecommunication
Emergency Telecommunications Sector - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Organize a ICT working group meeting and check/update and setup communication link among the HCT key players | WFP |  | Immediately
Check/update the contact list of local ICT working group and update the comm inventory | WFP |  | Immediately
Conduct a quick joint ICT assessment in the potential area | WFP/All |  | Immediately
Preposition the resources (staff, equipment) at least to provide basic communication service for day one | All Agencies |  | Immediately
Cordinate with local authorities for the possible communication infrastructure set up in the area | UNDSS/WFP |  | Immediately
Immediately after disaster
Organize a quick joint assessment for the availability of infrastructure in the affected area and try to restore/setup the basic data and communicationinfrasture as soon as possible | WFP/All |  | 48hrs
Provide ICT infrastructure assessment information to decide the activation of ETC cluster | WFP |  | 24hrs
Shipping/purchasing of equipment to provide longer term ICT solution in the affected area (if ETC is not activated) | All agencies |  | 1 week
If ETC is activated, prepare budget proposal and provide common data and telecomm services to interagencies | WFP |  | 1 week
Within two weeks
Setup long term data and telecomm infrastructure | WFP |  | 2 to 4 weeks
Setup UN radio room | UNDSS/WFP |  | 2 to 4 weeks
Regular ICT Working group /ECT meetings and share the updates | WFP |  | Daily/once a week

## Shelter
Shelter Cluster Minimum Preparedness Actions (MPAs)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Coordinate with transport agents to identify stanby capacities/quantities/delivery time for emergency distributions | Shelter Cluster | Cluster members | 3 to 5days | NFI & WaSH Clusters
Assess warehousing capacities against minimum agreed contingency requirements | Shelter Cluster | Cluster members | 3 to 5days | NFI & WaSH Clusters
Mobilise emergency shelter needs assessment team | Shelter Cluster | Cluster members | 5 days (maximum) | NFI & WaSH Clusters
If population relocated, emergency shelter distribution in advance of event | Shelter Cluster | Cluster members | 5 days (maximum) | NFI& WaSH Clusters
Mobilise emergency shelter needs assessment support from national level (as required) | Shelter Cluster | Cluster members | 5 days (maximum) | NFI& WaSH Clusters
Immediately after disaster
Mobilise assessment team, which includes evaluation of need for intersector assessment, led by OCHA | Shelter Cluster | Cluster members | 36 to 48hrs | NFI & WaSH Clusters
Conduct rapid assessments of emergency shelter needs for affected population, which can include security threats/risks, access to affected areas and logistical needs | Shelter Cluster | Cluster members | 7 days | NFI & WaSH Clusters
Distribute emergency shelter from contingency stock | Shelter Cluster | Cluster members | 7 days | NFI & WaSH Clusters
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | Shelter Cluster | Cluster members | 7 days | NFI & WaSH Clusters
Organise coordination meetings, which can include liaising with appropriate government counterpart at national and state level | Shelter Cluster | Cluster members | 24 to 36hrs | NFI & WaSH Clusters
Attend in Yangon and state level ICC meeting(s) | Shelter Cluster | OCHA | 24 to 48hrs | Sectors/Clusters
Within two weeks
Initiate procurement to supplement deliveries if initial distrbutions inadquate | Shelter Cluster | Cluster members | 7 to 10 days | NFI & WaSH Clusters
Deploy additional staff from emergency rosters | Shelter Cluster | IFRC | 14 days
If appropriate, adjust plan/strategy | Cluster members |  | 14 days | NFI & WaSH Clusters
Support the formulation of draft appeals involving all relevant parteners | Cluster members |  | 14 days

## WASH
WASH Cluster - Minimum Preparedness Actions (MPA)
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilize assessment team set up | WaSH Cluster | Pre-listed | Immediately
Mobilize NWC team for field support | WaSH Cluster | Pre-listed | Immediately
Pre-distribution of water reagent for water purification | WaSH Cluster |  | Immediately
If population relocated, Hygiene Kit distribution mechanism set up for reactive distribution for most vulnerable, in evacuation center straight after the events | WaSH Cluster |  | Immediately
Liaise with the appropriate governmental counter part | WaSH Cluster |  | Immediately
Immediately after disaster
Mobilize assessment team set up and evaluate assessment possibility for inter sectorial assessment lead by OCHA | WaSH Cluster | Pre-listed | 24hrs
WaSH Cluster participates to ICC meeting and keep inform WaSH partners | WaSH Cluster | OCHA |  | Sectors/Clusters
Evaluate the possibility to set up a WaSH coordination platform in the affected area | WaSH Cluster | If necessary | ASAP
WaSH Cluster keep close liaison with OCHA for update information | WaSH Cluster |  | Continous
WaSH Cluster share any relevant information with MIMU/OCHA | WaSH Cluster
WaSH Cluster share assessment findings with partners | WaSH Cluster | All concern
Liaise with OCHA/MIMU for mapping of needs | WaSH Cluster | OCHA/MIMU
Production of regular WaSH situation report and minutes meeting | WaSH Cluster |  | Every second day
Develop close link with either UNHCR or IOM on evacuation sites situation | WaSH Cluster | UNHCR/IOM |  | Shelter
Mobilize stocks available and define a supply process with UNICEF and other agencies | WaSH Cluster | UNICEF | 3 days | Logistics
Identify partners to support distribution of Hygien Kits and to deploy first WaSH support | WaSH Cluster | Cluster partners | 3 days
Contact UNICEF (stand by agreement) and OCHA on resource mobilization for WaSH needs | WaSH Cluster | UNICEF/OCHA | 3 days
Communicate with RECA, Global WASH Cluster CAST, UNICEF Regional Office on preliminary analysis, needs and support needed | WaSH Cluster | RECA | 3 days
Keep informedWaSH partners onmobilization of funds and donors support to the response | WaSH Cluster | All partners | Continuous
Evaluate and deploy first water supply possibility for affected population and evaluate overall response cost in respect of technical standard pre-defined | WaSH Cluster | WaSH Cluster | 5 days max.
Supply emergency sanitation equipment and define first response possible and evaluate overall response cost in respect of technical standard pre-defined | WaSH | WaSH Cluster partners | 5 days max.
Recruitment of additional Cluster staff to support the team in the affected areaor ofr coordination at national level | UNICEF | WaSH Cluster | 1 week
Daily update of 3W, including capacity response | WaSH Cluster |  | Daily
Monitoring of NFI supply | WaSH Cluster | Implementing partners | Weekly
Within two weeks
Consolidate the geographical positioning of WaSH actors | WaSH Cluster | Sub WaSH Cluster | 2 weeks
Consolidate the most appropriate technical response, with technical harmonization concern | WaSH Cluster | Sub WaSH Cluster | 2 weeks
Consolidate supply chain for NFI and any other equipment | WaSH Cluster | Sub WaSH Cluster | 2 weeks
Consolidate response capacity regarding funding available/needed, human resources, partners coverage, information management and identification of gaps | All WaSH actors | All WaSH actors | 3 weeks
Upgrade 3W tools to measure the response versus Sphere guidelines | WaSH Cluster |  | 3 weeks
Develop a proper briefing package for the arrival of new actors | WC IM |  | 1 month
Re-enforce cross-cutting issues as gender, children access, handicap,… | All partners |  | 1 month
Define early recovery phase in the approach | All partners | Sub WaSH Cluster | 1 month
Define a medium term (3 months) intervention strategy | WaSH Cluster | All partners | 1 month
Identify the most appropriate cluster coordination setting with government (co-leadership?) | WaSH Cluster |  | 1 month
Consolidate response team (cluster and partners) | All partners | Sub-cluster | 1 month
Conduct a WaSH base line survey | Sub WaSH Cluster | All partners | 2 weeks
Organize RECA assessment if not yet deployed | WaSH Cluster | RECA | 2 weeks
Identify and advocate for financial needs for next 3 months | WaSH Cluster |  | 3 weeks