## Cover
Annex 2 _ Sector Contingency Response Plans

## CRP
All Sector Contingency Response Plans (CRP) / Scenario: Cyclone in Rakhine
Sector/Cluster | Activity | Status |  |  | Due Date | Lead
|  | Completed | Ongoing | Not Started
Camp Management and Camp Coordination Cluster | Government plan on evacuation sites to be known by CCCM Cluster and wider humanitarian community |  | ü |  | n/a | CCCM Cluster Parther IOM
Camp Management and Camp Coordination Cluster | CCCM training for Government on post natural disaster settings, “principles and approaches” | ü |  |  | n/a | CCCM Cluster Parther IOM
Camp Management and Camp Coordination Cluster | Establish responsibilities and coordination mechanisms between the Government and CCCM partner agencies to coordinate effectively |  | ü |  | Aug. 2014 | CCCM Cluster
Camp Management and Camp Coordination Cluster | Monthly updated list online of Cluster participants (www.shelternficccmmyanmar.org) | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Every two months data/analysis on CCCM coverage (www.shelternficccmmyanmar.org) | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Updated site plans online for key/vulnerable IDP communities (www.shelternficccmmyanmar.org) | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Focal points for Camp Management assessments with awareness of | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Standards, shared wih partners
Camp Management and Camp Coordination Cluster | All partners aware of overall CCCM strategy, including cross-cutting issues | ü |  |  | n/a | CCCM Cluster
Camp Management and Camp Coordination Cluster | Collect and analyse information on populations likely to be more vulnerable |  | ü |  | Sept. 2014 | CCCM Cluster
Camp Management and Camp Coordination Cluster | Agree with Government and CCCM partner agencies on roles and responsibilities of Rakhine State Government versus Camp Management actors |  | ü |  | Aug. 2014 | CCCM Cluster
Camp Management and Camp Coordination Cluster | Agree on data management, data sharing mechanisms and protocols, rapid assessment tools and reporting formats | ü |  |  | n/a | CCCM Cluster
Early Recovery Sector (ER) | 3W matrix updated and circulated every quarter | ü |  |  | n/a | UNDP
Early Recovery Sector (ER) | Contact lists updated and circulated atleast twice a year | ü |  |  | n/a | UNDP
Early Recovery Sector (ER) | Identify ER focal points for joint assessments (includes identification and appointment of expert lead for comprehensive ER assessment) |  |  | ü | Sept. 2014 | UNDP
Early Recovery Sector (ER) | Organization of ER assessment team including SURGE capacity |  |  | ü | Sept. 2014 | UNDP
Early Recovery Sector (ER) | RRD capacity assessment for recovery coordination |  |  | ü | Sept. 2014 | UNDP
Early Recovery Sector (ER) | Work with RRD, sectors/clusters to identify priority recovery interventions and locations based on the assessment |  |  | ü | Sept. 2014 | UNDP
Early Recovery Sector (ER) | Support sectors/clusters integrate recovery within emergency response |  |  | ü | Sept. 2014 | UNDP
Early Recovery Sector (ER) | Support RRD to set-up coordination mechanism and initial training of RRD on recovery coordination and disaster management |  |  | ü | xxx | UNDP
Early Recovery Sector (ER) | Support RRD to maintain updated profile of partners (local and state) and government contacts |  |  | ü | xxx | UNDP
Early Recovery Sector (ER) | Support RRD to set-up information data base/MIS and train responsible personnel accordingly |  |  | ü | Sept. 2014 | UNDP
Early Recovery Sector (ER) | Convene donors for a round table discussion based on the rapid assessment. Strengthen engagement as time proceeds |  |  | ü | Sept. 2014 | UNDP
Early Recovery Sector (ER) | ER multi sector assessment tool developed and sector members trained |  |  | ü | 2014-07-01 | UNDP
Early Recovery Sector (ER) | Training to government counterparts, sector members and cluster/sector leads on conflict sensitivity |  |  | ü | Aug. 2014 | UNDP
Education in Emergencies (EiE) | RakhineEiE coordination mechanisms: agree and clarify roles and responsibilities of sector partners and members | ü |  |  | n/a | SCI, UNICEF
Education in Emergencies (EiE) | 3W and sector contact list: up to date and shared at least every month | ü |  |  | n/a | UNICEF
Education in Emergencies (EiE) | Map capacity of all implementing sector partners, including State Education Department (SED) and township education offices (TEOs). Include staff numbers and capacity (expertise and experience for assessment and response), supplies and systems (especially logistics and data) | ü |  |  | n/a | SCI, UNICEF
Education in Emergencies (EiE) | Pre-identify key operational areas of each EiE sector member for assessment and response based on current area of operation and capacity |  | ü |  | 2014-07-01 | UNICEF
Education in Emergencies (EiE) | Collect baseline data on existing education services in the planning area to guide assessment and response in case of emergency (Sector 3W for camps, SED data for rest) | ü |  |  | n/a | UNICEF
Education in Emergencies (EiE) | Agree/develop EiE assessment tools: EiE section of the multi-sector initial rapid assessment tool and a contextually-appropriate EiE specific needs assessment tool |  | ü |  | 2014-07-01 | National EiE Sector
Education in Emergencies (EiE) | Identify local partners where possible: local NGO/CSO working in education with potential to partnership in the event of disaster, particularly the remote areas |  |  | ü | 2014-07-01 | UNICEF and SCI
Education in Emergencies (EiE) | Agree standards and programme components appropriate to the context (to be further honed to the type of emergency). Ensure all sector partners are aware of and understand these and how to plan for and implement them (including organizing refresher sessions for education personnel if necessary, and possible) |  | ü |  | 2014-07-01 | National EiE Sector, SCI
Education in Emergencies (EiE) | Ensure joint preparedness planning with the other sectors/clusters, especiallyWaSH and Child Protection to ensure coherency between the different contingency plans |  | ü |  | 2014-07-01 | UNICEF
Education in Emergencies (EiE) | Conflict Sensitivity& DNH: If possible provide a joint refresher training forEiE sector partnersfield staff to ensure approach and principles are considered during response planning and implementation |  |  | ü | Sept. 2014 | UNICEF, National EiE Sector
Food Sector | Udpated contact list of sector participants shared at list twice per year | ü |  |  | n/a | WFP
Food Sector | Updated list of Rahkine State Government counterparts | ü |  |  | n/a | WFP
Food Sector | Sector stockpiles available in Rahkine State | ü |  |  | n/a | WFP
Food Sector | Focal points for joint assessments | ü |  |  | n/a | WFP
Food Sector | Training for joint assessment |  | ü |  | 2014-07-01 | WFP
Health Cluster | Mapping of partners, including UN agencies, MOH and NGOs. Where about and availability for What actions, 3-W mapping of partners and potential partners, including their logistic capacity |  |  |  | n/a | Health Cluster
Health Cluster | Identified focal points for joint assessments | ü |  |  | n/a | Health Cluster
Health Cluster | Strengthening of coordination mechanism among cluster partners and development of a joint advocacy mechanism. |  | ü |  | Aug. 2014 | Health Cluster
Health Cluster | Identification of facilities and referral mechanisms in potentially affected areas |  | ü |  | 2014-07-01 | Health Cluster
Health Cluster | Share with partners available WHO and national guidelines on treatment of communicable diseases and other diseases, including basic emergency obstetrics and new-born care, psycho-social support, treatment of geriatric diseases, revised IASC HIV guidelines and case confidentiality. |  | ü |  | 2014-07-01 | Health Cluster
Health Cluster | MRCS to share emergency response procedures among the health partners. Check lessons learnt from previous cyclone. |  |  | ü | 2014-06-01 | MRCS / WHO
Health Cluster | Share minimum initial service package (MISP) for primary health care (PHC), reproductive health (PH) and psychosocial support (PSS) in an emergency with humanitarian actors, health staff and relevant stakeholders | ü |  |  | n/a | WHO, UNFPA
Health Cluster | Strengthening early warning system and disease surveillance |  | ü |  | Sept. 2014 | Health Cluster
Health Cluster | Adapt generic tools (data collection, reporting formats) recommended by Global Health Cluster such as the ‘Rapid assessment matrix’ and standard tools (with reference to Sphere assessment tools and standards) |  | ü |  | Sept. 2014 | Health Cluster
Health Cluster | To agree the human resources for the emergency response team among Cluster partners |  | ü |  | 2014-07-01 | Health Cluster
Health Cluster | Collection of baseline data including Health, WaSH and Nutrition indicators |  | ü |  | Sept. 2014 | Health Cluster
Health Cluster | Pre-positioning and stock-piling of medical supplies and equipment including medicines and vaccines, hygiene and dignity kits, reproductive health kits and medication for treatment of trauma /acute /chronic diseases (ensure linkage with other sectors) |  | ü |  | 2014-07-01 | Health Cluster
Health Cluster | Centralize an interagency stock database of pre-positioned medical supplies including SHD's emergency supplies. |  | ü |  | 2014-07-01 | Health Cluster
Non Food Items Cluster | Establish responsibilities and coordination mechanisms between the Government and NFI partner agencies to coordinate effectively |  | ü |  | 2014-07-01 | NFI Cluster
Non Food Items Cluster | Monthly updated list online of Cluster participants (www.shelternficccmmyanmar.org) | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Every two months data/analysis on NFI coverage (www.shelternficccmmyanmar.org) | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Updated site plans online for key/vulnerable IDP communities (www.shelternficccmmyanmar.org) | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Focal points for joint assessments with awareness of NFI standards, shared wih partners and updated 3 times per year |  | ü |  | 2014-06-01 | NFI Cluster
Non Food Items Cluster | Clarify total NFI contigency supplies for entire Cluster, updated 3 times per year |  | ü |  | 2014-06-01 | NFI Cluster
Non Food Items Cluster | All partners aware of overall NFI strategy, including cross-cutting issues | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Collect and analyse information on populations likely to be affected, and identify likely scenarios and responses |  | ü |  | Sept. 2014 | NFI Cluster
Non Food Items Cluster | Agree with Government and NFI partner agencies on minimum NFI standards in-line with prioritised criteria | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Arrange procurement of contingency supplies, as required | ü |  |  | n/a | NFI Cluster
Non Food Items Cluster | Coordinate with transport agents to identify stanby capacities/quantities/delivery time for emergency NFI distributions |  |  | ü | 2014-06-01 | NFI Cluster
Non Food Items Cluster | Assess warehousing capacities against minimum agreed contingency requirements |  | ü |  | 2014-06-01 | NFI Cluster
Non Food Items Cluster | Agree on data management, data sharing mechanisms and protocols, rapid assessment tools and reporting formats | ü |  |  | n/a | NFI Cluster
Nutrition Sector | Updated contact list of sector participants in Rakhine shared at least twice per year | ü |  |  | n/a | UNICEF
Nutrition Sector | Focal points for joint assessments in Rakhine with sector expertise identified, shared with partners and updated twice per year |  |  |  | n/a | UNICEF
Nutrition Sector | Mapping (3W) of partners working in Rakhine, including UN agencies, MoH and I/NGOs | ü |  |  | n/a | UNICEF
Protection Sector | Maintain and update Protection working group, Child Protection and GBV sub-working groups contact lists at the Sittwe level | ü |  |  | n/a | UNHCR, UNFPA, UNICEF
Protection Sector | Consolidate and keep up to-date contacts of key focal points within line ministries at the state and township level | ü |  |  | n/a | UNHCR, UNICEF
Protection Sector | Ensure data protection and security protocols are in place for each protection-related case management agency, in case of evacuation of personnel |  |  | ü | 2014-06-01 | UNHCR, UNFPA
Protection Sector | Harmonize Child Protection Case Management Form and agree on a Child Protection Information Management System, Child Protection Information Managemetn Sistem (CPIMS) emergency template |  | ü |  | 2014-06-01 | UNICEF (SC)
Protection Sector | Initiate emergency GBV IMS: emergency intake forms and information sharing protocols |  | ü |  | 2014-06-01 | UNFPA, UNHCR
Protection Sector | Identify Protection WG, CP and GBV SWG members with relevant language and technical skills willing to take part in the inter-agency rapid assessment teams |  | ü |  | 2014-06-01 | UNHCR, UNFPA
Protection Sector | Disseminate the revised MIRA form and specific protection related questions/observations to theprotection actors and ensure that the assessment team members are familiar with the protection-related questionnaire. |  | ü |  | 2014-06-01 | UNHCR
Protection Sector | Develop and disseminate a protection action sheets (addressing Gender/GBV/CP/Elderly/Disabled issues) per sector to mitigate potential risks in the delivery of broader humanitarian assistance |  | ü |  | 2014-06-01 | UNHCR, UNICEF
Protection Sector | Develop and disseminate protection emergency ‘Toolkit’ to include safety audit tools, rapid assessment/focus group questions. Include guidance notes on child protection, GBV and main protection issues in emergencies. |  | ü |  | 2014-06-01 | UNHCR, UNFPA
Protection Sector | Disseminate CP Inter-Agency Minimum Standards |  |  | ü | 2014-06-01 | UNICEF
Protection Sector | Disseminate emergency GBV “service mapping” tool to confirm within 48 hours of crisis services that are still in place and accessible (taking the freedom of movement and bias factor, and inter-communal dynamic into account) |  | ü |  | 2014-06-01 | UNFPA
Protection Sector | Consolidate and keep updated protection-related items stockpiles (as per stock pile list) available in country |  | ü |  | 2014-06-01 | UNHCR, UNFPA
Protection Sector | Refresher training the protection actors on the use of the protection incident monitoring form |  | ü |  | 2014-06-01 | UNHCR
Protection Sector | Ensure Protection Sector level are briefed on Protection from Sexual Violence and Abuse (PSEA) and are able to inform communities on complaint mechanisms and immediate assistance |  | ü |  | 2014-06-01 | UNHCR , UNICEF
Protection Sector | Train women’s groups on “emergency” GBV response priorities and providing psychosocial first aid. |  | ü |  | 2014-06-01 | UNFPA, IRC, DRC
Shelter Cluster | Establish responsibilities and coordination mechanisms between the Government and shelter partner agencies to coordinate effectively |  | ü |  | 2014-07-01 | Shelter Cluster
Shelter Cluster | Monthly updated list online of Cluster participants (www.shelternficccmmyanmar.org) | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Every two months data/analysis on emergency/temporary shelter coverage (www.shelternficccmmyanmar.org) | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Updated site plans online for key/vulnerable IDP communities (www.shelternficccmmyanmar.org) | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Focal points for joint assessments with awareness of emergency shelter | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Clarify total emergencyshelter contigency supplies for entire Cluster, updated 3 times per year |  | ü |  | 2014-06-01 | Shelter Cluster
Shelter Cluster | All partners aware of overall shelter strategy, including types of emergency shelter intervention, minimum standards and cross-cutting issues | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Collect and analyse information on populations likely to be affected, and identify likely scenarios and responses |  | ü |  | Sept. 2014 | Shelter Cluster
Shelter Cluster | Arrange procurement of contingency supplies, as required | ü |  |  | n/a | Shelter Cluster
Shelter Cluster | Coordinate with transport agents to identify stanby capacities/quantities/delivery time for emergency distributions |  |  | ü | 2014-06-01 | Shelter Cluster
Shelter Cluster | Assess warehousing capacities against minimum agreed contingency requirements |  | ü |  | June 2014 | Shelter Cluster
Shelter Cluster | Agree on data management, data sharing mechanisms and protocols, rapid assessment tools and reporting formats | ü |  |  | n/a | Shelter Cluster
WASH Cluster | Public Information management system in place | ü |  |  |  | National WaSH Cluster /MIMU
WASH Cluster | Updated contact list of sector participants shared at least every month | ü |  |  |  | RakhineWC (RWC)
WASH Cluster | Updated 4W shared at monthly bases | ü |  |  |  | RWC
WASH Cluster | Define proper linkage with Government (Contact list, preliminary meeting,…) | ü
WASH Cluster | Share with partners the mechanism existing with Regional Emergnecy Cluster Adviser (RECA) and Global cluster for specific support activation | ü
WASH Cluster | Government plan on evacuation sites to be known by WaSH actors |  | ü |  | June 2014 | RWC/ACF
WASH Cluster | Update AWD 2013 contingency plan |  | ü |  | June 2014 | RWC/WHO
WASH Cluster | Cross-cutting issues identified, shared with partners and included in check-lists |  | ü |  | June 2014 | RWC
WASH Cluster | WaSH stockpiles available, updated at least 3 times per year and shared with partners, and supply chain identified for rapid procurement and delivery and storage | ü |  |  | n/a | All partners and UNICEF
WASH Cluster | Identification of specific contingency capacity of WaSH actors (staff, volume activity, volunteers…) | ü |  |  | n/a | RWC
WASH Cluster | Identification of flooding risk level for each actual working location |  |  | ü | June 2014 | RWC
WASH Cluster | Focal points for joint assessments with WaSH expertise identified, shared with partners and updated 3 times per year | ü |  |  | n/a | RWC
WASH Cluster | WaSH baseline on evacuation sites |  |  | ü | Sept.2014 | RWC/ACF
WASH Cluster | Ensure pre-positioning of equipment (water treatment, HK, sanitation…) |  | ü |  | July 2014 | All Partner and UNICEF
WASH Cluster | Minimum assistance package defined in the national preparedness WaSH plan shared | ü |  |  | n/a | NWC
WASH Cluster | Capacity building/training to partners on identified gaps provided |  |  | ü | July 2014 | RWC
WASH Cluster | Ensure water testing protocol for the actual WaSH response to be easily replicated |  | ü |  | June 2014 | WaSHWG
WASH Cluster | Ensure desludging protocol from the actual WaSH response to be easily replicated | ü |  |  | n/a | WaSHWG
WASH Cluster | Ensure update maps of road access | ü |  |  |  | MIMU
WASH Cluster | All emergency latrines to be decommissioned in IDP camps |  | ü |  | June 2014 | Focal NGO
WASH Cluster | Secure all sewage treatment station with proper drainage, and decommission unnecessary one | ü |  |  | n/a | Focal NGO
WASH Cluster | Desludging of all ¾ full latrines in IDP camps and all health structures |  | ü |  | July 2014 | Focal NGO
WASH Cluster | All water points in IDP camps have concrete apron |  | ü |  | July 2014 | Focal NGO
WASH Cluster | Upgrading drainage in IDP camps |  | ü |  | July 2014 | Focal NGO

## CCCM
CCCM Sector - Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilise camp management needs assessment team | CCCM Cluster | DRC, SCI, Solidarities, RI, LWF | 5 days (maximum) | Rakhine NFI, Shelter Clusters
If population relocated, assess camp management needs | CCCM Cluster | DRC, SCI, Solidarities, RI, LWF | 5 days (maximum) | Rakhine NFI, Shelter Clusters
Mobilise camp management needs assessment support from national level (as required) | CCCM Cluster | DRC, SCI, Solidarities, RI, LWF | 5 days (maximum) | Rakhine NFI, Shelter Clusters
Immediately after disaster
Mobilise camp management assessment team | CCCM Cluster | DRC, SCI, Solidarities, RI, LWF | 24 to 36hrs | Rakhine NFI, Shelter Clusters
Conduct rapid assessments of camp management needs of affected population, which can include security threats/risks, access to affected areas and logistical needs | CCCM Cluster | DRC, SCI, Solidarities, RI, LWF | 72hrs | Rakhine NFI, Shelter Clusters
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | CCCM Cluster | DRC, SCI, Solidarities, RI, LWF | 7 days | Rakhine NFI, Shelter Clusters
Organise daily coordination meeting in Yangon and Sittwe, which can include liaising with appropriate government counterpart at national and state level | CCCM Cluster | DRC, SCI, Solidarities, RI, LWF | 24 to 36hrs | Rakhine NFI, Shelter Clusters
Attend in Yangon and Sittwe ICC meeting | CCCM Cluster | UNOCHA | 24 to 48hrs | Sectors/Clusters
Within two weeks
Deploy additional staff from emergency rosters | CCCM Cluster | IOM | within 21 days
If appropriate, adjust plan/strategy | CCCM Cluster |  | within 28 days

## ER
Early Recovery Sector - Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Share updated 3W matrix and contact lists | UNDP | Sector partners | Immediately
Confirm stand by out of country and in country surge capacity for rapid deployment for assessments etc. | UNDP | Sector partners | 24hrs
Liaise with key government counterparts and begin early coordination | UNDP | Sector partners | 24hrs
Immediately after disaster
Convene first national level combined meeting between the ER sector and DRR working group | UNDP | Sector partners, DRR WG | 24hrs | Sectors/clusters DRR WG
Establish a coordinated contact with key government counterparts | UNDP
Activate surge deployment | UNDP
Work side by side with relevant government coordinating body, RRD, to plan and coordinate for disaster response for inclusion in Flash Appeals | UNDP | Sector partners | 24 to 36hrs
Support sectors/clusters to identify opportunities for recovery interventions | UNDP | Sector/Cluster | 24 to 36hrs
Rapid Assessment of impact on local governance arrangements and their capacity to coordinate and | UNDP | DDR WG | 48 hrs
manage emergency response
Convene first national level combined meeting between the ER sector and DRR working group | UNDP | Sector partners, DRR WG | 24 hrs | Sector/cluster, DRR WG
Activate surge deployment
Within two weeks
Convene first national level combined meeting between the ER sector and DRR working group | UNDP | Sector partners, DRR WG | 24hrs | Sectors/clusters, DRR WG
Establish a coordinated contact with key government counterparts
Activate SURGE deployment
Work side by side with relevant government coordinating body, RRD. to plan and coordinate for disaster response for inclusion in Flash Appeals | UNDP | Sector partners | 24 to 36hrs
Support sectors/clusters to identify opportunities for recovery interventions | UNDP | Sectors/Clusters | 24 to 36hrs
Rapid Assessment of impact on local governance arrangements and their capacity to coordinate and | UNDP | DDR WG | 48hrs
manage emergency response
Convene first national level combined meeting between the ER sector and DRR working group | UNDP | Sector partners,DRR WG | 24hrs | Sectors/clusters, DRR WG
Activate surge deployment

## Education
Education in Emergencies Sector - Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Update and share 3W and contact list with relevant partners | UNICEF | All relevant actors in Rakhine | On EW
Initiate agreed emergency coordination mechanisms with the sector partners, including SED, TEOs and other sector/cluster coordinators, through existing mechanisms | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | On EW | Sectors/Cluster, especially Child Protection, Shelter, WaSH
Check with all partners (including Government) that local EiE preparedness capacity is still valid – education stocks, education personnel (including teachers), pre-identified local NGO/CSO education partners, and update if necessary – and prime them for needs assessment | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | On EW | Education partners
Immediately after disaster
Convene first EiE Sector emergency meeting with available partners, including SED & TEOs and agree initiation of contingency plan (revising aspects if necessary). Agree regular meeting times, places and coordination responsibilities | UNICEF, SCI | SED, SCI, LWF, Plan, MRCS, CFSI | 24hrs
Request, compile and share any information already available on education services managed or supported by each organization - staff, structures, materials. (Continue this process throughout crisis expanding it in line with information available and transitioning into the regular sector sitrep later on) | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | 24 to 48hrs
Obtain initial information on potential damage to education personnel, structures and supplies through SEO, TEOs and implementing partners, using their existing education staff network (including liaisons, PTAs and community teachers). Starting draft EiE sector response plan based on this initial snapshot (to be updated by education information from MIRA – next point) | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | 24 to 48hrs | Information from all/any other sector
Attend ICC meetings to share information on the EiE sector’s initial needs and plans and priorities. Update OCHA 3Ws (Who does What Where) based on new reality and on an ongoing basis thereafter based on evolvingEiE response plans | UNICEF, SCI | SED, SCI, LWF, Plan, MRCS, CFSI | 24 to 48 hrs | Sector / clusters
Coordinate initial request for education supplies by partners from their respective in-country preparedness stocks, working with national EiE Sector Coordinator. (In addition encourage partners to submit purchase requests from their own agencies using available funding and collate these). | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | 48 to 72 hrs
Coordinate and support any request for rapid seed funding from pooled funding mechanisms (e.g. CERF and Myanmar Education Consortium (MEC) through the best placed organization (or the one lacking funding from its own internal emergency sources) |  | MEC, OCHA
MobilizeEiE sector members able to participate in the Multi-sector Initial Rapid Assessment (MIRA) and train on education section of tool (so they can guide other non-education personnel in team). | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | 72 hrs | Sector / clusters
Coordinate data processing and analysis of the education section of the MIRA. Share the analysis with the other sectors/clusters | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | 4 days | Sector /clusters
Use information from the MIRA to update and finalize initial sector response plans including which organization will do what where based on capacity and placement other sector activities. Use plans to finalize master concept note which agencies can adapt to fundraise for their respective areas. | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | 6 days | Sector/clusters
Within two weeks
Coordinate partner’s needs for education response surge capacity. Request information management support from the COs to effectively manage growing pool of information, demand for information for fundraising and proposals. | UNICEF, SCI | SED, TEOs SCI, LWF, Plan, MRCS, CFSI | 2 weeks
Coordinate ans support the preparation of a comprehensive joint education sector needs and damage assessments in the affected communities with the SED/TEO and through Head teachers and Parent Teacher Associations (PTA). | SEO, UNICEF, SCI | Sectorpartners | 2 weeks
Conduct a comprehensive joint education sector needs and damage assessments in the affected communities (with the SED/TEO and through Head teachers and PTAs) and collect and analyze the data. Share the analysis with the other sector/clusters. | SEO, UNICEF, SCI | Sectorpartners | 14 days +
Update plans and develop new proposals based on comprehensive education assessment data and analysis (to build on initial response plans and concept notes). SED to request additional education material at National level. | SEO, UNICEF, SCI | Sectorpartners | 14 days +

## Food
Food Sector - Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Obtain weather forecast from various sources | OCHA | UNDSS | Daily
Identify areas and population at risk | WFP | OCHA | Inmediately
Update Logistics capacity assessment | WFP |  | Inmediately
Update list of transporters (road and waterways) | WFP |  | Inmediately
Identify warehouses and storage places | WFP |  | Inmediately
Prepare emergency roaster of staff | WFP |  | Inmediately
Identify and maintain Emergency Response Kits (mobile offices) | WFP |  | Inmediately
Identify available emergency food stocks | WFP |  | Inmediately
Immediately after disaster
Participate in coordination meetings (UN/NGOs, govt) | OCHA | UN/NGO | 24hrs
Develop initial assessment plans (including logistics arrangements) | OCHA | UN/NGO | 24hrs
Deploy initial assessment team(s) (multi-sector/cluster) | OCHA, WFP | UN/NGO | 48hrs | Sectors/Clusters
Confirm beneficiary numbers and location | OCHA, WFP | UN/NGO | 48 to 72hrs | Sectors/Clusters
Check existing stocks (and additional supplies) | WFP | UN/NGO | 24hrs
Arrange transportation to disaster affected areas | WFP
Deliver HEBs | WFP |  | 72 hrs
Deploy food distribution team | WFP | UN/NGO | 48 to 72hrs
Food distribution | WFP | UN/NGO | 72hrs
Follow-up meetings (partners, govt) | OCHA | UN/NGO | 96hrs
Within two weeks
Plan more detailed assessment (Food security assessment), if required | WFP | UN/NGOs | Day 5
Deploy Food security assessment team | WFP | Sector partners | Day 6
Check available food stocks | WFP | Sector partners | Day 7
Deliver food or cash assistance | WFP | Sector partners | Day 9
Food distribution | WFP | Sector partners | Day 9
Follow-up meetings (partners, govt) | OCHA | UN/NGOs | Day 12 | Sectors/Clusters

## Health
Health Cluster - Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning (EW) Phase
Update and share 3W and contact list with relevant partners | Health Cluster | Cluster partners | 24 hours after EW | WaSH and Nutrition
Initiate emergency coordination mechanisms | Health Cluster | Cluster partners | 24 hours after EW | WaSH and Nutrition
Identify staff available for assessments | Health Cluster | Cluster partners | 24 hours after EW | WaSH and Nutrition
Check with all partners on the pre-positioning and stock-piling of medical supplies and equipment including medicines and vaccines, hygiene and dignity kits, reproductive health kits and medication for treatment of trauma /acute /chronic diseases | Health Cluster | Cluster partners | 24 hours after EW | WaSH and Nutrition
Immediately after disaster
Activate pre-identified assessment team | Health Cluster | Cluster partners | 2 days
Organize the health cluster meeting and sharing update information from assessment team | Health Cluster | Cluster partners | 3 days
Launch distribution of emergency supplies to the affected locations as per cluster stock-piling | Health Cluster | Cluster partners | 4 days
Re-establish disrupted health services through the establishment of static and/or mobile clinic (PHC, SRH, Nutrition) and eventually the setup of secondary care emergency facilities | Health Cluster | Cluster partners, UNICEF | 7 days | Nutrition
Activate communication, coordination system between field staff and based health facilities | Health Cluster | Cluster partners | 1 days
Implement Early Warning and Response System (EWAR) | Health Cluster | Cluster partners | 4 days
Within two weeks
Follow up the progress on the initial assessment | Health Cluster | Cluster partners | 2 weeks
Inter-cluster coordination with particular emphasis on Shelter,WaSH, Nutrition and Protection (set up of an effective inter-sectoral information management system) | Health Cluster | Cluster partners, UNICEF, UNHCR | 2 weeks | Shelter, WaSH, Nutrition, Protection
Provide measles vaccination to 9-months to 15-years old children relocated in the evacuation sites/IDP camps/host families | MoH, Health Cluster | Cluster partners, UNICEF | 2 weeks
To provide psychological first aid to the affected population | Health Cluster | Cluster partners, UNDP | 2 weeks | Early Recovery

## NFI
Non Food Items Cluster - Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilise NFI needs assessment team | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 5 days (maximum) | Shelter, CCCM & WaSH
If population relocated, NFI distribution in advance of event | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 5 days (maximum) | Shelter, CCCM & WaSH
Mobilise NFI needs assessment support from national level (as required) | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 5 days (maximum) | Shelter, CCCM & WaSH
Immediately after disaster
Mobiliseassessment team, which includes evaluation of need for intersector assessment, led by OCHA | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 24 to 36hrs | Shelter, CCCM & WaSH
Conduct rapid assessments of NFI needs for affected population, which can include security threats/risks, access to affected areas and logistical needs | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 72hrs | Shelter, CCCM & WaSH
Distribute NFI core kits from contingency stock and any additional relief items demanded due to weather conditions and/or emergency circumstances | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 72hrs | Shelter, CCCM & WaSH
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 7 days | Shelter, CCCM & WaSH
Organisedaily coordination meeting in Yangon and Sittwe, which can include liaising with appropriate government counterpart at national and state level | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 24 to 36hrs | Shelter, CCCM & WaSH
Attend in Yangon and Sittwe ICC meeting | NFI Cluster | OCHA | 24 to 48hrs | Sector/Cluster
Within two weeks
Initiate procurement to supplement deliveries if initial distrbutionsinadquate | NFI Cluster | DRC, SCI, Solidarities, RI & LWF | 7 to 10 days
Deploy additional staff from emergency rosters | NFI Cluster | IFRC | 21 days
If appropriate, adjust plan/strategy | NFI Cluster | - | 28 days

## Nutrition
Nutrition Sector Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Verify existing stocks of essential supplies including RUTF, fortified nutritional products including blended food, and micronutrient supplements and identify resources for gaps | UNICEF | National Nutrition Centre (NNC/MoH), Myanmar Nutrition Technical Network (MNTN) | 3 days | Food, Health
Strengthen/confirm existing coordination mechanisms or, if unavailable, create them in collaboration with national and local authorities to ensure that the humanitarian response is timely and coordinated, and that it conforms to humanitarian principles and agreed-upon standards and benchmarks. | UNICEF | NNC/MoH, MNTN | 5 days | Food, Health
Immediately after disaster
Take part in inter-agency coordination at Rakhine level | UNICEF | NNC/MoH, MNTN | 24hrs
Ensure and establish effective coordination mechanism among nutrition partners in Rakhine | UNICEF | NNC/MoH, MNTN | 24hrs
Undertake a multi-sectoral rapid assessment in affected townships in Rakhine, including key priority information for nutrition | UNICEF | MNTN | 48 to 72hrs and within 1 to 2 weeks | Food, Health, WaSH
Within two weeks
Share information on results of rapid assessments with relevant stakeholders at State and national level and decide on further actions | UNICEF | NNC/MoH, MNTN | 7 days | Food, Health, WaSH
Organize coordination meeting, which can include liaising with appropriate government counterpart at national, Rakhine State and township level | UNICEF | NNC/MoH, MNTN | 7 days | Food, Health, WaSH
Ensure appropriate emergency nutrition response based on the needs of affected population in Rakhine. Response should follow sector/cluster responsibility and national/global humanitarian standards/guidelines | UNICEF | NNC/MoH, MNTN | 2 weeks | Food, Health, WaSH
Consult with the affected communities of Rakhine for development and implementation of programme communication, and include relevant and evidence-based nutrition messages in all programme communication activities. | UNICEF | NNC/MoH, MNTN | 2 weeks | C4D
If necessary, deploy additional staff from emergency rosters to affected areas of Rakhine | UNICEF | NNC/MoH, MNTN | 2 weeks
Nutrition sector/cluster identifies needs and financial resources required for activities among nutrition partners operating in Rakhine | UNICEF | NNC/MoH, MNTN | 2 weeks | Food, Health, WaSH
Support the formulation of draft appeals involving all relevant partners operating in Rakhine | UNICEF | NNC/MoH, MNTN | 2 weeks | Food, Health, WaSH

## Protection
Protection Sector Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilise assessment team / team members to participate in the initial multi sector rapid assessment | UNHCR | UNICEF, UNFPA, DRC | 3 days | Sectors/clusters
Update and share 3W and contact list with relevant partners | UNHCR | UNICEF, UNFPA | 3 days
Immediately after disaster
Mobilise assessment team / team members to participate in the initial multi sector rapid assessment | UNHCR | UNICEF, UNFPA, DRC | Immediate | Sectors/clusters
Activate response teams from the Protection Sector national standby emergency list (GBV emergency response teams, family separation screening teams, etc) | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | Immediate | Health , CCCM
Organise coordination meetings with relevant sector members and attend inter-sector coordination meetings | UNHCR | Protection WG. CP and GBV SWG | 24 to 36hrs | Shelter, CCCM &WaSH
Mobilise assessment team / team members to participate in the initial multi sector rapid assessment | UNHCR | UNICEF, UNFPA, DRC | Immediate | Sectors/clusters
Within two weeks
Conduct technical protection assessment and safety audits (to identify and mitigate additional risks across sectors) | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week | WaSH, Shelter, CCCM, Health and Food
Deploy response teams from the Protection WG (GBV emergency response teams, family separation screening teams, etc) | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week | Sectors/clusters
Map main protection issues and provide and assist solutions, based on the available, functioning services. | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week | Sectors/clusters
Map main protection issues and provide for and assist solutions | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 to 2 weeks | Sectors/clusters
Map available services for GBV response | UNFPA
Conduct tracing and family reunification for Unaccompanied and Separated Children (UASC) & referral to interim care | UNICEF |  | 1 week
Conduct tracing and family reunification for elderly and persons with disabilities | UNHCR | MRCS, ICRC | 1 week | WaSH, Shelter, CCCM
& Health
Reactivate the referral and management system (including GBV and CP) | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week | Health, Food, Nutrition, CCCM, NFI
Establish child friendly spaces and outreach in host communities and in locations of displacement/relocation | UNICEF | SAVE, DRC | 1 week | CCCM, GBV
Establish safe spaces and outreach for women, girls and survivors of GBV in locations of displacement/relocation | UNFPA | IRC | 1 week | CCCM, Child Protection
Distribute protection related items as needed | UNHCR, UNICEF, UNFPA | Protection WG, CP and GBV SWG | 1 week | CCCM, Health

## Shelter
Shelter Cluster Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilise emergency shelter needs assessment team | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 5 days (maximum) | NFI, CCCM & WaSH
If population relocated, emergency shelter distribution in advance of event | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 5 days (maximum) | NFI, CCCM & WaSH
Mobilise emergency shelter needs assessment support from national level (as required) | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 5 days (maximum) | NFI, CCCM & WaSH
Immediately after disaster
Mobiliseassessment team, which includes evaluation of need for intersector assessment, led by OCHA | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 24 to 36hrs | NFI, CCCM & WaSH
Conduct rapid assessments of emergency shelter needs for affected population, which can include security threats/risks, access to affected areas and logistical needs | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 72hrs | NFI, CCCM & WaSH
Distribute emergency shelter from contingency stock | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 72hrs | NFI, CCCM & WaSH
Share information on results of rapid assessments with relevant stakeholders and decide on further actions | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 7 days | NFI, CCCM & WaSH
Organisedaily coordination meeting in Yangon and Sittwe, which can include liaising with appropriate government counterpart at national and state level | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 24 to 36hrs | NFI, CCCM & WaSH
Attend in Yangon and Sittwe ICC meeting | Shelter Cluster | OCHA | 24 to 48hrs | Sectors/Clusters
Within two weeks
Initiate procurement to supplement deliveries if initial distrbutionsinadquate | Shelter Cluster | DRC, SCI, Solidarities, RI, LWF & MRF | 7 to 10 days
Deploy additional staff from emergency rosters | Shelter Cluster | IFRC | 21 days
If appropriate, adjust plan/strategy | Shelter Cluster |  | 28 days

## WASH
WASH Cluster Contingency Response Plan (CRP) / Scenario: Cyclone in Rakhine
Activity | Lead | Other Organizations | Timeline | Links with other sectors
Early Warning Phase
Mobilize assessment team set up | Rakhine WaSH Cluster | Pre-listed | Immediately | OCHA
Mobilize Nationa WaSH Cluster team for field support | National WaSH Cluster | Pre-listed | Immediately
Pre-distribution of water reagent for water purification | Rakhine WaSH Cluster | All partners | Immediately
Hygiene promotion team of partners re-enforced specific messages on good practices in such events | Rakhine WaSH Cluster | All partners | Immediately
If population relocated, Hygiene Kit distribution mechanism set up for reactive distribution for most vulnerable, in evacuation center straight after the events | Rakhine WaSH Group | All partners | Immediately
Immediately after disaster
Mobilize assessment team set up and evaluate assessment possibility for intersectorialassessment lead by OCHA | Rakhine WaSH Cluster | Pre-listed | 24hrs.
Organize a specific daily coordination meeting in Yangon and Sittwe | National and Rakhine WaSH Clusters | WaSH partners | Daily
Liaise with the appropriate governmental counterpart at national and state level | National and Rakhine WaSH Clusters
National Cluster and Rakhine Cluster participates into ICC meeting in Yangon and Sittwe and keep inform WaSH partners | National WaSH Cluster | OCHA |  | Sectors/Clusters
WaSH Cluster keeps close liaison with OCHA for update information | National and Rakhine WaSH Clusters | OCHA | Continous
WaSH Cluster share any relevant information with MIMU/OCHA | Rakhine WaSH Cluster |  |  | OCHA/MIMU
WaSH Cluster share assessment findings with partners | Rakhine WaSH Cluster
Liaise with OCHA/MIMU for mapping of needs | Rakhine WaSH Cluster | MIMU
Production of regular Wash Situation report and minutes meeting | Rakhine WaSH Cluster |  | Every 2nd day
Close link with either UNHCR or IOM on situation on evacuation sites | National WaSH Cluster | UNHCR/IOM |  | UNHCR/IOM
Mobilize stock available and define a supply process with UNICEF and other agencies from Yangon | National WaSH Cluster | UNICEF | 3 days | Logistics
Identify partners to support distribution of Hygiene Kit and to deploy first WaSH support | Rakhine WaSH Cluster | Concerned organizations | 3 days
Contact UNICEF (stand by agreement) and OCHA on resource mobilization for WaSH needs | National WaSH Cluster | UNICEF/OCHA | 3 days
Communicate with RECA on preliminary analysis, needs and potential foreseen support needed | National WaSH Cluster | RECA | 3 days
Keep informed WaSH partners onmobilization of funds and donors support to the response | National WaSH Cluster | Cluster partners | Continous
Evaluate and deploy first water supply possibility for affected population and evaluate overall response cost in respect of technical standard pre-defined | National WaSH Cluster | Rakhine WaSH Cluster and partners | 5 days max
Supply emergency sanitation equipment and define first response possible and evaluate overall response cost in respect of technical standard pre-defined | National WaSH Cluster | RWC and partners | 5 days max.
Recruitment of additional Cluster staff to support the team in the affected areaorcoordination at national level | UNICEF | Rakhine WaSH Cluster | 1 week
Daily update of 3W, including capacity response | Rakhine WaSH Cluster |  | Daily
Monitoring of NFI supply | Rakhine WaSH Cluster | Implementing partners | Weekly
Within two weeks
Consolidate the geographical positioning of each WaSH actors | Rakhine WaSH Cluster |  | 2 weeks
Consolidate the most appropriate technical response, with technical harmonization | Rakhine WaSH Cluster |  | 2 weeks
Consolidate supply chain for Hygiene Kits and any other equipment | National WaSH Cluster | Rakhine WaSH Cluster | 2 weeks
Top-up the response capacity with concern of funding available/needed, HR needs, partners coverage, systematization of the response, consolidation of information management and gap identification | National and Rakhine WaSH Clusters | WaSH partners | 3 weeks
Upgrade 3W tools to measure the response coverage versus Sphere guide lines | National WaSH Cluster |  | 3 weeks
Develop a proper briefing package for the arrival of new actors | WaSH Cluster IM |  | 1 month
Re-enforce cross-cutting issue as gender, children access, handicap,… | National WaSH Cluster | WaSH partners | 1 month
Prepare early recovery phase in approach | National WaSH Cluster | WaSH partners | 1 month
Define a medium term (3 months) intervention strategy | National WaSH Cluster | WaSH partners | 1 month
Identify the most appropriate cluster coordination setting with government (co-leadership?) | Rakhine WaSH Cluster |  | 1 month
Consolidate response team (cluster and partners) | National WaSH Cluster | Rakhine WaSH Cluster | 1 month
Support any logistic WaSH challenges with relevant agency (WFP if defined logistic cluster) | National WaSH Cluster | Rakhine WaSH Cluster |  | Logistics
Conduct a wash base line survey | Rakhine WaSH Cluster | WaSH partners | 2 weeks
Organize RECA assessment if not yet deployed | National WaSH Cluster | RECA | 2 weeks
Identify and advocate for financial needs for next 3 months | National WaSH Cluster |  | 3 weeks