| Research Terms of Reference Khost Earthquake Damage Assessment AFG2207 Afghanistan |  |
| --- | --- |
| June 2022 Version 1.0 |  |

# Executive Summary

| Country of intervention | Afghanistan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Type of Emergency | X | Natural disaster | □ | Conflict |  |  | □ | Other (specify) |  |
| Type of Crisis | □ | Sudden onset | □ | Slow onset |  |  | □ | Protracted |  |
| Mandating Body/ Agency | ES/NFI Cluster |  |  |  |  |  |  |  |
| IMPACT Project Code | 02FAK/02ARI |  |  |  |  |  |  |  |
| Overall Research Timeframe (from research design to final outputs / M&E) | 26/06/2022 to 21/07/2022 |  |  |  |  |  |  |  |
| Research Timeframe Add planned deadlines (for first cycle if more than 1) | 1. Pilot/ training: 02/07/2022 |  |  |  | 6. Preliminary presentation: 17/07/2022 |  |  |  |
|  | 2. Start collect data: 03/07/2022 |  |  |  | 7. Outputs sent for validation: 15/07/2022 |  |  |  |
|  | 3. Data collected: 09/07/2022 |  |  |  | 8. Outputs published: 18/07/2022 |  |  |  |
|  | 4. Data analysed: 12/07/2022 |  |  |  | 9. Final presentation: 19/07/2022 |  |  |  |
|  | 5. Data sent for validation: 12/07/2022 |  |  |  |  |  |  |  |
| Number of assessments | X | Single assessment (one cycle) |  |  |  |  |  |  |
|  | □ | Multi assessment (more than one cycle) |  |  |  |  |  |  |
| Humanitarian milestones Specify what will the assessment inform and when e.g. The shelter cluster will use this data to draft its Revised Flash Appeal; | Milestone |  |  |  | Deadline |  |  |  |
|  | □ | Donor plan/strategy |  |  | _ _/_ _/_ _ _ _ |  |  |  |
|  | □ | Inter-cluster plan/strategy |  |  | _ _/_ _/_ _ _ _ |  |  |  |
|  | X | Cluster plan/strategy |  |  | 17/07/2022 |  |  |  |
|  | □ | NGO platform plan/strategy |  |  | _ _/_ _/_ _ _ _ |  |  |  |
|  | □ | Other (Specify): |  |  | _ _/_ _/_ _ _ _ |  |  |  |
| Audience Type & Dissemination Specify who will the assessment inform and how you will disseminate to inform the audience | Audience type |  |  |  | Dissemination |  |  |  |
|  | X Strategic □ Programmatic □ Operational □ [Other, Specify] |  |  |  | □ General Product Mailing (e.g. mail to NGO consortium; HCT participants; Donors) X Cluster Mailing (Education, Shelter and WASH) and presentation of findings at next cluster meeting X Presentation of findings (e.g. at HCT meeting; Cluster meeting) X Website Dissemination (Relief Web & REACH Resource Centre) □ [Other, Specify] |  |  |  |
| Detailed dissemination plan required | □ | Yes |  |  | X | No |  |  |
| General Objective | In Coordination with the ES/NFI Cluster, REACH will develop a Household Building and Damage Assessment (HBDA) tool to conduct a representative assessment of damaged buildings in six South Eastern Districts affected by the June 2022 Khost Earthquake, in order to understand the overall scope and impact of damage caused to shelter and key infrastructure, in order to inform advocacy for shelter repair and reconstruction in the affected area. |  |  |  |  |  |  |  |
| Specific Objective(s) | - Identify the key services, including health centres, schools, shops, and public builsings damaged by the earthquake, including both the buidling’s structural integrity and the functionality of the services provided in the building. - Understand the scope of the damage to hosuehold shelters in the six districts most affected by the earthquake, including the level of damage and repairs needed. - Estimate the overall caseload, repairs needed, and likely overall costs in terms of damaged shelters in the six most affected districts. |  |  |  |  |  |  |  |
| Research Questions | - What key services were impacted by the earthquake, and how have they been damaged? - How have the buildings of key services been damaged, and what is needed to repair them? - What level of damage have household shelters sustained, and what repairs are needed to be made, or new shelters constructed? - How do the patterns of damage vary, depending upon the proximity to the epicentre? - What is the overall caseload in terms of affected buildings and households? - How much will be needed in terms of money and resources to address the overall damage caused by the earthquake? |  |  |  |  |  |  |  |
| Geographic Coverage | 14 Districts: Khost Province: Spera, Shumal, Matun, Mandozayi, Tani, Nadirshakot, Gurbuz Paktia Province: Shawak, Zadran Paktitka Province: Gyan, Barmal, Urgan, Siruk, Nika |  |  |  |  |  |  |  |
| Secondary data sources | - ALCIS, Afghanistan Earthquake Support Webmap, June 2022 - UNOCHA, Afghanistan: Flash Update #1, Earthquake in Paktitka and Khost Provinces, Afghanistan, 22 June 2022 - UNOCHA, Afghanistan: Flash Update #2, Earthquake in Paktitka and Khost Provinces, Afghanistan, 23 June 2022 - Conseil De L'Europe, European Macroeseismic Scale 1998, Cahiers du Centre Europeen de DEudynamique et de Seismologie, Volume 15 - UNDP, Household Building and Damage Assessment: Guidance Note, December 2019 |  |  |  |  |  |  |  |
| Population(s) | □ | IDPs in camp |  |  | □ | IDPs in informal sites |  |  |
| Select all that apply | □ | IDPs in host communities |  |  | □ | IDPs [Other, Specify] |  |  |
|  | □ | Refugees in camp |  |  | □ | Refugees in informal sites |  |  |
|  | □ | Refugees in host communities |  |  | □ | Refugees [Other, Specify] |  |  |
|  | □ | Host communities |  |  | □ | [Other, Specify] |  |  |
| Stratification Select type(s) and enter number of strata | □ | Geographical #:_ _ _ Population size per strata is known? □ Yes □ No | □ | Group #: _ _ _ Population size per strata is known? □ Yes □ No |  |  | □ | Distance from Epicentre #: 0-15km >15 – 30 km >30- 45km >45 - 60km Population size per strata is known? X Yes □ No |
| Data collection tool(s) | X | Structured (Quantitative) |  |  | □ | Semi-structured (Qualitative) |  |  |
|  | Sampling method |  |  |  | Data collection method |  |  |  |
| Structured data collection tool # 1 Select sampling and data collection method and specify target # interviews | □ Purposive □ Probability / Simple random X Probability / Stratified simple random □ Probability / Cluster sampling □ Probability / Stratified cluster sampling □ [Other, Specify] |  |  |  | X Key informant interview (Target #): 685 □ Group discussion (Target #):_ _ _ _ _ X Household interview (Target #): 772 □ Individual interview (Target #):_ _ _ _ _ □ Direct observations (Target #):_ _ _ _ _ □ [Other, Specify] (Target #):_ _ _ _ _ |  |  |  |
| Target level of precision if probability sampling | 95% level of confidence |  |  |  | 5+/- % margin of error |  |  |  |
| Data management platform(s) | X | IMPACT |  |  | □ | UNHCR |  |  |
| Expected ouput type(s) | □ | Situation overview #: _ _ | □ | Report #: _ _ |  |  | X | Profile #: _ _ |
|  | □ | Presentation (Preliminary findings) #: _ _ | □ | Presentation (Final) #: _ _ |  |  | □ | Factsheet #: 1 |
|  | □ | Interactive dashboard #:_ | □ | Webmap #: _ _ |  |  | X | Map #: 1 |
|  | □ | [Other, Specify] #: _ _ |  |  |  |  |  |  |
| Access | □ | Public (available on REACH resource center and other humanitarian platforms) |  |  |  |  |  |  |
|  | □ | Restricted (bilateral dissemination only upon agreed dissemination list, no publication on REACH or other platforms) |  |  |  |  |  |  |
| Visibility Specify which logos should be on outputs | REACH [By default unless specified otherwise] |  |  |  |  |  |  |  |
|  | Donor: UNHCR |  |  |  |  |  |  |  |
|  | Coordination Framework: ES/NFI Cluster |  |  |  |  |  |  |  |
|  | Partners: N/A |  |  |  |  |  |  |  |

# Rationale

  - Background

On 22 June, a 5.9 earthquake struck in Spera District of Khost Province on the border of Pakistan, heavily affecting 14 districts of Afghanistan’s Southeast Region.  As of 27 June, an estimated 1,039 people have died, 2,949 have been injured, and 4,500 houses have been partially or fully damaged in Paktika and Khost Provinces. In June, an estimated 1,900 homes in districts near the epicentre were destroyed. one of the most remote parts of Afghanistan. While NGOs have already begun to respond across the affected area, and key gaps have been identified, the full scope of the damage across the area, as well as the state of key public infrastructure, remains unclear.

Intended impact

In Coordination with the Emergency Shelter and Non-Food Items Cluster, REACH will conduct a rapid Household Building and Damage Assessment of both household shelters and key infrastructure in the affected area. This assessment will provide a full understanding of the scope of the damage, as well as the overall needs in terms of building and shelter repair. This will allow the Cluster to have a full understanding of the total impact of the earthquake, in terms of damage to buildings and overall disruption of services. When combined with population figures, this will provide both a baseline for the overall damage scope, and will also provide an advocacy tool for funding and coordination.

# Methodology

  - Methodology overview

For the assessment, REACH designed a single, Household Building and damage assessment tool, that can be used in 2 separate methodologies as part of a mixed methods approach. The first methodology will assess households, and the second methodology will assess key services, including health centres, education facilities, and market shops. Households will be assessed using a representative household methodology, according to Modified Mercalli Intensity (MMI) impact shake zones identified by USGS and demarcated by UNOSAT. In each region, households will be sampled at a 95% confidence and 7% margin of error. In addition, additional, “top up” interviews will be conducted so that a 95/7 sample will be available for four of the most affected districts, Barmal, Giyan, Spera, and Tani. A stratified cluster sampling approach using population estimated data from worldpop and a modified version of UNOCHA’s village list will be used to ensure a more rapid data collection.

Key services will be assessed using a purposive sampling methodology, taken from key services identified by Cluster lists and REACH’s previous Humanitarian Situation Monitoring (Formerly known as, “Hard To Reach”) Research Cycle. REACH will use Cluster lists of health and education facilities from the Health and Education Clusters, respectively. Lists of markets will come from REACH’s Humanitarian Situation Monitoring (HSM) assessment, which maps key services across all districts in Afghanistan.

Each methodology will be used to answer the following Research Questions:

- What key services were impacted by the earthquake, and how have they been damaged?

- How have the buildings of key services been damaged, and what is needed to repair them?

- What level of damage have household shelters sustained, and what repairs are needed to be made, or new shelters constructed?

- How do the patterns of damage vary, depending upon the proximity to the epicentre?

- What is the overall caseload in terms of affected buildings and households?

  - Population of interest

Household shelters affected by the earthquake are located within the Modified Mercalli Intensity (MMI) (4.5 – 6.5) shack zones of the Khost earthquake that happened on 22 June 2022. We will get representative samples from Spera and Tani of Khost province and Giyan, and Barmal districts of Paktika province which are affected the most due to that incident.

| Estimated household population in the earthquake-affected area |  |  |
| --- | --- | --- |
| X | disaggregation | Population |
| 1 | Ring1 | 3,523 |
| 2 | Ring2 | 33,249 |
| 3 | Ring3 | 59,149 |
| 4 | Barmal | 4,043 |
| 5 | Giyan | 6,071 |
| 6 | Spera | 4,771 |
| 7 | Tani | 12,169 |
| 8 | all | 95,921 |

Services infrastructure of health and education which are in the same abovementioned earthquake shake zones and their information would be obtained from health and education clusters respectively.

Major markers which are in the same shake zones and their list will be obtained from the Human Situation Monitoring Data.5

  - Secondary data review

In this section, we obtain the educations and health facilities list from their respective clusters, and we will survey all of those facilities located in the earthquake-affected area. For market assessment, we reviewed Humanitarian Situation Monitoring (HSM) data and will survey all major markets which are in the affected area. For determining the sample size in each of those districts, we used an estimated population of WorldPop data and used the OCHA settlement list to prepare the household sampling frame.

  - Primary Data Collection

- REACH will collect data, using the HBDA tool, from household representative who live in the earthquake shake zone of MMI (4.5 - 6.5). After stratified by districts, household will be randomly selected by the enumerators. Through this means, REACH aims to collect data on the level and extent of damage that household shelters get inflected by the earthquake. REACH intends to train 31 enumerators to conduct training of enumerators for one day in Gardiz capital of Paktya province at the REACH Office.

| Representative Household Sample Composition |  |  |  |  |
| --- | --- | --- | --- | --- |
| Province | Sample size | District | Sample size | MMI |
| Khost | 550 | Spera | 277 | 5.0 – 6.5 |
|  |  | Tani | 273 | 4.5 – 6.0 |
| Paktika | 580 | Barmal | 275 | 4.5 – 5.5 |
|  |  | Giyan | 305 | 5.0 – 6.0 |
| Grand Total |  |  | 1,130 |  |

| Health Facilities Sample frame |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Province | Sample size | District | Sample size |  | MMI |  |
| Paktika | 19 | Barmal | 3 |  | 4.5 – 5.5 |  |
|  |  | Giyan | 4 |  | 5.0 – 6.0 |  |
|  |  | Urgun | 5 |  | 4.5 – 5.0 |  |
|  |  | Ziruk | 4 |  | 5.0 – 5.5 |  |
|  |  | Nika | 3 |  | 4.5 – 5.0 |  |
| Paktya | 2 | Zadran | 2 |  | 4.5 |  |
| Khost | 91 | Matun (khost) | 23 |  | 4.5 |  |
|  |  | Mandozayi | 30 |  | 4.5 – 5.0 |  |
|  |  | Gurbuz | 7 |  | 4.5 |  |
|  |  | Nadir shah kot | 5 |  | 4.5 – 5.0 |  |
|  |  | Shamul | 4 |  | 4.5 – 5.0 |  |
|  |  | Spera | 7 |  | 5.0 – 6.5 |  |
|  |  | Tani | 15 |  | 4.5 – 6.0 |  |
| Total |  |  |  | 112 |  |  |  |

| Education facility sampling frame |  |  |  |  |
| --- | --- | --- | --- | --- |
| Province | Sample size | Districs | Sample Size | MMI |
| Khost | 253 | Gurbuz | 19 | 4.5 |
|  |  | Mandozayi | 41 | 4.5 – 5.0 |
|  |  | Matun (khost) | 98 | 4.5 |
|  |  | Nadir shah kot | 13 | 4.5 – 5.0 |
|  |  | Shamul | 18 | 4.5 – 5.0 |
|  |  | Spera | 18 | 5.0 – 6.5 |
|  |  | Tani | 46 | 4.5 – 6.0 |
| Paktika | 127 | Barmal | 9 | 4.5 – 5.5 |
|  |  | Giyan | 14 | 5.0 – 6.0 |
|  |  | Nika | 15 | 4.5 – 5.0 |
|  |  | Sar rawzah | 1 | 4.5 |
|  |  | Urgun | 66 | 4.5 – 5.0 |
|  |  | Zadran | 2 | 4.5 |
|  |  | Ziruk | 20 | 5.0 – 5.5 |
| Total | 380 |  | 380 |  |

| Major Market Sampling frame |  |  |  |  |
| --- | --- | --- | --- | --- |
| Province | Sample size | District | Sample size | MMI |
| Paktika | 4 | Giyan | 1 | 5.0 – 6.0 |
|  |  | Urgun | 1 | 4.5 – 5.0 |
|  |  | Ziruk | 1 | 5.0 – 5.5 |
|  |  | Nika | 1 | 4.5 – 5.0 |
| Khost | 29 | Matun (khost) | 1 | 4.5 |
|  |  | Mandozayi | 15 | 4.5 – 5.0 |
|  |  | Gurbuz | 2 | 4.5 |
|  |  | Nadir shah kot | 2 | 4.5 – 5.0 |
|  |  | Tani | 9 | 4.5 – 6.0 |
| Total |  |  | 33 |  |

- Additionally, in order to have representative samples for each of highly affected districts (Spera, Tani, Barmal and Giyan), REACH will conduct an extra 318 interviews, utilizing stratified random sampling in each of these districts.

  - Data Processing & Analysis

Data that will be collected by the REACH enumerators will be checked on a daily basis in accordance with IMPACT Data Cleaning Minimum Standards Checklist. The collected data will be processed and analysed using a customized script in R. Then, data, including raw and processed data along with analysis will be shared with IMPACT headquarters for review and validation. Analysed data, after HQ endorsement, will be used in the factsheet and presentation of key findings. Finally, factsheet, presentation and the dataset will be published on REACH Resource Centre and will be shared with ES/NFI Cluster and partners.

# Key ethical considerations and related risks

The proposed research design meets / does not meet the following criteria:

| The proposed research design… | Yes/ No | Details if no (including mitigation) |
| --- | --- | --- |
| … Has been coordinated with relevant stakeholders to avoid unnecessary duplication of data collection efforts? | Yes |  |
| … Respects respondents, their rights and dignity (specifically by: seeking informed consent, designing length of survey/ discussion while being considerate of participants’ time, ensuring accurate reporting of information provided)? | Yes |  |
| … Does not expose data collectors to any risks as a direct result of participation in data collection? | Yes |  |
| … Does not expose respondents / their communities to any risks as a direct result of participation in data collection? | Yes |  |
| … Does not involve collecting information on specific topics which may be stressful and/ or re-traumatising for research participants (both respondents and data collectors)? | Yes |  |
| … Does not involve data collection with minors i.e. anyone less than 18 years old? | Yes |  |
| … Does not involve data collection with other vulnerable groups e.g. persons with disabilities, victims/ survivors of protection incidents, etc.? | Yes |  |
| … Follows IMPACT SOPs for management of personally identifiable information? | Yes |  |

# 5. Roles and responsibilities

Table 3: Description of roles and responsibilities

| Task Description | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Research design | Assessment Officer | Research Manager | Project Manage, Country Coordinator | ES/NFI Cluster |
| Supervising data collection | Senior Project Officer | Project Manager | Research Manager | Country Coordinator |
| Data processing (checking, cleaning) | Database Officer | Assessment Officer | Database Manager | Research Manager, Project Manager |
| Data analysis | Database Officer | Assessment Officer | Database Manager | Research Manager, Project Manager |
| Output production | Assessment Officer | Research Manager | IMPACT Research Review Unit | ES/NFI Cluster, Country Coordinator |
| Dissemination | Assessment Officer | Research Manager | Country Coordinator | ES/NFI Cluster |
| Monitoring & Evaluation | Assessment Officer | Research Manager | Country Coordinator | IMPACT Research Review Unit |
| Lessons learned | Assessment Officer | Research Manager | Programme Manager, Database Manager | Country Coordinator |

Responsible: the person(s) who executes the task

Accountable: the person who validates the completion of the task and is accountable of the final output or milestone

Consulted: the person(s) who must be consulted when the task is implemented

Informed: the person(s) who need to be informed when the task is completed

NB: Only one person can be Accountable; the only scenario when the same person is listed twice for a task is when the same person is both Responsible and Accountable.

# Data Analysis Plan

Please See attached Document.

# 6. Data Management Plan

| Administrative Data |  |
| --- | --- |
| Research Cycle name | AFG2207 |
| Project Code | 02FAK (IMPACT Code 02AVO) |
| Donor | UNHCR/BHA |
| Project partners | ES/NFI Cluster |

| Research Contacts | Ari Weiss, ari.weiss@reach-initiative.org Karim Mirzad, karim.mirzad@reach-initiative.org |  |
| --- | --- | --- |
| Data Management Plan Version | Date: 28/06/2022 | Version:1.0 |

| Related Policies |  | IMPACT PII |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Documentation and Metadata |  |  |  |  |  |  |  |  |  |  |  |
| What documentation and metadata will accompany the data? Select all that apply |  | X | Data analysis plan |  |  |  | X |  | Data Cleaning Log, including: X Deletion Log X Value Change Log |  |  |  |
|  |  | □ | Code book |  |  |  | □ |  | Data Dictionary |  |  |  |
|  |  | □ | Metadata based on HDX Standards |  |  |  | □ |  | [Other, Specify] |  |  |  |
| Ethics and Legal Compliance |  |  |  |  |  |  |  |  |  |  |  |
| Which ethical and legal measures will be taken? |  | X | Consent of participants to participate |  |  |  | X |  | Consent of participants to share personal information with other agencies |  |  |  |
|  |  | □ | No collection of personally identifiable data will take place |  |  |  | X |  | Gender, child protection and other protection issues are taken into account |  |  |  |
|  |  | X | All participants reached age of majority |  |  |  |  |  | [Other, Specify] |  |  |  |
| Who will own the copyright and Intellectual Property Rights for the data that is collected? |  | IMPACT |  |  |  |  |  |  |  |  |  |
| Storage and Backup |  |  |  |  |  |  |  |  |  |  |  |
| Where will data be stored and backed up during the research? |  | X | IMPACT/REACH Kobo Server |  |  |  | □ |  | Other Kobo Server: [specify] |  |  |  |
|  |  | □ | IMPACT Global Physical / Cloud Server |  |  |  | X |  | Country/Internal Server |  |  |  |
|  |  | □ | On devices held by REACH staff |  |  |  | □ |  | Physical location [specify] |  |  |  |
|  |  | □ | [Other, Specify] |  |  |  |  |  |  |  |  |  |
| Which data access and security measures have been taken? |  | □ | Password protection on devices/servers |  |  |  | X |  | Data access is limited to Designated REACH Staff |  |  |  |
|  |  | □ | Form and data encryption on data collection server |  |  |  | □ |  | Partners signed an MoU if accessing raw data |  |  |  |
|  |  | □ | [Other, Specify] |  |  |  |  |  |  |  |  |  |
| Kobo Access Rights |  |  |  |  |  |  |  |  |  |  |  |
| Kobo Access |  | Person |  |  |  | Account Name |  |  |  |  |  |
| View Form |  | Taqi Shayan |  |  |  | mtsh |  |  |  |  |  |
| View and Edit Form |  | Taqi Shayan |  |  |  | mtsh |  |  |  |  |  |
| View Form and Submit Data |  | Taqi Shayan |  |  |  | mtsh |  |  |  |  |  |
| Download Data |  | Taqi Shayan |  |  |  | mtsh |  |  |  |  |  |
| Raw Data Access Rights |  |  |  |  |  |  |  |  |  |  |  |
| Raw Data Access |  | Reason |  |  |  | Person |  |  |  |  |  |
| Accountable |  | Accountable |  |  |  | Taqi Shayan |  |  |  |  |  |
| Access |  | Needed for Analysis of Data and Data checkign/Cleaning |  |  |  | Taqi Shayan, Jawad Keshawarz |  |  |  |  |  |
| Preservation |  |  |  |  |  |  |  |  |  |  |  |
| Where will data be stored for long-term preservation? |  | X | IMPACT / REACH Global Cloud / Physical Server |  |  |  | □ |  | OCHA HDX |  |  |  |
|  |  | X | REACH Country Server |  |  |  | □ |  | [Other, Specify] |  |  |  |
| Data Sharing |  |  |  |  |  |  |  |  |  |  |  |
| Will the data be shared publically? |  | X | Yes |  |  |  | □ |  | No, only with mandating agency / body |  |  |  |
| Will all data be shared? |  | □ | Yes |  |  |  | X |  | No, only anonymized/ cleaned/ consolidated data |  |  |  |
|  |  | □ | No, [Other, Specify] |  |  |  |  |  |  |  |  |  |
| Where will you share the data? |  | X | REACH Resource Centre |  |  |  | X |  | OCHA HDX |  |  |  |
|  |  | □ | HumanitarianResponse |  |  |  | □ |  | [Other, Specify] |  |  |  |
| Data protection risk assessment |  |  |  |  |  |  |  |  |  |  |  |
| Have you completed the Indicators Risk Assessment table below? |  | X | Yes |  |  |  |  | □ | No, no information that potentially allows identification of individuals is to be collected. |  |  |
|  |  | [Please complete the first 4 columns in the Indicators Risk Assessment table below] |  |  |  |  |  |  |  |  |  |
| Risk indicator | Type of identification risk |  |  | Disclosure implications | Benefits |  |  |  |  | Class | Required mitigation |
| phone | Direct Contact/Identification |  |  | Loss of Privacy/Reprecusions | Allows for follow up during data cleaning |  |  |  |  | [To be completed by IMPACT HQ] | [To be specified by IMPACT HQ] |
| rep_come | Identification |  |  | Loss of Privacy/Reprecusions | Ensures KI is knowledgeable to speak on the service |  |  |  |  |  |  |
| rep_health | Identification |  |  | Loss of Privacy/Reprecusions | Ensures KI is knowledgeable to speak on the service |  |  |  |  |  |  |
| rep_school | Identification |  |  | Loss of Privacy/Reprecusions | Ensures KI is knowledgeable to speak on the service |  |  |  |  |  |  |
| rep_utility | Identification |  |  | Loss of Privacy/Reprecusions | Ensures KI is knowledgeable to speak on the service |  |  |  |  |  |  |
| Responsibilities |  |  |  |  |  |  |  |  |  |  |  |
| Data collection |  | Aboraihan Safi, Aboraihan.safi@reach-initiative.org |  |  |  |  |  |  |  |  |  |
| Data cleaning |  | Karim Mirzad, karim.mirzad@reach-intiative.org |  |  |  |  |  |  |  |  |  |
| Data analysis |  | Taqi Shayan, taqi.shayan@reach-initiative.org |  |  |  |  |  |  |  |  |  |
| Data sharing/uploading |  | Taqi Shayan, taqi.shayan@reach-initiative.org |  |  |  |  |  |  |  |  |  |

# Monitoring & Evaluation Plan

- Please complete the M&E Plan column in the table and use the corresponding Tools in the Monitoring & Evaluation matrix to implement the plan during the research cycle.

| IMPACT Objective | External M&E Indicator | Internal M&E Indicator | Focal point | Tool | Will indicator be tracked? |
| --- | --- | --- | --- | --- | --- |
| Humanitarian stakeholders are accessing IMPACT products | Number of humanitarian organisations accessing IMPACT services/products Number of individuals accessing IMPACT services/products | # of downloads of x product from Resource Center | Country request to HQ | User_log | □ Yes |
|  |  | # of downloads of x product from Relief Web | Country request to HQ |  | □ Yes |
|  |  | # of downloads of x product from Country level platforms | Country team |  | □ Yes |
|  |  | # of page clicks on x product from REACH global newsletter | Country request to HQ |  | □ Yes |
|  |  | # of page clicks on x product from country newsletter, sendingBlue, bit.ly | Country team |  | □ Yes |
|  |  | # of visits to x webmap/x dashboard | Country request to HQ |  | □ Yes |
| IMPACT activities contribute to better program implementation and coordination of the humanitarian response | Number of humanitarian organisations utilizing IMPACT services/products | # references in HPC documents (HNO, SRP, Flash appeals, Cluster/sector strategies) | Country team | Reference_log | [List here relevant HPC-documents to be monitored: E.g. Iraq HNO 2018, Iraq Flash Appeal Mosul, Shelter Cluster strategy] |
|  |  | # references in single agency documents |  |  | [List here relevant agency-documents to be monitored: E.g. UNHCR Country Strategy, UNICEF WASH Response Strategy] |
| Humanitarian stakeholders are using IMPACT products | Humanitarian actors use IMPACT evidence/products as a basis for decision making, aid planning and delivery Number of humanitarian documents (HNO, HRP, cluster/agency strategic plans, etc.) directly informed by IMPACT products | Perceived relevance of IMPACT country-programs | Country team | Usage_Feedback and Usage_Survey template | [Outline here the usage survey to be implemented for this research cycle |
|  |  | Perceived usefulness and influence of IMPACT outputs |  |  | E.g. Usage survey to be conducted in November 2017, following the release of x outputs, targeting at least 10 partners |
|  |  | Recommendations to strengthen IMPACT programs |  |  |  |
|  |  | Perceived capacity of IMPACT staff |  |  | E.g. Usage survey to be conducted at the end of the research cycle related to all outputs, targeting at least 20 partners] |
|  |  | Perceived quality of outputs/programs |  |  |  |
|  |  | Recommendations to strengthen IMPACT programs |  |  |  |
| Humanitarian stakeholders are engaged in IMPACT programs throughout the research cycle | Number and/or percentage of humanitarian organizations directly contributing to IMPACT programs (providing resources, participating to presentations, etc.) | # of organisations providing resources (i.e.staff, vehicles, meeting space, budget, etc.) for activity implementation | Country team | Engagement_log | □ Yes |
|  |  | # of organisations/clusters inputting in research design and joint analysis |  |  | □ Yes |
|  |  | # of organisations/clusters attending briefings on findings; |  |  | □ Yes |

#### Annex 1: Methodology Notes (if relevant)

#### Annex 2: [Other Specify]

UNOCHA, Afghanistan Flash Update #4: Earthquake in Paktika and Khost Provinces, 26 June 2022.

ECHO, Afghanistan - Earthquake Update, Daily Flash of 27 June 2022.

UNOCHA, Afghanistan Flash Update #3: Earthquake in Paktika and Khost Provinces, 25 June 2022.

UNITAR, Preliminary Satellite-Derived Damage Assessment Khost Earthquake (21 June 2022, Mw 6.2), 24 June 2022

REACH, Humanitarian Situation Monitoring, Terms of Reference, February 2022

IMPACT Data Cleaning Minimum Standards Checklist, 2020