Meeting minutes

NFIs Working Group Meeting

Day/Date: Wednesday, 6 August 2014, 10:00 am

Agenda

- Standardization of NFIs kits and contents.

- Consumable items and distribution frequency

- Mapping actors, priorities, needs gaps and market

- Ensure information sharing and data base management.

- AoB

Meeting Minutes:

Shelter Cluster Meeting

| Agenda Item | Highlights of the Discussion | Action Point |
| --- | --- | --- |
| - Standardization of NFIs kits and contents. | Is the standardization a good idea? All say yes, to have unified kits and price indication. | All partners to send out their kits composition to consolidate the kits items SCC to share with partners different types of kits |
| - Consumable items and distribution frequency | The partners agreed to include consumable items sufficient minimum 2 weeks for each family of 6 members, so any kits preparation should consider the minimum period and the distribution reputation. |  |
| - Mapping actors, priorities, needs, gaps and market | Priorities: for immediate current needs and we need to see how the situation evolves, needs and priorities change. Mapping Actors: to ensure effective distribution it is recommended that each agency focus on one geographical area with possible rearrangements according to gaps and agencies capacities. Needs and Gaps: the partners have to update the 4Ws regularly to identify the gaps and needs Groups: Collective centres: Following the analysis and gaps according to UNRWA and MoSA information Assumption: - Significant number of people there for a couple of weeks - Majority of those in Collective Centres will require household kits and hygiene kits - Clothing – could one agency set up little shops/outlet with local suppliers based on vouchers system Non-displaced: host-families To identify the needs and to have clear and regular plans for targeting after consultation with MoSA Non-displaced: destroyed buildings To identify the needs if differ from other groups Assumptions - Not all are vulnerable or unable to provide for themselves - We don’t want to undermine cut out the private sector Market: What can people procure for themselves, quick market analysis needed and the recommendations to procure either from Gaza or outside market? | The SCC to update the partners regularly after gap analysis (suggestion :each week) The WG to identify the clothing voucher value |

Attendance list: NFIs WG meeting, Thursday August 06 2014

| Full Name | Organization | Job Title | Mobile Phone | E-mail |
| --- | --- | --- | --- | --- |
| Ismail Mansrah | PRCS | DRR coordinator | 0595-699 381 | imansrah@palestinercs.org |
| Hadeel Budeiri | IRPAL | Projects coordinator | 0592333394 | h.sharqawi@irpal.ps |
| Lana Abu Hijleh | Global communities (CHF) | Country director | 0599 413 101 | labuhijleh@globalcommunities.ps |
| Tony Rantissi | USAID | senior development specialist | 0505267731 | trantissi@usaid.gov |
| Lana Khalidi | ANERA | Manager of Admin and HR | 0526944469 | lanak@anera-jwg.org |
| Yousef Zalatimo | ANERA | Admin Assistant | 0542209183 | yzalatimo@anera-jwg.org |
| Reem Jafari | USAID | program specialist | 0502 022 617 | rjafari@usaid.gov |
| Kara Krutsinger | MercyCorps | Program support, reporting officer | 0542-883161 | kkrutisinger@ps.mercycorps.org |
| Nicole Lumezi | CRS | DCOP | 0549-765 001 | nicole.lumezi@crs.org |
| Hien ADJEMIAN | WFP | logistic cluster | 0546-773 100 | hien.adjemian@wfp.org |
| Vesna Stojanovic | UNRWA | Projects Coordinator | 0599 46 09 13 | v.stojanovic@unrwa.org |
| Keith Ochez | UNRWA | Project coordinator | 0542-325606 | K.OCHEZ@UNRWA.ORG |
| Fadi Shamisti | NRC | Shelter Cluster coordinator | 0546-663 902 | fadi.shamisti@nrc.no |
| Neil Brighton | NRC | Shelter Project Manager | 0549 023 744 | neil.brighton@nrc.no |