Relocation sites currently indentified (not complete!!!) d.d. 8th December 2009

| Point of origin | Status | Region relocation site | Province relocation site | Municipality | Name Rel site | Size m2 | Capacity (60% usable / 40mr per fam) | Planned relocation | Ongoing relocation | Completed relocation | Left over capacity relocation site |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Marikina, Bgay Fortune, Nangka, Conceptcion, Tanong | Existing | IV-A | Laguna | Santa Rosa | Southville IV-A |  | 480 |  |  | 487 | -7 |
| Marikina | Existing | IV-A | Laguna | Binan, Langkiwa | Southville V |  | 647 |  |  | 647 | 0 |
| Quezon city | Existing | III | Bulacan | San Jose del Monte | Towerville |  | 400 | 94 |  | 306 | 0 |
| Pasig / Waterways | Existing | IV-A | Laguna | Calauan | Southville VII |  | 600 | 0 |  | 600 | 0 |
| Pasig / Waterways | Existing | IV-A | Laguna | Calauan | Southville VII |  | 700 | 0 |  | 700 | 0 |
| Pasig / Waterways | Existing | IV-A | Laguna | Calauan | Southville VII |  | 800 | 192 |  | 608 | 0 |
| Pasig / Waterways | Existing | IV-A | Laguna | Calauan | Southville VII |  | 600 |  |  |  | 600 |
| Pasig / Waterways | Existing | IV-A | Laguna | Calauan | Southville VII |  | 384 |  |  |  | 384 |
|  | Approved | IV-A | Rizal | B'gay Dolores |  | 50.000 | 3.900 |  |  |  | 3.900 |
| LGU's of Rizal | Existing | IV-A | Rizal | Rodriguez / Muntalban | Joville 1 & 2 |  | 993 |  |  |  | 993 |
| MMIAC Priority Sites | Pending MGB? | IV-A | Rizal | Rodriguez / Muntalban | Rodriguez Hills |  | 1.918 | 1.207 | 0 | 711 | 0 |
| Taft North, Bakhaw, PHHC and Sta. Rosa in Mandurriao district; Taytay Zone II, Benedicto, Sambag, Dungon A, Dungon B., Ungka, Montinola, Calubihan, Cuartero, Our Lady of Lourdes, and Balabago in Jaro I district; and Lanit, Buntatala, Bito-on, Balantang, Tacas, and Tagbac in Jaro II district. | Under development | IV-A | Rizal | Rodriguez / Muntalban | San Isidro | 16.000 | 2.613 |  |  |  | 2.613 |
| Everywhere | Pending MGB? | III | Bulacan | San Miguel |  | 3.510.000 | 57.038 |  |  |  | 57.038 |
|  | Not suitable | CAR | Benguet | Itogo - kelly | Hoyback fraction | Site dispproved MGB | 3.250 |  |  |  | 3.250 |
| Luneta, Loacan, itogon | Pending MGB? | CAR | Benguet | Itogo - Tuding | Sitio Kalye Real |  | 3.250 |  |  |  | 3.250 |
| Kibungan | Pending MGB? | CAR | Benguet | Tawang | State university | 20.000 | 325 |  |  |  | 325 |
| Dangwa, capuyan | Pending MGB? | CAR | Benguet | Tublay - Lower coros | Private land | 100.000 | 1.625 |  |  |  | 1.625 |
| tbd | Not suitable | CAR | Benguet | Tuba | NHA housing | Site disapproved MGB |  |  |  |  | 0 |
| tbd | Existing, need rehabilitation | III |  | Calumpit, San Marcos | BDO |  | 46 |  |  |  | 46 |
| tbd | Identified, private donor | IV-A | Rizal | Antipolo | BDO | 6.270 | 102 |  |  |  | 102 |
| tbd | Identified, private donor | NCR | NCR | Muntalban | BDO | 20.000 | 325 |  |  |  | 325 |
| tbd | Identified, private donor | IV-A | Rizal | Tanay | BDO | 50.000 | 813 |  |  |  | 813 |
|  |  |  |  |  |  |  | 80.808 |  |  |  | 80.808 |

Table 9