MEETING

15/02/10, 17:00, OSOCC tent

| ACTION ITEMS |  |  |
| --- | --- | --- |
| - Deadlines: March 15th deadline for pipeline delivery in country. May 1st as 2 sheets per household coverage. - Pipeline. Cluster coordinator to follow up with key organisations |  |  |
| Organizations represented at this meeting |  |  |
| Canadian Red Cross American Red Cross IFRC ALEA’H | Save the children Poverty in Action Working group on disability Eagles Wings | DfID CARE USAID CHF International Airline Ambassadors |

### Introduction:

### 1 ore 2 plastic sheets?

Objective is that all families have 2 plastic sheets plus fixings by 01 May.

1 plastic sheet was as part of surge towards final product of transitional sheeting.

The concern is that 1 sheet makes it seen as with the job has been done. Clear messaging is required to ensure that families receive two sheets plus fixings.

There is a reporting issue – if 3 sheets are distributed then is that 1 or 2 families. Shelter IM to clarify this.

### Combined pipeline for transitional shelters

Proposal – one organisation takes the lead.

Procurement could be through a large agency (e.g. IOM, IFRC, UNOPS) or through private contractors.

Pipeline is not for emergency shelter materials.

### Private contractors

Guidance from USAID is that prefabricated structures are as a last resort. They are for use as structures to which universal public access is provided.

Should direct activities of contractors towards public infrastructure uses.

### Surge

WFP surge type activity will not be implemented for shelter. However there musrt remain a continued focus on shelter NFI distribution.

Shelter & NFI Cluster Contacts: www.shelterhaiti2010.org

Location: Cabin no. 48 MINUSTAH compound

Coordinator: Gregg MacDonald e: shelterhaiti2010 @gmail.com t: +509 3485 3012

Information Manager: Wan Sophonpanich e : shelterhaiti2010.im@gmail.com t : +509 4385 3017

Technical Coordinator: Joseph Ashmore e: mailto:shelterhaiti2010.tech1@gmail.com t: +509 4385 0302

Website: http://groups.google.com/group/shelterhaiti2010