## Front Page
CARAGA (DROMIC 17 January 2013) | DAMAGE |  | NUMBER OF
|  |  | DAMAGED HOUSES | Emergency |  |  | Recovery Shelter |  |  | Coverage
| Destroyed | Partial | Total | Completed | In Progress | Planned | Completed | In Progress | Planned | Emergency Coverage
SURIGAO DEL SUR | 5123 | 14482 | 19605 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Barobo | 42 | 29 | 71
Bayabas |  |  | 0
Cagwait | 17 |  | 17
Cantilan |  |  | 0
Cortes |  | 371 | 371
Hinatuan | 223 | 2800 | 3023
Lanuza |  | 10 | 10
Lianga | 25 | 21 | 46
Lingig | 3652 | 3694 | 7346
Marihatag | 10 | 39 | 49
San Agustin | 5 | 18 | 23
Tagbina | 616 | 13 | 629
Bislig | 533 | 7487 | 8020
DINAGAT ISLANDS | 1 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Cagdianao | 1 |  | 1
Dinagat |  | 5 | 5
SURIGAO DEL NORTE | 31 | 55 | 86
Dapa | 6 |  | 6
Mainit | 1 |  | 1
Placer | 23 |  | 23
Sta. Monica |  | 51 | 51
Surigao City | 1 | 4 | 5
AGUSAN DEL SUR | 19119 | 14006 | 33125 | 0 | 0 | 977 | 0 | 0 | 0 | 2.949%
Bunawan | 500 | 1643 | 2143
La Paz | 559 | 2395 | 2954
Loreto | 5014 | 1367 | 6381
Prosperidad |  | 29 | 29
Sibagat | 51 |  | 51
Sta.Josefa | 4108 | 1697 | 5805
Talacogon | 36 | 173 | 209
Tento | 5606 | 2331 | 7937
Verula | 3245 | 4371 | 7616
AGUSAN DEL NORTE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Las Nieves | 2 | 58 | 60
Tubay | 2 | 1 | 3
GRAND TOTAL | 24274 | 28548 | 52822 | 0 | 0 | 977 | 0 | 0 | 0
Based on DROMIC Caraga Region (30 January 2013) Update
Note 1: Coverage based on Agency reports on Plan, In Progress and Completed number of family figures against DROMIC damage figures
* Subject to funding, planning figures may change
All figures based on confirmed Funding Status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## AgusanDelSurComp by Type
Completed interventions by type of assistance
Updated as of: 16 Feb 2013
Damage figures based on DROMIC Caraga Region (30 January 2013) Update
Type of intervention based on Agency weekly updates

## SurigaoDelSurComp by Type
Completed interventions by type of assistance
Updated as of: 16 Feb 2013
Damage figures based on DROMIC Caraga Region (30 January 2013) Update
Type of intervention based on Agency weekly updates

## Agusan Del Sur
Agency Overview Agusan Del Sur
Updated as of: 16 Feb 2013
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | 11755
| 16657 | 14771 | 15085
Note 2: Total Number of Families Served: | 400 | Note 2: Total Planned Numbers of Families to be Served * | 2930
|  |  |  | Planned |  | Completed | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Recovery Shelter | Emergency Shelter
AGUSAN DEL SUR | LORETO | SABUD | UNHCR and CHR |  |  | 252 | 252
| LORETO Total |  |  |  |  | 252 | 252
| SANTA JOSEFA | POBLACION | International Organization for Migration |  |  | 69 | 69
|  | (blank) | World Vision
|  | CONCEPCION | International Organization for Migration |  |  | 38 | 38
|  | PATROCINIO | UNHCR and CHR |  |  | 40 | 40
|  | AWAO | International Organization for Migration |  |  | 53 | 53
|  | ANGAS | International Organization for Migration |  |  | 200 | 200
|  | SAYON | International Organization for Migration |  |  | 101 | 101
| SANTA JOSEFA Total |  |  |  |  | 501 | 501
| TRENTO | POBLACION | International Organization for Migration |  |  | 44 | 44
|  | SAN ISIDRO | International Organization for Migration |  | 16 | 47 | 63
|  | SAN ROQUE | International Organization for Migration |  | 17 | 38 | 55
|  | (blank) | World Vision
|  | NEW VISAYAS | International Organization for Migration |  |  | 81 | 81
|  | SAN IGNACIO | International Organization for Migration |  |  | 38 | 38
|  | SALVACION | International Organization for Migration |  |  | 38 | 38
|  | CUEVAS | International Organization for Migration |  |  | 38 | 38
|  | MANAT | International Organization for Migration |  |  | 38 | 38
|  | TUDELA | International Organization for Migration |  |  | 38 | 38
|  | BASA | International Organization for Migration |  |  | 38 | 38
|  | KAPATUNGAN | International Organization for Migration |  |  | 38 | 38
|  | LANGKILAAN | International Organization for Migration |  |  | 141 | 141
|  | PULANG LUPA | International Organization for Migration |  |  | 165 | 165
|  | STA. MARIA | International Organization for Migration |  | 17 | 39 | 56
|  | CEBULIN | International Organization for Migration |  |  | 38 | 38
|  | PANGAYAN | International Organization for Migration |  |  | 38 | 38
| TRENTO Total |  |  |  | 50 | 897 | 947
| VERUELA | (blank) | World Vision
|  | MAGSAYSAY | International Organization for Migration |  | 5 |  | 5
|  | DEL MONTE | International Organization for Migration |  | 10 | 154 | 164
|  | SINOBONG | International Organization for Migration |  | 10 | 575 | 585
|  | SANTA EMELIA | International Organization for Migration |  | 10 | 238 | 248
|  | CANDIIS | International Organization for Migration |  | 10 | 78 | 88
|  | LIMOT | International Organization for Migration |  |  | 124 | 124
|  | BINONGAN | International Organization for Migration |  | 5 | 111 | 116
| VERUELA Total |  |  |  | 50 | 1280 | 1330
| (blank) | (blank) | World Vision | 300 |  |  | 300
| (blank) Total |  |  | 300 |  |  | 300
AGUSAN DEL SUR Total |  |  |  | 300 | 100 | 2930 | 3330
Grand Total |  |  |  | 300 | 100 | 2930 | 3330
Note 1: Based on DROMIC CARAGA (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency report on Plan, in Progress and Completed number of family figures against DROMIC damages figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Surigao Del Sur
Agency Overview Surigao Del Sur
Updated as of: 16 Feb 2013
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | 13839
| 4520 | 9658 | 15085
Note 2: Total Number of Families Served: | 50 | Note 2: Total Planned Numbers of Families to be Served * | 1196
|  |  |  | Planned |  | Completed | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Recovery Shelter | Emergency Shelter
SURIGAO DEL SUR | LINGIG | POBLACION | International Organization for Migration |  | 20 |  | 20
|  | SAN ROQUE | International Organization for Migration |  |  | 150 | 150
|  | UNION | International Organization for Migration |  | 10 |  | 10
|  | PALO ALTO | UNHCR/Unyphil |  |  | 140 | 140
|  | RAJAH CABUNGSO-AN | International Organization for Migration |  |  | 40 | 40
|  | BOGAK | International Organization for Migration |  |  | 40 | 40
|  | TAGBOBO | International Organization for Migration |  |  | 85 | 85
|  | VILLAGE | International Organization for Migration |  |  | 46 | 46
|  | HANDAMAYAN | International Organization for Migration |  |  | 95 | 95
|  | MANDUS | International Organization for Migration |  | 10 |  | 10
|  | SABANG | International Organization for Migration | 10 |  |  | 10
| LINGIG Total |  |  | 10 | 40 | 596 | 646
| BISLIG | POBLACION | International Organization for Migration |  |  | 139 | 139
|  | Mangagoy | International Organization for Migration |  |  | 91 | 91
|  | Tabon | International Organization for Migration |  |  | 70 | 70
| BISLIG Total |  |  |  |  | 300 | 300
| HINATUAN | POBLACION | International Organization for Migration |  |  | 300 | 300
| HINATUAN Total |  |  |  |  | 300 | 300
SURIGAO DEL SUR Total |  |  |  | 10 | 40 | 1196 | 1246
Grand Total |  |  |  | 10 | 40 | 1196 | 1246
Note 1: Based on DROMIC CARAGA (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency report on Plan, in Progress and Completed number of family figures against DROMIC damages figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx