## Front Page
REGION XI (DROMIC 30 January 2013) | DAMAGE |  |  |  | NUMBER OF | Updated as of: 16 Feb 2013
[5 empty] | DAMAGED HOUSES | Emergency |  |  | Recovery Shelter |  |  | Note 1: Coverage | Note 1: Coverage
| Destroyed |  | Partial |  | Total | Completed | In Progress | Planned | Completed | In Progress | Planned | Emergency Coverage | Recovery Coverage
DAVAO ORIENTAL | 20673 | Diff | 15876 | Partial Diff | 36549 | 36965 | 1348 | 4073 | 203 | 10 | 358 | Emergency assistance recieved | 1.562%
Baganga | 6900 |  | 1738 |  | 8638 | 20953 |  | 2678 | 3 |  | 97
Boston | 2556 |  | 1056 |  | 3612 | 3725 | 780 | 746 |  | 10 | 30
Caraga | 1723 |  | 6347 |  | 8070
Cateel | 8786 |  | 567 |  | 9353 | 12287 | 568 | 649 | 200 |  | 231
Manay | 226 |  | 3714 |  | 3940
Tarragona | 232 |  | 1354 |  | 1586
Mati City | 250 |  | 1100 |  | 1350
DAVAO DEL SUR | 101 |  | 288 |  | 389
Don Marcelino | 78 |  | 182 |  | 260
Jose Abad Santos | 23 |  | 106 |  | 129
DAVAO DEL NORTE | 1758 |  | 20066 |  | 21824
Asucion | 450 |  | 982 |  | 1432
Carmen | 27 |  | 64 |  | 91
Dujali | 17 |  | 41 |  | 58
Kapalong | 469 |  | 12307 |  | 12776
New Corella | 473 |  | 3780 |  | 4253
San Isidro | 237 |  | 2012 |  | 2249
Sto.Tomas | 11 |  | 107 |  | 118
Talaingod |  |  | 282 |  | 282
Tagum City | 74 |  | 491 |  | 565
COMPOSTELA VALLEY | 32340 |  | 67638 |  | 99978 | 21477 | 1108 | 7120 | 3093 | 3812 | 4925 | 29.71% | 11.83%
Compostela | 8883 |  | 9658 |  | 18541 | 6752 | 610 | 415 |  |  | 40
Laak | 4848 |  | 8758 |  | 13606 | 3000 |  | 50
Mabini | 57 | 14 | 4360 | -4150 | 4417
Maco | 285 |  | 2383 | -46 | 2668
Maragusan | 235 | -173 | 1078 | 93 | 1313
Mawab | 701 | -11 | 3299 |  | 4000 |  | 65
Monkayo | 8023 | 510 | 12951 | 158 | 20974 | 4627 | 299 | 3871 | 2793 | 3812 | 4815
Montevista | 4072 | -408 | 5495 | -345 | 9567 | 2172 | 70 | 2065 |  |  | 50
Nabunturan | 2052 | 761 | 7342 | -926 | 9394 | 1555 |  |  |  |  | 20
New Bataan | 3134 | -990 | 11765 | -5912 | 14899 | 3371 | 64 | 719 | 300
Pantukan | 50 |  | 549 |  | 599
Unspecified Plans/Implementations | [5 empty] | 10000 | 0 | 12100 | 82 | 0 | 0
[6 empty] | 10000 |  | 12100 | 82
GRAND TOTAL | 54872 |  | 103868 |  | 158740 | 68442 | 2456 | 23293 | 3378 | 3822 | 5283
Based on DROMIC Region XI (30 January 2013) Update
Note 1: Coverage based on Agency reports on Plan, In Progress and Completed number of family figures against DROMIC damage figures
* Subject to funding, planning figures may change
All figures based on confirmed Funding Status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Completion by type
Completed interventions by type of assistance
Updated as of: 16 Feb 2013
Damage figures based on DROMIC Region XI (30 January 2013) Update
Type of intervention based on Agency weekly updates

## Compostela
Agency Overview Compostela
Updated as of: 16 Feb 2013
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | 10724
| 8883 | 9658 | 18541
Note 2: Total Number of Families Served: | 6792 | Note 2: Total Planned Numbers of Families to be Served * | 1025
|  |  |  | Planned |  | Completed |  | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Emergency Shelter | Recovery Shelter | Emergency Shelter
COMPOSTELA VALLEY | COMPOSTELA | MANGAYON | Catholic Relief Services |  |  |  | 618 | 618
|  |  | Plan International |  | 380 |  |  | 380
|  |  | International Organization for Migration |  |  |  | 208 | 208
|  | NEW ALEGRIA | HRC-OXFAM |  |  |  | 50 | 50
|  |  | International Organization for Migration |  |  |  | 95 | 95
|  | OSME-A | Plan International | 80 |  |  | 300 | 380
|  | PANAG | HRC-OXFAM |  |  |  | 38 | 38
|  | POBLACION | Plan International | 90 |  |  | 10 | 100
|  |  | ShelterBox International |  |  |  | 1 | 1
|  |  | International Organization for Migration |  |  |  | 93 | 93
|  | SAN JOSE | Catholic Relief Services |  |  |  | 309 | 309
|  |  | ShelterBox International |  |  |  | 5 | 5
|  |  | International Organization for Migration |  |  | 10 | 296 | 306
|  | SAN MIGUEL | Catholic Relief Services |  |  |  | 713 | 713
|  |  | Plan International | 80 | 35 |  | 315 | 430
|  | TAMIA | Plan International | 80 |  |  | 300 | 380
|  | (blank) | ShelterBox International | 50 |  |  |  | 50
|  | MUNICIPAL HALL (EC) | HRC-OXFAM |  |  |  | 192 | 192
|  | ALEGRIA | Catholic Relief Services
|  | MAPARAT | Catholic Relief Services |  |  |  | 544 | 544
|  |  | ShelterBox International |  |  |  | 25 | 25
|  |  | International Organization for Migration |  |  | 10 | 48 | 58
|  | AURORA | Catholic Relief Services |  |  |  | 304 | 304
|  | NGAN | Plan International | 230 |  |  | 300 | 530
|  |  | International Organization for Migration |  |  | 10 |  | 10
|  | OSMENA | Catholic Relief Services
|  |  | International Organization for Migration |  |  |  | 81 | 81
|  | BAGONGON | Catholic Relief Services |  |  |  | 202 | 202
|  |  | International Organization for Migration |  |  |  | 115 | 115
|  | GABI | Catholic Relief Services |  |  |  | 358 | 358
|  | LAGAB | Catholic Relief Services |  |  |  | 275 | 275
|  | MAPACA | Catholic Relief Services |  |  |  | 285 | 285
|  |  | International Organization for Migration |  |  | 10 | 150 | 160
|  | PANANSALAN | Catholic Relief Services |  |  |  | 166 | 166
|  |  | International Organization for Migration |  |  |  | 44 | 44
|  | SIOCON | Catholic Relief Services |  |  |  | 301 | 301
|  | Mormon | International Organization for Migration |  |  |  | 11 | 11
| COMPOSTELA Total |  |  | 610 | 415 | 40 | 6752 | 7817
COMPOSTELA VALLEY Total |  |  |  | 610 | 415 | 40 | 6752 | 7817
Grand Total |  |  |  | 610 | 415 | 40 | 6752 | 7817
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency report on Plan, in Progress and Completed number of family figures against DROMIC damages figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Laak (San Vicente)
Agency Overview Laak (San Vicente)
Updated as of: 16 Feb 2013
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining
| 4848 | 8758 | 13606 | 10556
Note 2: Total Number of Families Served: | 3000 | Note 2: Total Planned Numbers of Families to be Served * | 50
|  |  |  | Planned | Completed | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Emergency Shelter
COMPOSTELA VALLEY | LAAK (SAN VICENTE) | POBLACION | International Organization for Migration |  | 853 | 853
|  | (blank) | ShelterBox International | 50 |  | 50
|  | CONCEPCION | International Organization for Migration |  | 281 | 281
|  | KIDAWA | ShelterBox International |  | 32 | 32
|  | Kiokmay | International Organization for Migration |  | 338 | 338
|  | Libuton | International Organization for Migration |  | 168 | 168
|  | Sisimon | International Organization for Migration |  | 430 | 430
|  | Kibaguio | International Organization for Migration |  | 158 | 158
|  | Anitap | International Organization for Migration |  | 121 | 121
|  | Hinagtungan | International Organization for Migration |  | 73 | 73
|  | Bollukan | International Organization for Migration |  | 296 | 296
|  | Il Katipunan | International Organization for Migration |  | 160 | 160
|  | Limut | International Organization for Migration |  | 90 | 90
| LAAK (SAN VICENTE) Total |  |  | 50 | 3000 | 3050
COMPOSTELA VALLEY Total |  |  |  | 50 | 3000 | 3050
Grand Total |  |  |  | 50 | 3000 | 3050
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency report on Plan, in Progress and Completed number of family figures against DROMIC damages figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Monkayo
Agency Overview Monkayo
Updated as of: 16 Feb 2013
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | 757
| 8023 | 12951 | 20974
Note 2: Total Number of Families Served: | 7420 | Note 2: Total Planned Numbers of Families to be Served * | 4111
Number of Families served |  |  |  | Status
|  |  |  | In Progress |  | Planned |  | Completed |  | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Recovery Shelter | Emergency Shelter | Recovery Shelter | Emergency Shelter | Recovery Shelter
COMPOSTELA VALLEY | MONKAYO | BANLAG | Save the Children International |  |  | 811 |  |  |  | 811
|  |  | ShelterBox International |  |  |  |  | 15 |  | 15
|  |  | Habitat for Humanity Philippines | [5 empty] | 328.5 | 328.5
|  |  | PLGU | [5 empty] | 60 | 60
|  | HAGUIMITAN | Save the Children International |  |  |  |  | 493 |  | 493
|  |  | Habitat for Humanity Philippines |  |  |  | 476.5 |  |  | 476.5
|  |  | LGU | [5 empty] | 16 | 16
|  |  | PLGU | [5 empty] | 28 | 28
|  | INAMBATAN | Save the Children International |  |  |  |  | 407 |  | 407
|  |  | ShelterBox International |  |  |  |  | 2 |  | 2
|  |  | Habitat for Humanity Philippines |  |  |  | 571.8 |  |  | 571.8
|  |  | PLGU | [5 empty] | 50 | 50
|  | MOUNT DIWATA | Plan International |  |  | 265 |  |  |  | 265
|  |  | PLGU | [5 empty] | 30 | 30
|  | NABOC | Save the Children International |  |  | 748 |  |  |  | 748
|  |  | Habitat for Humanity Philippines |  |  |  | 571.8 |  |  | 571.8
|  |  | International Organization for Migration |  |  |  | 30 |  |  | 30
|  |  | PRC |  |  |  |  | 150 |  | 150
|  |  | PLGU | [5 empty] | 40 | 40
|  | PASIAN (SANTA FILOMENA) | Save the Children International |  |  | 1295 |  |  |  | 1295
|  |  | Habitat for Humanity Philippines |  |  |  | 476.5 |  |  | 476.5
|  |  | LGU | [5 empty] | 120 | 120
|  |  | PLGU | [5 empty] | 30 | 30
|  | Barangay Hall(Purok 3) | UNHCR/Unyphil |  |  |  |  | 40 |  | 40
|  | POBLACION | ShelterBox International |  |  |  |  | 11 |  | 11
|  |  | Habitat for Humanity Philippines | [5 empty] | 328.5 | 328.5
|  |  | International Organization for Migration |  |  |  |  | 24 |  | 24
|  |  | LGU | [5 empty] | 7 | 7
|  |  | PLGU | [5 empty] | 126 | 126
|  | SAN ISIDRO | Plan International | 18 |  |  |  | 189 |  | 207
|  |  | International Organization for Migration |  |  |  |  | 200 |  | 200
|  |  | PLGU | [5 empty] | 40 | 40
|  | SAN JOSE | Habitat for Humanity Philippines |  | 476.5 |  |  |  |  | 476.5
|  |  | LGU | [5 empty] | 100 | 100
|  |  | PLGU | [5 empty] | 58 | 58
|  | (blank) | ShelterBox International | 50 | [5 empty] | 50
|  |  | Lutheran World Relief |  | 2859 |  |  |  |  | 2859
|  | UPPER ULIP | Catholic Relief Services |  |  | 521 |  |  |  | 521
|  |  | Plan International | 173 |  | 15 |  | 73 |  | 261
|  |  | Habitat for Humanity Philippines |  |  |  | 571.8 |  |  | 571.8
|  |  | PRC |  |  |  |  | 150 |  | 150
|  |  | PLGU | [5 empty] | 50 | 50
|  | CASOON | Plan International |  |  | 207 |  |  |  | 207
|  |  | PLGU | [5 empty] | 40 | 40
|  | Barangay Hall(Purok 3) | UNHCR/Unyphil |  |  |  |  | 85 |  | 85
|  | RIZAL | ShelterBox International |  |  |  |  | 4 |  | 4
|  |  | Habitat for Humanity Philippines |  | 476.5 |  |  |  |  | 476.5
|  |  | LGU | [5 empty] | 171 | 171
|  |  | PLGU | [5 empty] | 40 | 40
|  | Barangay Hall(Purok 2) | UNHCR/Unyphil |  |  |  |  | 40 |  | 40
|  | SALVACION | ShelterBox International |  |  |  |  | 10 |  | 10
|  |  | Habitat for Humanity Philippines |  |  |  | 476.5 |  |  | 476.5
|  |  | International Organization for Migration |  |  |  |  | 830 |  | 830
|  |  | PLGU | [5 empty] | 40 | 40
|  | BAYLO | Habitat for Humanity Philippines | [5 empty] | 328.5 | 328.5
|  |  | International Organization for Migration |  |  |  |  | 4 |  | 4
|  |  | LGU | [5 empty] | 7 | 7
|  |  | PLGU | [5 empty] | 46 | 46
|  | Barangay Hall(Purok 2) | UNHCR/Unyphil |  |  |  |  | 40 |  | 40
|  | OLAYCON | Habitat for Humanity Philippines | [5 empty] | 328.5 | 328.5
|  |  | International Organization for Migration |  |  |  |  | 3 |  | 3
|  |  | LGU | [5 empty] | 65 | 65
|  |  | PLGU | [5 empty] | 75 | 75
|  | UNION | Catholic Relief Services |  |  |  |  | 328 |  | 328
|  |  | ShelterBox International |  |  |  |  | 1 |  | 1
|  |  | Habitat for Humanity Philippines |  |  |  | 476.5 |  |  | 476.5
|  |  | International Organization for Migration |  |  |  |  | 8 |  | 8
|  |  | PLGU | [5 empty] | 40 | 40
|  | BABAG | Habitat for Humanity Philippines |  |  |  | 571.8 |  |  | 571.8
|  |  | International Organization for Migration |  |  |  |  | 1 |  | 1
|  |  | PRC |  |  |  |  | 100 |  | 100
|  |  | PLGU | [5 empty] | 40 | 40
|  | MAMUNGA | ShelterBox International |  |  |  |  | 2 |  | 2
|  |  | Habitat for Humanity Philippines |  |  |  | 571.8 |  |  | 571.8
|  |  | International Organization for Migration |  |  |  |  | 495 |  | 495
|  |  | PLGU | [5 empty] | 40 | 40
|  | TUBO-TUBO (NEW DEL MONTE) | Plan International | 58 |  | 9 |  | 193 |  | 260
|  |  | ShelterBox International |  |  |  |  | 2 |  | 2
|  |  | International Organization for Migration |  |  |  | 10 | 35 |  | 45
|  |  | PLGU | [5 empty] | 40 | 40
|  | AWAO | International Organization for Migration |  |  |  | 10 | 47 |  | 57
|  |  | PLGU | [5 empty] | 40 | 40
|  | MACOPA | International Organization for Migration |  |  |  |  | 645 |  | 645
|  |  | PLGU | [5 empty] | 40 | 40
| MONKAYO Total |  |  | 299 | 3812 | 3871 | 4815 | 4627 | 2793 | 20217
COMPOSTELA VALLEY Total |  |  |  | 299 | 3812 | 3871 | 4815 | 4627 | 2793 | 20217
Grand Total |  |  |  | 299 | 3812 | 3871 | 4815 | 4627 | 2793 | 20217
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency report on Plan, in Progress and Completed number of family figures against DROMIC damages figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Montevista
Agency Overview Montevista
Updated as of: 16 Feb 2013
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | 5210
| 4072 | 5495 | 9567
Note 2: Total Number of Families Served: | 2185 | Note 2: Total Planned Numbers of Families to be Served * | 2172
|  |  |  | In Progress | Planned |  | Completed | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Emergency Shelter | Recovery Shelter | Emergency Shelter
COMPOSTELA VALLEY | MONTEVISTA | BANKEROHAN NORTE | Save the Children International |  |  |  | 242 | 242
|  | NEW CALAPE |  |  |  |  | 223 | 223
|  | POBLACION | International Organization for Migration |  |  | 20 | 110 | 130
|  | SAN VICENTE | Save the Children International |  |  |  | 281 | 281
|  | TAPIA | Save the Children International |  | 559 |  |  | 559
|  |  | International Organization for Migration |  |  |  | 109 | 109
|  | CAMANTANGAN/Purok 1 | UNHCR/Unyphil |  |  |  | 280 | 280
|  | LINOAN | Save the Children International |  | 649 |  |  | 649
|  |  | International Organization for Migration |  |  |  | 94 | 94
|  | NEW CEBULAN | Save the Children International |  | 144 |  |  | 144
|  | CANIDKID | Save the Children International |  | 280 |  |  | 280
|  | CAMANSI | Plan International |  |  |  | 55 | 55
|  |  | International Organization for Migration |  |  | 15 |  | 15
|  | CONCEPCION | Plan International | 39 |  |  | 73 | 112
|  | NEW VISAYAS | Plan International | 4 | 17 |  | 160 | 181
|  | PROSPERIDAD | Plan International | 27 | 30 |  | 153 | 210
|  | LEBANON | Plan International |  | 70 |  | 48 | 118
|  | BANAGBANAG | Plan International |  | 92 |  |  | 92
|  | NEW DALAGUETE/ Barangay Hall Purok 2 | UNHCR/Unyphil |  |  |  | 80 | 80
|  | BANGLASAN | Save the Children International |  | 224 |  |  | 224
|  |  | International Organization for Migration |  |  |  | 100 | 100
|  | New Sibulan | International Organization for Migration |  |  |  | 64 | 64
|  | Dauman | International Organization for Migration |  |  |  | 100 | 100
|  | Bankerohan sur | International Organization for Migration |  |  | 15 |  | 15
| MONTEVISTA Total |  |  | 70 | 2065 | 50 | 2172 | 4357
COMPOSTELA VALLEY Total |  |  |  | 70 | 2065 | 50 | 2172 | 4357
Grand Total |  |  |  | 70 | 2065 | 50 | 2172 | 4357
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency report on Plan, in Progress and Completed number of family figures against DROMIC damages figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Nabunturan
Agency Overview Nabunturan
Updated as of Feb. 16, 2013
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining
| 2052 | 7342 | 9394 | 4827
Note 2: Total Number of Families Served: | 2342 | Note 2: Total Planned Numbers of Families to be Served * | 2225
|  |  |  | Planned | Completed |  | Grand Total
Province | Municipality | Barangay | Organisation | Recovery Shelter | Emergency Shelter | Recovery Shelter
COMPOSTELA VALLEY | NABUNTURAN | POBLACION | International Organization for Migration |  | 25 |  | 25
|  |  | LGU |  | 25 | 147 | 172
|  | SAN ISIDRO | LGU |  | 25 | 89 | 114
|  | SAN ROQUE | International Organization for Migration | 10 | 115 |  | 125
|  |  | LGU |  | 25 | 166 | 191
|  | SAN VICENTE | LGU |  | 25 | 15 | 40
|  | MAINIT | LGU |  | 25 | 128 | 153
|  | MAGSAYSAY | International Organization for Migration | 10 | 50 |  | 60
|  |  | PRC |  | 150 |  | 150
|  |  | LGU |  | 25 | 279 | 304
|  | KATIPUNAN | LGU |  |  | 64 | 64
|  | CABIDIANAN | LGU |  | 25 | 42 | 67
|  | SANTA MARIA | International Organization for Migration |  | 50 |  | 50
|  |  | LGU |  | 50 | 97 | 147
|  | MANAT | LGU |  | 50 | 256 | 306
|  | Unspecified | International Organization for Migration |  | 545 |  | 545
|  | So. Baptist Church | International Organization for Migration |  | 20 |  | 20
|  | NEW SIBONGA | International Organization for Migration |  | 100 |  | 100
|  |  | LGU |  |  | 31 | 31
|  | BASAK | International Organization for Migration |  | 50 |  | 50
|  |  | PRC |  | 150 |  | 150
|  |  | LGU |  | 25 | 229 | 254
|  | PANGUTOSAN | International Organization for Migration |  | 50 |  | 50
|  |  | PRC |  | 150 |  | 150
|  |  | LGU |  | 25 | 147 | 172
|  | LINDA | International Organization for Migration |  | 100 |  | 100
|  |  | LGU |  | 25 | 57 | 82
|  | ANISLAGAN | LGU |  | 25 | 17 | 42
|  | ANTIQUERA | LGU |  | 25 | 64 | 89
|  | BAYABAS | LGU |  | 25 | 47 | 72
|  | BUKAL | LGU |  | 25 | 6 | 31
|  | CABACUNGAN | LGU |  | 25 | 44 | 69
|  | LIBASAN | LGU |  | 25 | 37 | 62
|  | MAGADING | LGU |  | 25 | 137 | 162
|  | MATILO | LGU |  |  | 45 | 45
|  | MIPANGI | LGU |  | 25 | 51 | 76
|  | NEW DAUIS | LGU |  | 25 | 19 | 44
|  | OGAO | LGU |  | 25 | 27 | 52
|  | SASA | LGU |  |  | 10 | 10
|  | SANTO NI-O (KAO) | LGU |  | 25 | 38 | 63
|  | TAGNOCON | LGU |  | 25 | 53 | 78
| NABUNTURAN Total |  |  | 20 | 2205 | 2342 | 4567
COMPOSTELA VALLEY Total |  |  |  | 20 | 2205 | 2342 | 4567
Grand Total |  |  |  | 20 | 2205 | 2342 | 4567
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency report on Plan, in Progress and Completed number of family figures against DROMIC damages figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## New Bataan
Agency Overview New Bataan
Updated as of: 16 Feb 2013
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | 10445
| 3134 | 11765 | 14899
Note 2: Total Number of Families Served: | 783 | Note 2: Total Planned Numbers of Families to be Served * | 3671
|  |  |  | In Progress | Planned | Completed |  | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Emergency Shelter | Emergency Shelter | Recovery Shelter
COMPOSTELA VALLEY | NEW BATAAN | ANDAP | Plan International |  | 171 | 23 |  | 194
|  | Purok 6(Plateau) | PRC |  |  | 150 |  | 150
|  | BANTACAN | Catholic Relief Services |  |  | 221 |  | 221
|  | COGONON | Catholic Relief Services |  |  | 124 |  | 124
|  |  | Plan International |  | 130 |  |  | 130
|  | PANAG | Catholic Relief Services |  |  | 418 |  | 418
|  |  | Habitat for Humanity Philippines |  |  |  | 100 | 100
|  | SAN ROQUE | Catholic Relief Services |  |  | 186 |  | 186
|  |  | Plan International |  | 130 |  |  | 130
|  |  | ShelterBox International |  |  | 7 |  | 7
|  | (blank) | ShelterBox International |  | 73 |  |  | 73
|  |  | Swiss Red Cross/PRC |  |  | 200 |  | 200
|  | FATIMA | Catholic Relief Services |  |  | 90 |  | 90
|  |  | Habitat for Humanity Philippines |  |  |  | 100 | 100
|  | BATINAO | Catholic Relief Services |  |  | 124 |  | 124
|  | MAGANGIT | Catholic Relief Services |  |  | 166 |  | 166
|  | KAHAYAG | Catholic Relief Services |  |  | 125 |  | 125
|  |  | ShelterBox International |  |  | 6 |  | 6
|  | MAGSAYSAY | Catholic Relief Services |  |  | 95 |  | 95
|  | KATIPUNAN | Catholic Relief Services |  |  | 304 |  | 304
|  | Manurigao | Plan International |  | 130 |  |  | 130
|  | CABINUANGAN (POB.) | Plan International | 64 | 85 | 1117 |  | 1266
|  |  | Habitat for Humanity Philippines |  |  |  | 100 | 100
|  | CABINUANGAN/Parish | Catholic Relief Services |  |  | 15 |  | 15
| NEW BATAAN Total |  |  | 64 | 719 | 3371 | 300 | 4454
COMPOSTELA VALLEY Total |  |  |  | 64 | 719 | 3371 | 300 | 4454
Grand Total |  |  |  | 64 | 719 | 3371 | 300 | 4454
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency report on Plan, in Progress and Completed number of family figures against DROMIC damages figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx