## Front Page
REGION XI (DROMIC 30 January 2013) | DAMAGE |  |  |  | NUMBER OF
[5 empty] | DAMAGED HOUSES | Emergency |  |  | Recovery Shelter |  |  | Note 1: Coverage | Note 1: Coverage
| Destroyed |  | Partial |  | Total | Completed | In Progress | Planned | Completed | In Progress | Planned | Emergency Coverage | Recovery Coverage
DAVAO ORIENTAL | 20673 | Diff | 15876 | Partial Diff | 36549 | 36965 | 1348 | 4073 | 203 | 10 | 358 | Emergency assistance recieved
Baganga | 6900 |  | 1738 |  | 8638 | 20953 |  | 2678 | 3 |  | 97
Boston | 2556 |  | 1056 |  | 3612 | 3725 | 780 | 746 |  | 10 | 30
Caraga | 1723 |  | 6347 |  | 8070
Cateel | 8786 |  | 567 |  | 9353 | 12287 | 568 | 649 | 200 |  | 231
Manay | 226 |  | 3714 |  | 3940
Tarragona | 232 |  | 1354 |  | 1586
Mati City | 250 |  | 1100 |  | 1350
DAVAO DEL SUR | 101 |  | 288 |  | 389 | [6 empty] | 0% | 0%
Don Marcelino | 78 |  | 182 |  | 260
Jose Abad Santos | 23 |  | 106 |  | 129
DAVAO DEL NORTE | 1758 |  | 20066 |  | 21824 | [6 empty] | 0% | 0%
Asucion | 450 |  | 982 |  | 1432
Carmen | 27 |  | 64 |  | 91
Dujali | 17 |  | 41 |  | 58
Kapalong | 469 |  | 12307 |  | 12776
New Corella | 473 |  | 3780 |  | 4253
San Isidro | 237 |  | 2012 |  | 2249
Sto.Tomas | 11 |  | 107 |  | 118
Talaingod |  |  | 282 |  | 282
Tagum City | 74 |  | 491 |  | 565
COMPOSTELA VALLEY | 32340 |  | 67638 |  | 99978 | 21477 | 1108 | 7120 | 1614 | 3812 | 4925 | 29.71% | 10.35%
Compostela | 8883 |  | 9658 |  | 18541 | 6752 | 610 | 415 |  |  | 40
Laak | 4848 |  | 8758 |  | 13606 | 3000 |  | 50
Mabini | 57 | 14 | 4360 | -4150 | 4417
Maco | 285 |  | 2383 | -46 | 2668
Maragusan | 235 | -173 | 1078 | 93 | 1313
Mawab | 701 | -11 | 3299 |  | 4000 |  | 65
Monkayo | 8023 | 510 | 12951 | 158 | 20974 | 4627 | 299 | 3871 | 1314 | 3812 | 4815
Montevista | 4072 | -408 | 5495 | -345 | 9567 | 2172 | 70 | 2065 |  |  | 50
Nabunturan | 2052 | 761 | 7342 | -926 | 9394 | 1555 |  |  |  |  | 20
New Bataan | 3134 | -990 | 11765 | -5912 | 14899 | 3371 | 64 | 719 | 300
Pantukan | 50 |  | 549 |  | 599
Unspecified Plans/Implementations | [5 empty] | 10000 | 0 | 12100 | 82 | 0 | 0
[6 empty] | 10000 |  | 12100 | 82
GRAND TOTAL | 54872 |  | 103868 |  | 158740 | 68442 | 2456 | 23293 | 1899 | 3822 | 5283
Based on DROMIC Region XI (30 January 2013) Update
Note 1: Coverage based on Agency reports on Plan, In Progress and Completed number of family figures against DROMIC damage figures
* Subject to funding, planning figures may change
All figures based on confirmed Funding Status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Completion by Type
Completed interventions by type of assistance
Updated as of: 16 Feb 2013
Damage figures based on DROMIC Region XI (30 January 2013) Update
Type of intervention based on Agency weekly updates

## Baganaga
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | Emergency assistance recieved
| 6900 | 1738 | 8638
Note 2: Total Number of Families Served: | 20956 | Note 2: Total Planned Numbers of Families to be Served * | 2775 | Planned |  | Completed |  | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Recovery Shelter | Emergency Shelter | Recovery Shelter
DAVAO ORIENTAL | BAGANGA | BANAO | ShelterBox International | 50 |  |  |  | 50
|  |  | ICRC |  |  | 507 |  | 507
|  |  | Plan International | 316 |  |  |  | 316
|  | CAATIHAN | International Organization for Migration |  |  | 92 |  | 92
|  | CARMEN | International Organization for Migration |  |  | 54 |  | 54
|  | KINABLANGAN | Catholic Relief Services |  |  | 735 |  | 735
|  |  | ShelterBox International | 50 |  |  |  | 50
|  |  | ICRC |  |  | 1248 |  | 1248
|  |  | Plan International | 875 |  |  |  | 875
|  |  | International Organization for Migration |  | 10 |  |  | 10
|  | POBLACION | International Organization for Migration |  |  | 165 |  | 165
|  | SAN ISIDRO | Catholic Relief Services |  |  | 287 |  | 287
|  |  | ICRC |  |  | 632 |  | 632
|  |  | International Organization for Migration |  | 10 | 37 |  | 47
|  | SAN JOSE | International Organization for Migration |  |  | 25 |  | 25
|  | SIMULAO | International Organization for Migration |  |  | 95 |  | 95
|  | BACULIN | Catholic Relief Services |  |  | 25 |  | 25
|  |  | ICRC |  |  | 1013 |  | 1013
|  | BOBONAO | ICRC |  |  | 333 |  | 333
|  | BATAWAN | ICRC |  |  | 271 |  | 271
|  | BATIANO | ICRC |  |  | 967 |  | 967
|  | BINONDO | Catholic Relief Services |  |  | 676 |  | 676
|  |  | ICRC |  |  | 886 |  | 886
|  |  | Plan International | 650 |  |  |  | 650
|  | CAMPAWAN | Catholic Relief Services |  |  | 246 |  | 246
|  |  | ICRC |  |  | 750 |  | 750
|  |  | Plan International | 367 |  |  |  | 367
|  | CENTRAL (POB.) | Catholic Relief Services |  |  | 70 |  | 70
|  |  | ICRC |  |  | 1267 |  | 1267
|  | DAPNAN | Catholic Relief Services |  |  | 298 |  | 298
|  |  | ICRC |  |  | 902 |  | 902
|  | LAMBAJON | Catholic Relief Services |  |  | 503 |  | 503
|  |  | ICRC |  |  | 2622 |  | 2622
|  |  | International Organization for Migration |  | 10 |  |  | 10
|  | LUCOD | ICRC |  |  | 1189 |  | 1189
|  | MAHANUB | ICRC |  |  | 1246 |  | 1246
|  |  | Plan International | 370 |  |  |  | 370
|  | MIKIT | Catholic Relief Services |  |  | 198 |  | 198
|  |  | ICRC |  |  | 335 |  | 335
|  | SALINGCOMOT | ICRC |  |  | 905 |  | 905
|  | SAN VICTOR | ICRC |  |  | 432 |  | 432
|  | SAOQUEGUE | ICRC |  |  | 1033 |  | 1033
|  | Ban-ao | Catholic Relief Services |  |  | 258 |  | 258
|  |  | International Organization for Migration |  | 17 |  | 3 | 20
|  | MAHAN-UB | Catholic Relief Services |  |  | 273 |  | 273
|  | Sibahay | International Organization for Migration |  |  | 106 |  | 106
|  | Cauwayanan | International Organization for Migration |  |  | 84 |  | 84
|  | Sta. Cruz | International Organization for Migration |  |  | 88 |  | 88
|  | Saoqueque | International Organization for Migration |  |  | 100 |  | 100
|  | Unspecified yet | International Organization for Migration |  | 50 |  |  | 50
| BAGANGA Total |  |  | 2678 | 97 | 20953 | 3 | 23731
DAVAO ORIENTAL Total |  |  |  | 2678 | 97 | 20953 | 3 | 23731
Grand Total |  |  |  | 2678 | 97 | 20953 | 3 | 23731
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency reports on Plan, In Progress and Completed number of family figures against DROMIC damage figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Cateel
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | Emergency assistance received
| 8786 | 567 | 9353
Note 2: Total Number of Families Served: | 12487 | Note 2: Total Planned Numbers of Families to be Served * | 1448
|  |  |  | In Progress | Planned |  | Completed |  | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Emergency Shelter | Recovery Shelter | Emergency Shelter | Recovery Shelter
DAVAO ORIENTAL | CATEEL | POBLACION | Catholic Relief Services |  |  |  | 61 |  | 61
|  |  | ICRC |  |  |  | 1667 |  | 1667
|  | Cateel District Hospital | UNHCR/Unyphil |  |  |  | 285 |  | 285
|  | SAN MIGUEL | ICRC |  |  |  | 256 |  | 256
|  |  | International Organization for Migration |  |  |  | 10 |  | 10
|  | SAN VICENTE | ICRC |  |  |  | 128 |  | 128
|  | Patung/Banlo | ICRC |  |  |  | 181 |  | 181
|  |  | Habitat for Humanity Philippines |  |  | 181 |  |  | 181
|  | ABIJOD | ICRC |  |  |  | 565 |  | 565
|  |  | Habitat for Humanity Philippines |  |  |  |  | 200 | 200
|  | ALEGRIA | ICRC |  |  |  | 343 |  | 343
|  |  | HRC-OXFAM |  |  |  | 382 |  | 382
|  |  | International Organization for Migration |  |  |  | 10 |  | 10
|  | ALIWAGWAG | ICRC |  |  |  | 337 |  | 337
|  | ARAGON | ICRC |  |  |  | 734 |  | 734
|  |  | Plan International | 568 |  |  |  |  | 568
|  |  | International Organization for Migration |  |  | 8 | 20 |  | 28
|  | BAYBAY | ICRC |  |  |  | 194 |  | 194
|  | MAGLAHUS | ICRC |  |  |  | 355 |  | 355
|  | MAINIT | ICRC |  |  |  | 543 |  | 543
|  |  | Plan International |  |  |  | 206 |  | 206
|  |  | International Organization for Migration |  |  | 22 | 30 |  | 52
|  | MALIBAGO | ICRC |  |  |  | 406 |  | 406
|  | SAN ALFONSO | ICRC |  |  |  | 809 |  | 809
|  |  | Plan International |  |  |  | 679 |  | 679
|  |  | International Organization for Migration |  |  |  | 10 |  | 10
|  | SAN ANTONIO | ICRC |  |  |  | 977 |  | 977
|  |  | International Organization for Migration |  |  | 20 | 10 |  | 30
|  | SAN RAFAEL | ICRC |  |  |  | 730 |  | 730
|  |  | International Organization for Migration |  |  |  | 10 |  | 10
|  | SANTA FILOMENA | ICRC |  |  |  | 328 |  | 328
|  | TAYTAYAN | ICRC |  |  |  | 1440 |  | 1440
|  |  | Plan International |  | 649 |  |  |  | 649
|  |  | International Organization for Migration |  |  |  | 20 |  | 20
|  | Acacia | International Organization for Migration |  |  |  | 56 |  | 56
|  | Almasiga | International Organization for Migration |  |  |  | 41 |  | 41
|  | Camagong | International Organization for Migration |  |  |  | 56 |  | 56
|  | Gemelina | International Organization for Migration |  |  |  | 55 |  | 55
|  | Ipil-Ipil | International Organization for Migration |  |  |  | 65 |  | 65
|  | Kalahi Bens Mixed Brgy | International Organization for Migration |  |  |  | 20 |  | 20
|  | Madre de Casas | International Organization for Migration |  |  |  | 50 |  | 50
|  | Mangga | International Organization for Migration |  |  |  | 120 |  | 120
|  | Maribujac | International Organization for Migration |  |  |  | 56 |  | 56
|  | Talisay | International Organization for Migration |  |  |  | 42 |  | 42
| CATEEL Total |  |  | 568 | 649 | 231 | 12287 | 200 | 13935
DAVAO ORIENTAL Total |  |  |  | 568 | 649 | 231 | 12287 | 200 | 13935
Grand Total |  |  |  | 568 | 649 | 231 | 12287 | 200 | 13935
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency reports on Plan, In Progress and Completed number of family figures against DROMIC damage figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx

## Boston
Note 1: Damage | Totally Destroyed : | Partially Damage: | Total Damage: | Note 3: Remaining | Emergency assistance recieved
| 2556 | 1056 | 3612
Note 2: Total Number of Families Served: | 3755 | Note 2: Total Planned Numbers of Families to be Served * | 1536
|  |  |  | In Progress | Planned |  | Completed |  | Grand Total
Province | Municipality | Barangay | Organisation | Emergency Shelter | Recovery Shelter | Emergency Shelter | Recovery Shelter | Emergency Shelter
DAVAO ORIENTAL | BOSTON | CAATIHAN | ICRC |  |  |  |  | 373 | 373
|  |  | International Organization for Migration |  |  |  |  | 92 | 92
|  | CARMEN | ICRC |  |  |  |  | 386 | 386
|  |  | International Organization for Migration | 10 |  | 10 |  | 54 | 74
|  | CAWAYANAN | ICRC |  |  |  |  | 248 | 248
|  | POBLACION | Catholic Relief Services |  |  |  |  | 22 | 22
|  |  | ICRC |  |  |  |  | 402 | 402
|  |  | Plan International | 750 |  |  |  |  | 750
|  |  | International Organization for Migration |  |  |  |  | 147 | 147
|  | SAN JOSE | ICRC |  |  |  |  | 602 | 602
|  |  | Plan International |  |  | 357 |  |  | 357
|  |  | International Organization for Migration | 10 |  |  | 10 | 190 | 210
|  | SIBAJAY | Plan International |  |  | 359 |  |  | 359
|  | SIMULAO | ICRC |  |  |  |  | 192 | 192
|  |  | International Organization for Migration |  |  |  |  | 95 | 95
|  | CABASAGAN | ICRC |  |  |  |  | 446 | 446
|  |  | Plan International |  |  |  |  | 187 | 187
|  |  | International Organization for Migration | 10 |  |  | 10 | 99 | 119
|  | Sibahay | International Organization for Migration |  | 10 | 10 |  | 106 | 126
|  | Cauwayanan | International Organization for Migration |  |  | 10 | 10 | 84 | 104
| BOSTON Total |  |  | 780 | 10 | 746 | 30 | 3725 | 5291
DAVAO ORIENTAL Total |  |  |  | 780 | 10 | 746 | 30 | 3725 | 5291
Grand Total |  |  |  | 780 | 10 | 746 | 30 | 3725 | 5291
Note 1: Based on DROMIC Region XI (30 January 2013) update
Note 2: Number of Families Served base on Agency Reports
Note 3: Remaining based on Agency reports on Plan, In Progress and Completed number of family figures against DROMIC damage figures
* Plan may change subject to funding
All figures based on comfirmed funding status as per agency reports unless otherwise specified
https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx