## REP_SumPROV
Website: | https://www.sheltercluster.org/Asia/Philippines/TyphoonPablo2012/Pages/default.aspx
[5 empty] | Best Case |  | Worst
|  |  |  | TOTAL PROJECTED HOUSES DAMAGED OR DESTROYED | 128476 |  | 205782
|  |  |  | TOTAL CURRENTLY PLANNED EMERGENCY SHELTER PROGRAMS | 103979 |  | 103979
|  |  |  | GAP | 24497 |  | 101803
|  |  | DSWD DATA | [9 empty] | AGENCY SHELTER REPORTS
LOCATION |  |  | EVACUATION CENTRES |  |  |  | HOUSING DAMAGE |  |  |  |  | ANALYSIS | EMERGENCY SHELTER |  |  | RECOVERY SHELTER
REGION | PROVINCE | POPULATION | INSIDE | OUTSIDE | TOTAL | % POP | DESTROYED | PARTIAL | TOTAL | PROJECTED | % POP | DIFF - Housing vs Ecs | COMPLETED | PLANNED | TOTAL | COMPLETED | PLANNED | TOTAL
|  | families | families | families | families |  | houses | houses | houses | houses
|  | Note 1 | Note 2 | Note 2 | Note 2 |  | Note 2 | Note 2 | Note 2 | Note 3
Caraga | SURIGAO DEL SUR | 87590 | 93 | 102 | 195 | 0.2226% | 5859 | 12810 | 18669 | 18669 | 21.31% | 18474 | 1000 | 0 | 1000 | 0 | 0 | 0
Caraga | DINAGAT ISLANDS | 24162.6 | 0 | 25 | 25 | 0.1035% | 1 | 5 | 6 | 6 | 0.02483% | 19 | 0 | 0 | 0 | 0 | 0 | 0
Caraga | SURIGAO DEL NORTE | 80310.4 | 0 | 0 | 0 | 0% | 10 | 577 | 587 | 587 | 0.7309% | 587 | 0 | 0 | 0 | 0 | 0 | 0
Caraga | AGUSAN DEL SUR | 96798.2 | 1051 | 6165 | 7216 | 7.455% | 12021 | 11743 | 23764 | 23764 | 24.55% | 16548 | 234 | 0 | 234 | 0 | 2000 | 2000
Caraga | AGUSAN DEL NORTE | 102196 | 444 | 65 | 509 | 0.4981% | 22 | 71 | 93 | 93 | 0.091% | 416 | 0 | 0 | 0 | 0 | 0 | 0
| SUB TOTAL | 391057.2 | 1588 | 6357 | 7945 | 2.032% | 17913 | 25206 | 43119 | 43119 | 11.03% | 35174 | 1234 | 0 | 1234 | 0 | 2000 | 2000
XI | DAVAO ORIENTAL | 97220.8 | 0 | 44887 | 44887 | 46.17% | 11322 | 5179 | 16501 | 26501 | 27.26% | 18386 | 18659 | 3600 | 22259 | 0 | 0 | 0
XI | DAVAO DEL SUR | 292203.2 | 0 | 1003 | 1003 | 0.3433% | 101 | 288 | 389 | 389 | 0.1331% | 614 | 0 | 0 | 0 | 0 | 0 | 0
XI | DAVAO DEL NORTE | 134702.2 | 0 | 33263 | 33263 | 24.69% | 102 | 2862 | 2964 | 2964 | 2.2% | 30299 | 0 | 0 | 0 | 0 | 0 | 0
XI | COMPOSTELA VALLEY | 127473.2 | 2304 | 116380 | 118684 | 93.11% | 25462 | 30041 | 55503 | 55503 | 43.54% | 63181 | 4641 | 16600 | 21241 | 200 | 1300 | 1500
| SUB TOTAL | 651599.4 | 2304 | 195533 | 197837 | 30.36% | 36987 | 38370 | 75357 | 85357 | 13.1% | 112480 | 23300 | 20200 | 43500 | 200 | 1300 | 1500
| UNSPECIFIED LOCATIONS | [11 empty] | 1400 | 57845 | 59245 | 0 | 0 | 0
| GRAND TOTAL | 1042656.6 | 3892 | 201890 | 205782 | 19.74% | 54900 | 63576 | 118476 | 128476 | 12.32% | 77306 | 25934 | 78045 | 103979 | 200 | 3300 | 3500
| Total Population | 5213283
NOTE 1 | Source: National Statistics Coordination Board - Average Familiy Size = 5 People
NOTE 2 | Source: Department of Social Welfare and Development
NOTE 3 | Projected Total Houses either Destroyed or Partially Damaged - this includes assumptions for Cateel Municipality @ 10,000 Houses based upon number of families in Ecs

## BYLocation
STATUS | (Multiple Items)
Sum of NumFAM | Column Labels
Row Labels | Emergency Shelter | Recovery Shelter | Grand Total
AGUSAN DEL SUR |  | 2000 | 2000
BUNAWAN
HelpAge / Cose
ROSARIO
HelpAge / Cose
SANTA JOSEFA
World Vision
TRENTO
HelpAge / Cose
World Vision
VERUELA
World Vision
(blank)
World Vision |  | 2000 | 2000
COMPOSTELA VALLEY | 16600 | 1300 | 17900
COMPOSTELA
CATHOLIC RELIEF SERVICES | 5000 |  | 5000
Plan International
ShelterBox
Monkayo
Habitat for Humanity |  | 1300 | 1300
Plan International
Save the Children International | 3488 |  | 3488
Montevista
Plan International
Save the Children International | 2910 |  | 2910
ShelterBox
NABUNTURAN (Capital)
ShelterBox
NEW BATAAN
CATHOLIC RELIEF SERVICES | 5000 |  | 5000
Plan International
ShelterBox
unspecified
AADC Mindanao
Save the Children International | 102 |  | 102
(blank)
Plan International | 100 |  | 100
DAVAO ORIENTAL | 3600 |  | 3600
BAGANGA
CATHOLIC RELIEF SERVICES | 1750 |  | 1750
Plan International
BOSTON
Plan International
CATEEL
CATHOLIC RELIEF SERVICES | 1750 |  | 1750
Plan International
CITY OF MATI (Capital)
ShelterBox
(blank)
Plan International | 100 |  | 100
DINAGAT ISLANDS
LORETO
World Vision
unspecified | 34295 |  | 34295
(blank)
ICRC | 34295 |  | 34295
(blank) | 23550 |  | 23550
(blank)
DSWD | 20000 |  | 20000
PRC | 1400 |  | 1400
ShelterBox | 450 |  | 450
USAID/WFP | 1700 |  | 1700
Grand Total | 78045 | 3300 | 81345

## BYAgency
Sum of NumFAM | Column Labels
| Emergency Shelter |  | Recovery Shelter |  | Transitional Shelter | (blank) | Grand Total
Row Labels | Completed | Planned | Completed | Planned | Planned | (blank)
AADC Mindanao
CATHOLIC RELIEF SERVICES |  | 13500 |  |  |  |  | 13500
DSWD | 404 | 20000 |  |  | 830 |  | 21234
Habitat for Humanity |  |  | 200 | 1300 |  |  | 1500
HelpAge / Cose
ICRC | 7300 | 34295 |  |  |  |  | 41595
IOM | 951 | [5 empty] | 951
Plan International | 519 | 200 |  |  |  |  | 719
PRC |  | 1400 |  |  |  |  | 1400
Save the Children International |  | 6500 |  |  |  |  | 6500
ShelterBox |  | 450 |  |  |  |  | 450
USAID/WFP | 16760 | 1700 |  |  |  |  | 18460
World Vision |  |  |  | 2000 |  |  | 2000
(blank)
Grand Total | 25934 | 78045 | 200 | 3300 | 830 |  | 108309