SHELTER CLUSTER MEETING

MINUTES OF THE MEETING

JANUARY 27, 2014 (1400Hrs) -Revised Version 2

NEW OSOCC BUILDING, GUIUAN, E. SAMAR

CHAIR: IOM

ATTENDEES:

| NAME | ORG | CONTACT # | EMAIL ADDRESS |
| --- | --- | --- | --- |
| - CLETO ABAD | IOM\HoO | - | cabad@iom.int |
| - MA. LORRIELYN CAPACITE | IOM\IMA | - | lcapacite@iom.int |
| - RODOLFO A. YODICO II | IOM\SHELTER | - | rodox81@yahoo.com |
| - MARIA ANGELA D'ADAMO | OXFAM\WASH | 09267231149 | mdadamo@oxfam.org.uk |
| - JEAN-BENOT ALIX | Tdh | 09155060630 | Jal@Tdh.ch |
| - GEKE KIEFT | ZOA | 09202951392 | g.kieft@ZOA.NL |
| - MARTA PIOWERAS | SIF | 09283213263 | shelterphilippines@secours-islamique.org |
| - RENE VIDALLO | CORDAID | 09206146064 | rene.vidall@iirr.org |
| - MYRAVIT P. TOLEDO | CRS | 09296071600 | myravit.toledo@crs.org |
| - MODELEEN JOR RON LANGFORD | CORDAID | 09152646203 | ronald.langford@gmail.com |
| - GWENAELLE RAVON | ICRC |  | gravon@icrc.org |
| - GAVIN MACMILLAN | ICRC | 09989600122 | gamacmillan@icrc.org |
| - TIMU KNAUTE | OCHA | 09276334458 | knaute@un.org |

- EMERGENCY MARKET MAPPING AND ANALYSIS (EMMA) EXERCISE

- EMMA is on its last day of fieldwork. Organizations that are participating are IOM, OXFAM and CRS. - For further details and specific information, please contact Czarina from OXFAM, CZARINA M. KUNSO, ckunso@oxfam.org.uk

- PARTNER UPDATES

With the aim of avoiding duplications, promoting cooperation amongst the various partners, and also to identify shelter gaps, all SC partners present in the meeting agreed to share information on their respective shelter projects specifically the target barangays in E. Samar & Marabut. - ICRC - Shelter On-Going Assessment Since December In 12 Municipalities (In Eastern Samar And Samar), Still On-Going In Uplands (Way Delayed Due To Bad Weather ); - Some Discussions Have Been On-Going At The Municipal Levels - Target Is 6'000 Houses In 2014 - Start Of The Beneficiaries Selection Process Together With The Philippine Red Cross (PRC) On 6 Pilot Sites - Brgy. Tinabanan, Marabut - Biga & Cansingkol, Giporlos - Naga & Palactad, Quinapondan - Brgy. Tacla-On, Salcedo - Islands Which Will Be Assessed As Soon As The Weather Condition Allows: - Salvation Maliwaliw, Salcedo, Homonhon & Victory, Guiuan - List Of Barangays Concerned And Design Of The Core Progressive House Already Shared With The Shelter Cluster In Guiuan: - CRS - Full House & Shelter Repair (pilot) in Quinapondan, Giporlos, Salcedo & Lawaan - Quinapondan - Alang alang, Bagte, Buenavista & Paco - Giporlos - San Isidro, Paya, Coticot, Biga - Salcedo - Buwa-buwa, Bagtong & Balud - CORDAID - Holistic program. Strengthening the capacity of the barangay (capacity building) Target - 2 years - Sulangan & Ngolos, Guiuan - SIF - SIF is planning to implement a programme Shelter + toilet for each household. - SIF is making an assessment in Hernani (Carmen, Garawon, Poblacion 3 and 4, in coordination with ZOA and TdH who are already working there, to avoid duplications). - In Nagaja, Padang and Poblacion 2 (Hernani), SIF is waiting for the list of affected families that the municipality of Hernani is preparing (around 191 washed out houses according to the MPDC) to start an assessment. - The MPDC in Hernani and the DOH told SIF that no actor was working there. - TDH - Assessing - San Julian - Balangkayan - Hernani

- DISASTER RISK REDUCTION TRAINING (DRR Training)

- IOM - 12 Brgys in Mercedes & 12 Brgys. in Guiuan