Shelter Cluster Meeting

Minutes of the Meeting

Location: New OSOCC Building, Guiuan, E. Samar

Date: January 6, 2014

Chair: IOM

Attendees:

| NAME | ORGANIZATION | CONTACT # | EMAIL ADDRESS |
| --- | --- | --- | --- |
| - Rommel de Guzman | IOM | - | rdeguzman@iom.int |
| - Albert Spiteri | IOM | - | aspiteri@iom.int |
| - Angela Moore | UNHCR | - | moorea@unhcr.org |
| - Maksat Pataev | ACTED | - | maksat.pataev@acted.org |
| - Andrew Martin | UN OCHA | - | martin14@un.org |
| - Lailati Aboubakari. | Secours Islamique France | - | aboubakari@secours-islamique.org |
| - Ludek Suoboda | PIN | 09279209440 | ludek.suoboda@pinf.cz |
| - Petr Navrat | PIN | 09151141079 | Petr.Navrat@pinf.cz |
| - Libby Dometita | OXFAM | 09189646337 | MDometita@oxfam.org.uk |
| - Brad Mellicker | IOM | 09267245776 | BMELLICKER_AS@iom.int |
| - Nattha C. Gaytos | IOM | 09174549492 | ngaytos@iom.int |

Tents, ESKs and NFIs

- Presentation of the partners involved (please refer to the powerpoint  presentation)

- Tents – recommendation from the shelter cluster is to phase out

- Emergency shelter kits – the recommendation is to move to recovery shelter to support the self-recovery of the population who are rebuilding their own houses.

Chainsaw Operation

- Salary cap for chainsaw operators

- IOM - starting salary started at P500/ day and later increased to P600/ day

- People in need – P500/day

- WHO provides for a tetanus vaccination for chainsaw operators and assistants

- Red cross provides for an affordable insurance policy for the chainsaw operators and other people involved in the operation

G.I. Sheets

- DSWD is giving out 44,000 G.I. sheets in Guiuan.

- IOM and other actors are also giving out G.I. sheets in other places

New Reporting Format

- There is a new reporting format for the shelter cluster reporting (please see attached format).

Evacuation centers in case of calamity

- MSWD in Guiuan provided a list of at least 40 sites (8 sites were in the islands)

- Of the 32 pre-Yolanda ECs in Guiuan municipality (excluding the islands)

- 3 are usable now / need minor repairs

- 25 need significant repairs before they could be used (most of them are schools)

- 4 need to be rebuilt completely