| Country : YEMEN |  | Year : 2022 |  | Date of launch of the CCPM process (sharing of the online survey): 16th of January 2023 |  | Date of the survey results revision and action plan meeting: 30th of March 2023 |  | Date of completion of the CCPM (sharing of the action plan at the GSC): 18 of April 2023 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Cluster Core Functions | Performance Status | Prioritization | Actions agreed | Timeframe agreed | Responsible to follow up | Constraints, unexpected circumstances, good practice |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Supporting service delivery | 79%: Satisfactory (needs minor improvement) | Top priority | - Follow-up on the authority approval on the revised rapid needs assessment form. - Develop a beneficiary list template to capture key elements. - Establish a risk mapping to inform the response. - Develop a guideline on data sharing protocol and relevant tools. - Develop guidance on how to tackle cross-checking beneficiaries lists among partners. - Update the distribution guideline (incl. community participation and protection mainstreaming) and follow up with partners to ensure compliance. - Develop a catalog of shelter solutions recommended in Yemen. - Establish shelter maintenance/upgrade kits with adding new items based on technical assessments. - Review the NFI kit composition and specifications. - Review the Shelter Cluster membership tool and criteria for enrolling new members in either active or info. mailing list. | Q2-Q3 Q3 Q3 Q2 Q3 Q3-Q4 Q3 Q3 Q3 Q4 | SCT SCT SCT & SAG SCT & SAG SCT SCT & TWiG SCT & TWiG SCT & TWiG SCT & TWiG SCT | - Access constraints, incl. delays in approving projects sub-agreement or extensions as well as movement clearances. - Frequent escalation of hostilities and additional waves of displacements present a challenge to the response. - Natural hazards impact communities, including IDPs, and generate additional needs. - Funding shortages and limited resources hinder plans to scale up the response. - Confidentiality of data |
| 2. Informing HC/HCT strategic decision-making | 81%: Satisfactory (needs minor improvement) | Medium priority | - Establish an emergency mechanism and guidance to ensure timely reporting and actual response to emerging emergencies. - Develop specific messaging for the HC/HCT. - Develop an in-depth gap analysis. - Promote the shift from emergency to durable shelter solutions. | Q2-Q3 Q2-Q4 Q2-Q3 Q2-Q4 | SCT & SAG SCT & SAG SCT SCT | - Funding shortage is a key challenge. |
| 3. Planning and implementing cluster strategies | 73% Satisfactory (needs minor improvement) | Top priority | - Organize an annual retreat with Sub-National Cluster coordinators and partners to monitor the implementation of the Shelter Cluster Multi-Year Strategy. - Follow up with OCHA to share with the Cluster the access constraints template in a monthly basis - Encourage Cluster partners to participate actively in the Cluster meetings and share their plans and strategic directions. | Q2 Q2 – Q4 Q2 – Q4 | SCT SCT Partners | - Shortage of resources hinders the implementation of strategies. - Engagement of donors in the development of strategies and planning processes is beneficial. |
| 4. Monitoring and evaluating performance | 69% Satisfactory (needs minor improvement) | Medium priority | - Develop eligibility crieteria for all shelter and NFI activities including emergency shelter, transitional shelter, house rehabilitation …etc - Present lessons learned or best practices, especially during the cluster meetings. - Organize a dedicated discussion on areas of improvement to the cluster 5W system. - Strengthen post-distribution monitoring tools and analysis to inform planning and strategy development. | Q4 Q2 - Q4 Q4 Q3 | SCT & TWiG SCT SCT & Partners SCT | - Further follow-up is needed to encourage partners to share 5W. - High turnover of partner’s staffing reduces the effectiveness of programs as a result of discontinuity in staffing and loss of institutional memory. - Reporting at the site level is a time consuming and the reporting system is not highly flexible to incorprate the list of sites from CCCM Cluster database - Internet connection presents challenges in reporting, among other difficulties. - Provide further capacity-building programs and coaching for the coordination team as well as cluster partners. |
| 5. Building national capacity in preparedness and contingency planning | 77%: Satisfactory (needs minor improvements) | Top priority | - Update the Shelter Cluster Common Pipeline SOP and tools & develop a one-pager to explain the benefit of the pipeline. - Explore the establishment of new warehouses for the Shelter Cluster Common Pipeline in strategic locations. - Organize capacity buidling programs frequently and focus on developing contingency plans and SOPs | Q3 Q2 Q3-Q4 | SCT & SAG SCT SCT | - Provision of mandatory documents such as needs assessment reports, beneficiaries’ lists, and contingency stocks release agreements takes time to prepare. - Advocacy is needed to address the funding situation and the replenishment of the SC contingency pipeline. - Additional warehouses and contingency supplies need to be prepositioned in proximity to areas prone to flood to facilitate rapid response. - There is a greater need to address the specific needs of the affected population timely. - Access remains a key challenge to conflict front-line districts such as Harad, Midi, and Bakil Al Mair. - There is a need to define damages (full, partial, minor) caused by flooding and determine the appropriate response. - Absence of multi-sectoral need assessment tool. - Lack of an SOP or guideline on the response to the flood-affected families and pre-defined response timeline. - Delays in getting the authority approval to the cluster revised rapid needs assessment tool. - Delays in the flood response are often related to the lengthy agencies processes, limited staffing, internal bureaucracy procedures, and centralization of decision-making. - Partners often do not have sufficient funding to engage in the flood response. - Difficulties, delays, and in some cases, denial of clearances by authorities when transporting supplies between governorates. - There is a need to strengthen the Post monitoring. |
| 6. Supporting robust advocacy | 73%: Satisfactory (needs minor improvements) | Top priority | - Organize donor outreach missions to advocate for Shelter/NFI priorities. - Explore opportunities to organize a dedicated donor conference potentially in Amman. - Strengthen the visibility of the Shelter Cluster Common Pipeline. - Advocate with donors for funding the Shelter Cluster Common Pipeline, including warehousing, transportation, and distribution expenses - Increase the advocates’ visibility by organizing regular meetings and dissemnation of information | Q2-Q1 2024 Q4 Q2-Q1 2024 Q2-Q4 Q2 – Q1 2023 | SCT & SCT SCT SCT SCT | - Further advocacy on cross-cutting issues, incl. HLP. - Advocacy at a higher level particularly by the HC/HCT regarding preserving the integrity of humanitarian space and facilitating sub-agreements approvals and movement clearances. - Further advocacy is needed for funding the Shelter Cluster Common Pipeline. |
| 7. Promoting accountability to affected populations | 74%: Satisfactory (needs minor improvements) | Medium priority | - Strengthen partners’ capacity in the accountabilities to the affected population, including the complaints and feedback mechanism. - Finalize the cross-cutting issues focal points workplan and support them to put it in action. - Conduct a survey to reflect the opinions of the affected population in ensuring inclusivity and privacy | Q3 Q2 Q4 | SCT Cross-Cutting issues focal points SCT | - Strengthen the partner's capacity in ensuring the participation of the affected community in all project stages, including decision making, complaints, and feedback mechanisms. - Further considerations need to be given to people with specific needs and people with disability across the response cycle. - Explore areas to be strengthened in implementing the rights-based approach, community-based approach, and age, gender, and diversity approach. |