| Situation Report ¦ Cluster input form Palestine-Gaza ¦ Shelter¦ 26 08 2014 |  |
| --- | --- |

| Cluster | Shelter |
| --- | --- |
| Lead agency | Norwegian Refugee Council (NRC) |
| Agency focal point | Iyad Abu Hamam ( Mobile:059 7077233, e-mail: iyad.hamam@nrc.no) |
| Reporting period | 25-26 08 2014 |
| Report number | 38 |
| Information request sent on | 26 08 2014 |
| Completed form requested by | 26 08 2014 |
| OCHA focal point | Katleen Maes |

Key figures Damage levels (in # of housing units). Minor damage; Major damage; Severe damage; Destroyed. Classification of Damage; Windows and doors and small holes in external walls with cost of repair is less than USD 5,000; Damages are in part of the house and some parts stil inhabited and the estimated cost of repair is between USD 5,000 and USD 10,000; Damages are in essential parts of the house, un-inhabited until major work takes place. Cost between USD 10,000 and USD 20,000; Totally Destroyed or beyond repair houses, need demolition and reconstruction. Cost over USD 20,000. TOTAL (# of housing units); 38,000; 5,800; 8,000; 10,080. % of pre-crisis housing stock; 11.0%; 1.7%; 2.3%; 2.9%. # individuals; 228,000; 34,800; 48,000; 60,500. Reconstruction/Repair estimated cost (USD); $38,000,000; $46,400,000; $104,000,000; $403,200,000.

MPWH teams are in the process of collecting detailed lists of households who had their homes totally destroyed and severely damaged. The ministry started to provide each family (category 1: total destruction) with $1000 cash as rapid assistance donated by the Qatari Committee for reconstruction. About 2500 families have already received this amount. It was agreed that Joint assessment teams from UNRWA, UNDP, and MPWH will conduct detailed damage assessment for totally destroyed and severely damaged uninhabitable houses as soon as final ceasfire agreement is reached. In the same time UNRWA and UNDP teams will conduct detailed damage assessment for shelters having major and minor damage for refugee and non refuge families respectively. According to MPWH, the latest breakdown of totally destroyed and severely damaged housing units per governorate is shown below: As reported by UNRWA on (26 Aug 2014) more than 324,122 people are displaced at 85 UNRWA schools and 7 PA schools (Supplied with food and nonfood items by UNRWA) all over Gaza strip disaggregated per governorate as shown below: # schools; # IDPs. Gaza; 29; 76095. Khan Younes; 18; 58877. Middle; 8; 13394. North; 16; 85465. Rafah; 14; 55278. PA Schools run by UNRWA; 7; 35013. Total; 92; 324,122. 18 government schools in Gaza city are still open as temporary shelters for IDP’s from East and North Gaza. The following is a breakdown of these IDP shelters and their inhabitants as updated by MoSA (by 26 Aug): Location; # Families; # individuals. As'ad Saftawi School; 66; 400. Mosa Bin Nusseir School; 62; 370. Salah Eddin School; 128; 846. Abd El-Fattah Hmoud; 150; 1150. Fahmi Al-Jerjawi; 147; 811. Hamama School; 98; 564. Sheikh Radwan School; 114; 709. Al-Rafidin School; 159; 951. Al-Huda School; 111; 672. Al-Karmel School; 141; 1280. Hasan El-Basri School; 160; 819. Moustafa Hafez School; 131; 858. El-Amal Orphans Institute; 16; 124. Ahmad Showqi Secondary school for girls; 196; 1082. Al-Mawhobin boys Schools; 76; 500. Al-Mawhobin Girls Schools; 119; 753. Majeda Wasela; 180; 1100. Al-Buraq School; 147; 963. Total; 2201; 13952.

The total number of IDP’s at UNRWA and public IDP shelters has increased after the deterioration of security situation and the break of ceasefire. Figure below shows the number of registered IDP’s at UNRWA and Public shelters as of 26 Aug compared with the previous peak on 5 Aug statistics.

With the permanent ceasfire in place, the number of IDP’s will start to decrease to about 100,000 whose shelters are totally destroyed or un-inhabitable until further temporary shelter solutions are identified.

Humanitarian needs

Total estimated people in need of Shelter assistance: 514,604 108,500 individuals whose shelters were totally destroyed or sustained major structural damages need emergency NFI kit including mattresses, blankets, hygiene kit, kitchen set, etc, and in the medium term, they will need cash assistance to cover rental fees and basic household items. NFI emergency shelter repair interventions such as Nylon and tarpaulin are needed for about 5800 families (34,800) individuals whose houses suffered detructions but are still inhabited. About 228,000 individuals are living in slightly affected houses with broken windows and damaged doors, and need NFI assistance such as nylon and plastic sheets. However shelter partners considered this as second priority that will be dealt with at later stages after ceasfire and damage assessment conducted. 143,304 individuals internally displaced people registered and reached by various shelter actors.

Humanitarian response

|  |  |  | NFIs: household |  |  | NFIs: hygiene |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Living situation | # of individuals | # of households | Distributed (# households) | stocks in pipeline | Gap | Distributed (# households) | stocks in pipeline | Gap |
| Displaced: UNRWA collective centres | 324,122 | 54,020 | 43,255 | 0 | 10,765 | 70,140 | 0 | 11,899 |
| Displaced: MoSA collective centres | 13,952 | 2,325 | 3,084 | 0 | -759 | 4,188 | 0 | 14,064 |
| Displaced: other collective centres | 0 | 0 | 2,460 | 0 | -2,460 | 5,033 | 2,300 | -1,739 |
| Displaced: host-families | 140,895 | 23,483 | 8,773 | 0 | 14,710 | 16,942 | 1,000 | 21,462 |
| TOTAL | 478,969 | 79,828 | 57,572 | 0 | 22,256 | 96,303 | 3,300 | 45,686 |

For more details: See shelter NFI response and gap analysis section.

Gaps and constraints

Total estimated gap in [Shelter] (total needs minus total response): Emergency shelter kit (blankets, Mattresses, Kitchen Set, Hygeine kit, etc..) for 22,256 families. 45,686 Family hygiene kits for IDP’s at UNRWA and public shelters as well as hosted families. Cash assistance for 18,080 families to cover rental fees and urgent expenses (74,400,000$) Shlter NFIs (nylon and tarpaulin and/or assistance to replace broken glass and repair of damaged windows and doors) for 38,000 families (after ceasfire and damage assessment conducted) Although shelter cluster has been prepared for emergency situations, the lack of ceasefire and movement restrictions are the main constraints for the delivery of most urgent shelter/NFI assistance. The increased number of IDP’s resulted in too much overcrowding at UNRWA schools and a need to open more MoEHE schools. Additionally a lack of NFI’s is noticed as UNRWA stock is at minimum level now and they are procuring NFI’s daily. For UNRWA there are often difficulties accessing some of the NFI storage warehouses in Gaza such as Karni, as well as other shelter actors who lack safe access or movement inside the Gaza strip.

Coordination

- Shelter cluster is collecting information from shelter members who cooperate to verify and triangulate the information collected from at least three sources of information: MoSA, MPWH, ICRC and PRCS. the figures are based on field visits and etimations due to the current security situation which limits the movement of assessment teams and prevents conduting Joint IRA. All information is kept at shelter database and crosschecked to coordinate interventions of partners without duplications. All shelter partners are crosschecking their beneficiary lists on the consolidated shelter database which is created and maintained by NRC.

| Shelter NFI’s response and gap analysis |  |  |  | NFIs: household |  |  | NFIs: hygiene |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Area | Living situation | # of individuals | # of households | Distributed (# households) | stocks in pipeline | Gap | Distributed (# households) | stocks in pipeline | Gap |
| North_Gaza | Displaced: UNRWA collective centres | 120,478 | 20,080 | 14,617 | 0 | 5,463 | 27,659 | 0 | -7,579 |
|  | Displaced: MoSA collective centres |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Displaced: other collective centres |  | 0 | 224 | 0 | -224 | 527 | 0 | -527 |
|  | Displaced: host-families | 26,400 | 4,400 | 1,955 | 0 | 2,445 | 1,000 | 250 | 3,150 |
|  | Non-displaced: lightly damaged house |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: heavily damaged houses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: destroyed house |  | 0 |  |  |  |  |  |  |
|  | North Gaza sub-total | 146,878 | 24,480 | 16,796 | 0 | 7,684 | 29,186 | 250 | -4,956 |
| Gaza | Displaced: UNRWA collective centres | 76,095 | 12,683 | 17,836 | 0 | -5,154 | 19,802 | 0 | -7,120 |
|  | Displaced: MoSA collective centres | 13,952 | 2,325 | 3,084 | 0 | -759 | 4,188 | 0 | -1,863 |
|  | Displaced: other collective centres |  | 0 | 1,165 | 0 | -1,165 | 947 | 750 | -1,697 |
|  | Displaced: host-families | 78,300 | 13,050 | 3,063 | 0 | 9,987 | 8,932 | 250 | 3,868 |
|  | Non-displaced: lightly damaged house |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: heavily damaged houses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: destroyed house |  | 0 |  |  |  |  |  |  |
|  | Gaza sub-total | 168,347 | 28,058 | 25,148 | 0 | 2,910 | 33,869 | 1,000 | -6,811 |
| Dier_Al_Balah | Displaced: UNRWA collective centres | 13,394 | 2,232 | 4,883 | 0 | -2,651 | 3,191 | 0 | -959 |
|  | Displaced: MoSA collective centres |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Displaced: other collective centres |  | 0 | 260 | 0 | -260 | 806 | 500 | -1,306 |
|  | Displaced: host-families | 3,023 | 504 | 1,111 | 0 | -607 | 1,479 | 0 | -975 |
|  | Non-displaced: lightly damaged house |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: heavily damaged houses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: destroyed house |  | 0 |  |  |  |  |  |  |
|  | Dier Al Balah sub-total | 16,417 | 2,736 | 6,254 | 0 | -3,518 | 5,476 | 500 | -3,240 |
| Khan_Younis | Displaced: UNRWA collective centres | 58,877 | 9,813 | 1,097 | 0 | 8,716 | 7,700 | 0 | 2,113 |
|  | Displaced: MoSA collective centres | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Displaced: other collective centres |  | 0 | 570 | 0 | -570 | 1,669 | 600 | -2,269 |
|  | Displaced: host-families | 24,398 | 4,066 | 1,707 | 0 | 2,359 | 4,589 | 250 | -773 |
|  | Non-displaced: lightly damaged house |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: heavily damaged houses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: destroyed house |  | 0 |  |  |  |  |  |  |
|  | Khan Younis sub-total | 83,275 | 13,879 | 3,374 | 0 | 10,505 | 13,958 | 850 | -929 |
| Rafah | Displaced: UNRWA collective centres | 55,278 | 9,213 | 4,822 | 0 | 4,391 | 11,788 | 0 | -2,575 |
|  | Displaced: MoSA collective centres |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Displaced: other collective centres |  | 0 | 241 | 0 | -241 | 1,084 | 450 | -1,534 |
|  | Displaced: host-families | 11,183 | 1,864 | 937 | 0 | 927 | 942 | 250 | 672 |
|  | Non-displaced: lightly damaged house |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: heavily damaged houses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Non-displaced: destroyed house |  | 0 |  |  |  |  |  |  |
|  | Rafah sub-total | 66,461 | 11,077 | 6,000 | 0 | 5,077 | 13,814 | 700 | -3,437 |
|  | TOTAL | 481,378 | 80,230 | 57,572 | 0 | 22,658 | 96,303 | 3,300 | 46,088 |

| Activity by agency |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Report of activities by agency by Governorate |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | NFIs: household |  |  |  |  |  |  |  |  | NFIs: hygiene |  |  |  |  |  |  |  |
| Agency |  | North_Gaza | Gaza | Dier_Al_Balah | Khan_Younis | Rafah | TOTAL |  | Comments |  | North_Gaza |  | Gaza | Dier_Al_Balah | Khan_Younis | Rafah | TOTAL | Comments |
| ANERA |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3,341 |  | 8,701 | 0 | 0 | 0 | 12,042 | Including 24 lit of drinking water per kit |
| CARE |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |
| CRS |  | 466 | 948 | 457 | 728 | 400 | 2,999 |  |  |  | 1,000 |  | 1,400 | 1,000 | 1,000 | 600 | 5,000 |  |
| GC/CHF |  | 1,220 | 250 | 0 | 0 | 0 | 1,470 |  |  |  | 5,000 |  | 0 | 0 | 0 | 0 | 5,000 |  |
| HelpAge |  | 560 | 558 | 560 | 560 | 651 | 2,889 |  |  |  | 224 |  | 279 | 280 | 280 | 186 | 1,249 |  |
| IOCC |  | 0 | 260 | 0 | 0 | 0 | 260 |  |  |  | 0 |  | 260 | 0 | 0 | 0 | 260 |  |
| IR-Pal |  | 0 | 500 | 0 | 0 | 0 | 500 |  |  |  | 0 |  | 250 | 0 | 0 | 0 | 250 |  |
| Maan Center |  | 0 | 125 | 0 | 125 | 0 | 250 |  | 4 mattresses and 4 blanket per kit |  | 0 |  | 531 | 0 | 719 | 400 | 1,650 |  |
| MAP |  | 0 | 50 | 50 | 25 | 25 | 150 |  | 4 mattresses and 4 blanket per kit |  | 0 |  | 351 | 366 | 450 | 198 | 1,365 |  |
| Mercy Corps |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7,020 |  | 9,702 | 0 | 2,841 | 6,928 | 26,491 |  |
| MoSA |  | 213 | 533 | 105 | 191 | 115 | 1,157 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |
| NRC |  | 0 | 300 | 0 | 0 | 0 | 300 |  |  |  | 0 |  | 300 | 0 | 0 | 0 | 300 |  |
| PRCS |  | 0 | 3,846 | 0 | 0 | 0 | 3,846 |  |  |  | 300 |  | 3,763 | 300 | 300 | 300 | 4,963 |  |
| PU-AMI |  | 0 | 0 | 339 | 748 | 342 | 1,429 |  |  |  | 0 |  | 0 | 339 | 748 | 342 | 1,429 |  |
| SCI |  | 0 | 75 | 0 | 20 | 110 | 205 |  |  |  | 115 |  | 300 | 0 | 0 | 0 | 415 |  |
| SIF-PAL |  | 0 | 1,000 | 0 | 0 | 0 | 1,000 |  |  |  | 0 |  | 1,000 | 0 | 0 | 0 | 1,000 |  |
| UNICEF |  | 0 | 592 | 0 | 0 | 0 | 592 |  | Though PRCS |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Through PRCS |
| UNRWA |  | 14,337 | 16,111 | 4,743 | 977 | 4,357 | 40,525 |  |  |  | 12,186 |  | 7,032 | 3,191 | 7,620 | 4,860 | 34,889 |  |
|  |  | 16,796 | 25,148 | 6,254 | 3,374 | 6,000 | 57,572 |  |  |  | 29,186 |  | 33,869 | 5,476 | 13,958 | 13,814 | 96,303 |  |
| National Shelter Cluster focal point |  |  |  |  |  |  |  |  |  |  | Gaza Shelter Cluster focal point |  |  |  |  |  |  |  |
| Coordinator: Fadi Shamisti, NRC Jerusalem, email: fadi.shamisti@nrc.no, telephone: 054 666 3902 |  |  |  |  |  |  |  |  |  |  | Coordinator: Iyad Abu Hamam, NRC Gaza, email: iyad.hamam@nrc.no, telephone: 059 707 7233 |  |  |  |  |  |  |  |
| Date : 26/Aug/14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |