## 4Ws
28/10/2014 | Shelter/NFI 4 Ws - COMPLEMENTARY SHELTER INTERVENTIONS
WHO |  | WHAT | WHERE |  |  |  | WHEN |  |  | TARGET
Organization Name | Type | Activity | Governorates | Areas Name | Shelters Names | Type of beneficiaries | Status | Activity Start Date | Activity Completion Date | Number of Planned HH | Number of HH Reached | Number of Planned Indivdulas | Number of Individulas Reached
Médecins du Monde | INGOs | hygiene Kit (Family) | Middle | Al Mugraqa (Juher ad Dik) |  |  | Planned | September 10th | October 9th | 670 |  | 5000
Médecins du Monde | INGOs | hygiene Kit (Family) | Khan Younis | Khuza'a |  |  | Submitted / Unfunded | October 9th | November 20th | 2500 |  | 15000
Médecins du Monde | INGOs | hygiene Kit (Family) | Khan Younis | Al Fukhari |  |  | Submitted / Unfunded | October 9th | November 20th | 1166 |  | 7000
Mercy Corps | INGOs | hygiene Kit (Family) | Gaza | Gaza | None | IDPS in Hosted Families and Informal shelters | Completed | 2014-07-19 |  |  | 760 |  | 5320
Mercy Corps | INGOs | hygiene Kit (Family) | North |  |  | IDPs UNRWA Shelter | Completed | 2014-07-31 |  |  | 7020 |  | 49140
Mercy Corps | INGOs | hygiene Kit (Family) | Gaza | Jabalia | Jabalia Prep Girls A, B, and C Schools and Jabalia Elementary Coed | IDPs UNRWA Shelter | Completed | 2014-07-19 |  |  | 1073 |  | 7511
Mercy Corps | INGOs | Plastic Sheets (Nylon) |  |  |  |  | Planned |  |  | 10080 |  | 70560
Mercy Corps | INGOs | hygiene Kit (Family) | Gaza | Gaza | 4 Public Schools in Al Rimal Area | IDPs MoE Shelter | Completed | 2014-07-31 | 2014-08-04 |  | 407 |  | 3660
Mercy Corps | INGOs | hygiene Kit (Family) | Gaza | Gaza | 4 public schools in Sheik Redwan and Al Daraj Area | IDPs MoE Shelter | Ongoing | 2014-08-03 |  | 116 | 164 | 812 | 1312
Mercy Corps | INGOs | hygiene Kit (Family) | Gaza |  |  | IDPs UNRWA Shelter | Completed | 2014-07-31 | 2014-07-31 |  | 1000 |  | 7000
Mercy Corps | INGOs | hygiene Kit (Family) | Gaza |  |  | IDPs UNRWA Shelter | Ongoing | 2014-08-07 |  | 1015 | 1015 | 8120 | 8120
Mercy Corps | INGOs | hygiene Kit (Family) | Khan Younis | Khuza'a |  | IDPs Hosted Families | Completed | 2014-08-12 |  | 2000 | 2000 | 16000 | 16000
Mercy Corps | INGOs | hygiene Kit (Family) | Rafah | Rafah |  | IDPs UNRWA Shelter | Ongoing |  |  | 19852 | 6928 | 158816 | 55424
Mercy Corps | INGOs | hygiene Kit (Family) | Gaza |  |  |  | Ongoing | 2014-08-17 |  | 4649 | 4649 | 37192 | 37192
Mercy Corps | INGOs | hygiene Kit (Family) | Middle | Dier Al Balah |  |  | Ongoing | 2014-08-18 |  | 700 | 700 | 5600 | 5600
Mercy Corps | INGOs | hygiene Kit (Family) | Khan Younis | Bani Suhaila |  |  | Ongoing | 2014-08-18 |  | 600 | 1247 | 4800 | 9976
DanChurchAid | INGOs | Hygiene kits | North Gaza | Jabalia Camp | Private/ informal shelters/ hosted families | IDPS in Hosted Families and Informal shelters | Completed | 2014-08-02 | 2014-08-05 | 700 | 1029 | 4060 | 7225
DanChurchAid | INGOs | Hygiene kits | Gaza | Gaza City (Sheikh Redwan, Al Sabra and Sheja'eya) | Private/ informal shelters/ hosted families | IDPS in Hosted Families and Informal shelters | Completed | 2014-08-02 | 2014-08-05 | 1100 | 1100 | 6380 | 7788
DanChurchAid | INGOs | Diapers for PWD's | North Gaza | Bet Hanoun, Jabalia and Bet Lahya | Private/ informal shelters/ hosted families | PWD's | Completed | 2014-08-02 | 2014-08-05 | 300 | 462 | 300 | 462
DanChurchAid | INGOs | Hygiene kits | Rafah | Tal Sultan | Private/ informal shelters/ hosted families | IDPS in Hosted Families and Informal shelters | Completed | 2014-08-09 | 2014-08-13 | 800 | 744 | 4640 | 4523
DanChurchAid | INGOs | Hygiene kits | Khanyounis | Khanyounis Camp | Private/ informal shelters/ hosted families | IDPS in Hosted Families and Informal shelters | Completed | 2014-08-09 | 2014-08-13 | 1500 | 1500 | 8700 | 9168
DanChurchAid | INGOs | Hygiene kits | Der Al Balah | Der Al Balah | Private/ informal shelters/ hosted families | IDPS in Hosted Families and Informal shelters | Completed | 2014-08-09 | 2014-08-13 | 500 | 423 | 2900 | 1834
DanChurchAid | INGOs | Hygiene kits | Gaza | Gaza City | Private/ informal shelters/ hosted families | IDPS in Hosted Families and Informal shelters | Completed | 2014-08-09 | 2014-08-13 | 460 | 502 | 2668 | 3584
DanChurchAid | INGOs | Hygiene kits | North Gaza | Jabalia Camp | Private/ informal shelters/ hosted families | IDPS in Hosted Families and Informal shelters | Completed | 2014-08-09 | 2014-08-13 | 380 | 689 | 2204 | 3643
DanChurchAid | INGOs | School uniform, bags and stationary | North Gaza | Bet Hanoun | Private/ informal shelters/ hosted families/UNRWA shelters | Displaced students in primary schools | Planned | 15/9/2014 | 14/10/2014 | 4100 |  | 4100
DanChurchAid | INGOs | Unconditional cash (200USD) | Gaza Strip | Gaza Strip | Private/ informal shelters/ hosted families/UNRWA shelters | Displaced people who have lost their homes with recognized need to the project identified aid. | Planned | 15/9/2014 | 31/12/2014 | 1340 |  | 7772
DanChurchAid | INGOs | Hygiene promotion and kits |  |  |  | Families of malnurished children | Planned
Economic & Social Development Center of Palestine | National NGOs/ CBOs | Full NFI Family kit (Standard) | Khan Younis | Abasan al Kabira | 1- Ibn Khaldun Primary School 2- Al Amal Primary School 3- Al Horany Preparatory School 4- Al Hinawi Primary School 5- Haeeat Primary and Preparatory School 6- Shikh Jamil Primary School | IDPs UNRWA Shelter | Ongoing | 15-08-2014 | 29-09-2014 | 300 | Ongoing | 1800 | Ongoing | IDPs UNRWA Shelter are went to rented houses
Save The Children | INGO | Distribution of 750 HHs kits include (250 Mattresses, 250 Pillows and 250 Blankets) | Gaza | Gaza | Holy Family shelter School | IDPs | Done | 2014-07-22 | 2014-07-22 | 250 | 250 | NA | 900 person include 120 child under 2 years.
Save The Children | INGO | Distribution of 500 Baby Hygiene Kits - By Beit Lahia Development Association | North Gaza | Beit Hanoun, Beit Lahia and Jabalia | Families outside shelters | IDPs | Done | 2014-08-06 | 2014-08-28 | 500 | 404 | NA | Complete list of Beneficiaries have been forwarded to Shelter Cluster
Save The Children | INGO | Distribution of 750 Baby Hygiene Kits - By Save Youth Future Society | Gaza | Gaza | Families outside shelters | IDPs | Done | 2014-08-04 | 2014-08-25 | 750 | 700 | NA | We need complete list of Beneficiaries
Save The Children | INGO | Distribution of 400 Baby Hygiene Kits - By Al Karmel Association | Middle Area | Middle Area | Families outside shelters | IDPs | Done | 2014-08-05 | 2014-08-27 | 400 | 200 | NA | We need complete list of Beneficiaries
Save The Children | INGO | Distribution of 500 Baby Hygiene Kits - By Bayader | South | Khanyounis | Families outside shelters | IDPs | Done | 2014-08-14 | 2014-08-28 | 500 | 250 | NA | We need complete list of Beneficiaries
Save The Children | INGO | Distribution of 350 Baby Hygiene Kits - By Yaboos Charity | South | Rafah | Families outside shelters | IDPs | Done | 2014-08-15 | 2014-08-26 | 350 | 175 | NA | We need complete list of Beneficiaries
Save The Children | INGO | Distribution of 115 Family Hygiene Kits - By Beit Lahia Development Association | North Gaza | Beit Hanoun, Beit Lahia and Jabalia | Families outside shelters | IDPs | Done | [5 empty] | Most affected areas (access restricted areas)
Save The Children | INGO | Distribution of 300 Family Hygiene Kits - By Save Youth Future | Gaza | Gaza | IDPs at school shelters ( Hamamah, Al Huda, Al Rafedyn and Shuhadaa Al Redwan Schools) | IDPs | Done | 2014-08-05 | 2014-08-05 | 300 | 300
Save The Children | INGO | Distribution of 100 Family Hygiene Kits - By Al Karmel Association | Middle Area | Middle Area | Families outside shelters | IDPs | Done
Save The Children | INGO | Distribution of 100 Family Hygiene Kits - By Bayader | South | Khanyounis | Families outside shelters | IDPs | Done
Save The Children | INGO | Distribution of 100 Family Hygiene Kits - By Yaboos Charity | South | Rafah | Families outside shelters | IDPs | Done
Save The Children | INGO | MEF for Bayader - Distribution Of 20 HHs NFI Packages (Blankets, Mattresses and kitchen set). | South | Khanyounis | Families outside shelters | IDPs | Done
Save The Children | INGO | MEF for Yaboos Charity - Distribution Of 30 NFI Packages (Kitchen Kits, First Aid Kits and Electric Flash light). | South | Rafah | Families outside shelters / Totally destroyed homes | IDPs | Done | 2014-08-09 | 2014-08-12 | 30 | 30 | NA | We need complete list of Beneficiaries
Save The Children | INGO | MEF for Yaboos Charity - Distribution Of 80 NFI Packages (Kitchen Kits). | South | Rafah | Shelters & Hosted families for the IDPs | IDPs | Done | 2014-08-09 | 2014-08-12 | 80 | 80 | 800 | We need complete list of Beneficiaries
Save The Children | INGO | MEF for Al Karmel Association - Distribution Of 250 Toys & 250 Flashlight | Middle Area | Middle Area | Families outside shelters | IDPs | Done | 2014-08-28 | 2014-09-04
Save The Children | INGO | Distribution of 600 Family Hygiene Kits - By Yaboos Charity | Rafah | Rafah | Families outside shelters |  | Done | 2014-08-18 | 2014-09-04 |  |  |  | Will be provided to shelter
Save The Children | INGO | Distribution of 900 Family Hygiene Kits - By Save Youth Future | Gaza | Gaza | Families outside shelters |  | Done | 2014-08-20 | 2014-09-04 |  |  |  | Will be provided to shelter
Save The Children | INGO | Distribution of 600 Family Hygiene Kits - By Beit Lahia Development Association | North Gaza | North Gaza | Families outside shelters |  | Done | 2014-08-24 | 2014-09-04 |  |  |  | Will be provided to shelter
Save The Children | INGO | Distribution of 400 Family Hygiene Kits - By Al Karmel Association | Middle Area | Middle Area | Families outside shelters |  | Done | 2014-08-17 | 2014-09-04 |  |  |  | Will be provided to shelter
Global Communities/CHF | INGOs | hygiene Kit (Family) |  |  |  |  | Planned | 2014-12-10 | 31/10/2014 | 9000
PRCS-ICRC | INGOs | PRCS-ICRChouse destruction relief kits; PRCS-ICRC Hygiene Kit Content PRCS-ICRC Food Parcel - Gaza 2014 | East Salah -Al-Din Road | Targeted locations: Whole area East of Salah-al-Din road (most heavily affected area) Areas included: North Gaza governorate - Beit Hanoun Gaza governorate - Shijai'ya / Shijai'ya Toffah / Shijai'ya Zaitoun Deir-al-Balah governorate - Joher al Deek / Wadi Salqa (Abo Ajeen) / East of Burage / East of Maghazi / Al Mossader Khan Younis governorate - Khosa'a / Zana / Qarara / Abasan al Kabira / Abasan al Jadida / Fokhari / Bani Sohayla Rafah governorate - Shoka | Families outside shelters |  | Done |  | 20/10/2014 | 24000 | 14000

## GAPS
Shelter/NFI 4 Ws - COMPLEMENTARY SHELTER INTERVENTIONS
WHAT | WHERE |  |  | WHEN |  | TARGET |  | NOTES
Activity | Governorates | Areas Name | Shelters Names | Suggested Start Date | End of coverarge Date | Number of Beneficaries | Type of benficiaries | Focal points, coordination…

## WHO (hidden)
List of Types of Organizations
GOVERNMENT
INGOs
National NGOs/ CBOs
UN AGENCIES

## WHAT (hidden)
List of Activities
blankets
Mattresses
Kitchen set
hygiene Kit (baby)
hygiene Kit (Family)
Mats
Gas Stoves
Plastic Sheets (Nylon)
Tarpaulin Sheets
heaters
Searchlight
Tents
Sleeping Bags
Clothes
School bags
Full NFI Family kit (Standard)

## Sheet4 (hidden)
Completed
Funding
Ongoing
Submitted / Unfunded
Suspended

## WHEN (hidden)
Status of Activity
Ongoing
Completed
Funded
Submitted / Unfunded
Suspended
Planned

## WHERE (hidden)
North Gaza
Gaza
Dier Al Balah
Khan Younis
Rafah
| Governorate | Area/ Locality
| North Gaza | Al Qaraya al Badawiya (Umm An-Naser)
Beit Lahiya
Beit Hanoun
Jabalia Camp
Jabalia
| Gaza Governorate | Gaza
Ash Shati Camp
Gaza
Madinat Az Zahra
Al Mugraqa (Juher ad Dik)
| Dier Al Balah Governorate | An Nuseriat Camp
An Nuseriat
Al Bureji
Az Zawayda
Dier Al Balah Camp
Al Maghazi
Dier Al Balah
Al Musaddar
Wadi as Salqa
| Khan Younis Governorate | Khan Younis Camp
Khan Younis
Bani Suhaila
Abasan al Jadida (as Saghira)
Abasan al Kabira
Khuza'a
Al Fukhari
| Rafah Governorate | Rafah
Rafah Camp
Al -Naser (Al Bayuk)
Shuka
Tal Sultan
Governorate
North
Gaza
Middle
Khan Younis
Rafah
Area/ Locality
Al Qaraya al Badawiya (Umm An-Naser)
Beit Lahiya
Beit Hanoun
Jabalia Camp
Jabalia
Gaza
Ash Shati Camp
Gaza
Madinat Az Zahra
Al Mugraqa (Juher ad Dik)
An Nuseriat Camp
An Nuseriat
Al Bureji
Az Zawayda
Dier Al Balah Camp
Al Maghazi
Dier Al Balah
Al Musaddar
Wadi as Salqa
Khan Younis Camp
Khan Younis
Bani Suhaila
Abasan al Jadida (as Saghira)
Abasan al Kabira
Khuza'a
Al Fukhari
Rafah
Rafah Camp
Al -Naser (Al Bayuk)
Shuka
Tal Sultan

## TYPE OF AFFECTED POPOULATION (hidden)
TYPE
IDPs UNRWA Shelter
IDPs MoE Shelter
IDPs Hosted Families
IDPs Private Shelter
Patients and Hospital Staff
IDPS in Hosted Families and Informal shelters
Poor Families