## Shelter Summary
SENDONG 2012 SHELTER CLUSTER: SUMMARY OF SHELTER NEED AND RESPONSE BY LOCATION
2012-01-12
PROVINCE | MUNICIPALITY | NUMBER OF DAMAGE HOUSES* |  |  | FAMILIES IN EVACUATION CENTRES** | TEMPORARY SHELTER / FAMILY
|  | TOTAL | TOTALLY | PARTIALLY |  | TENTS | TENT PLANNED | TEMPORARY SHELTER | TEMPORARY SHLETER PLANNED
Lanao del Norte | Iligan City | 20120 | 5246 | 14874 | 4298 | 155 | 250 | 0 | 0
Misamis Oriental | Cagayan de Oro City | 18436 | 5801 | 12635 | 2816 | 674 | 280 | 0 | 750
Unspecified | Unspecified |  |  |  | 0 | 63 | 1633 | 0 | 100
TOTAL | TOTAL | 38556 | 11047 | 27509 | 7114 | 892 | 2163 | 0 | 850
PROVINCE | MUNICIPALITY | NUMBER OF DAMAGE HOUSES* |  |  | REHABILITATION / HOUSE
|  | TOTAL | TOTALLY | PARTIALLY | SHELTER KIT | SHELTER KIT PLANNED | VOUCHER/ CASH | VOUCHER PLANNED | TOTAL | PROJECTED COVERAGE
Lanao del Norte | Iligan City | 20120 | 5246 | 14874 | 0 | 710 | 0 | 500 | 1210 | 8.135%
Misamis Oriental | Cagayan de Oro City | 18436 | 5801 | 12635 | 0 | 750 | 0 | 500 | 1250 | 9.893%
Unspecified | Unspecified |  |  |  | 0 | 6699 | 0 | 0 | 6699
TOTAL | TOTAL | 38556 | 11047 | 27509 | 0 | 8159 | 0 | 1000 | 9159 | 33.29%
PROVINCE | MUNICIPALITY | NUMBER OF DAMAGE HOUSES* |  |  | CONSTRUCTION / HOUSE
|  | TOTAL | TOTALLY | PARTIALLY | SEMI-PERMANENT SHELTER | SEMI-PERMANET PLANNED | PERMANENT HOUSING | PERMANENT PLANNED | TOTAL | PROJECTED COVERAGE
Lanao del Norte | Iligan City | 20120 | 5246 | 14874 | 0 | 1000 | 0 | 1000 | 2000 | 38.12%
Misamis Oriental | Cagayan de Oro City | 18436 | 5801 | 12635 | 0 | 1600 | 0 | 5844 | 7444 | 128.3%
Unspecified | Unspecified |  |  |  | 0 | 0 | 0 | 2450 | 2450
TOTAL | TOTAL | 38556 | 11047 | 27509 | 0 | 2600 | 0 | 9294 | 11894 | 107.7%
NOTE: Need for permanent housing is expected to increase due to no-build zones
* Updates from DSWD as of 11 January 2012
** Source: DTM Snapshot, dated 9 Januaury 2012, assuming all families in ECs have damaged houses

## Agency Summary
SENDONG 2012 SHELTER CLUSTER: SUMMARY OF SHELTER NEED AND RESPONSE BY AGENCY
2012-01-12
| TEMPORARY SHELTER |  |  |  | REHABILITATION |  |  |  | CONSTRUCTION
IMPLEMENTING ORGANISATION | TENTS | TENT PLANNED | TEMPORARY SHELTER | T-SHLETER PLANNED | SHELTER KIT | SHELTER KIT PLANNED | VOUCHER/ CASH | VOUCHER PLANNED | SEMI-PERMANENT SHELTER | SEMI-PERMANET PLANNED | PERMANENT HOUSING | PERMANENT PLANNED
Values
Implementing Organisation | Tent Distributed | Tent Planned | Sum of TEMPORARY SHELTER | Sum of T-SHLETER PIPELINE | Shelter Kit Distributed | ShelterKit_Planned | Voucher Support | Voucher_Planned | Semi-Permanent Built | Semi_Planned | Permenent Built | Permanent_Planned
CRS |  |  |  | 400 | [5 empty] | 600
DepEd | 63
Disaster Aid Internation |  | 100
DOE | 38
DSWD |  | 530 |  | 150
FFCCCII | [11 empty] | 600
Habitat for Humanity Philippines | [5 empty] | 2119 | [5 empty] | 6844
IOM |  |  |  | 200 |  | 5040
Kapuso Foundation | [11 empty] | 200
Oro Habitat | [11 empty] | 150
Plan International | 152 | 248
PRC | 150 | 200 |  |  |  | 1000 |  | 1000 |  | 2000
Shelter Box | 489 | 1085
Xavier University | [11 empty] | 500
Grand Total | 892 | 2163 |  | 750 |  | 8159 |  | 1000 |  | 2600 |  | 8294