## Shelter Summary
SENDONG 2012 SHELTER CLUSTER: SUMMARY OF SHELTER NEED AND RESPONSE BY LOCATION
2012-01-15
PROVINCE | MUNICIPALITY | NUMBER OF DAMAGE HOUSES* |  |  | FAMILIES IN EVACUATION CENTRES** | FAMILIES WITH HOST FAMILIES | TEMPORARY SHELTER SUPPORT / FAMILY
|  | TOTAL | TOTALLY | PARTIALLY |  |  | TENTS | TENT PLANNED | TEMPORARY SHELTER | TEMPORARY SHLETER PLANNED
Lanao del Norte | Iligan City | 20120 | 5246 | 14874 | 4298 |  | 155 | 250 | 0 | 0
Misamis Oriental | Cagayan de Oro City | 18436 | 5801 | 12635 | 2816 |  | 674 | 280 | 0 | 780
Unspecified | Unspecified | [5 empty] | 63 | 1633 | 0 | 100
TOTAL | TOTAL | 38556 | 11047 | 27509 | 7114 | 0 | 892 | 2163 | 0 | 880
PROVINCE | MUNICIPALITY | NUMBER OF DAMAGE HOUSES* |  |  | REHABILITATION SUPPORT / FAMILY
|  | TOTAL | TOTALLY | PARTIALLY | SHELTER KIT | SHELTER KIT PLANNED | VOUCHER/ CASH | VOUCHER PLANNED | TOTAL | PROJECTED COVERAGE
Lanao del Norte | Iligan City | 20120 | 5246 | 14874 | 136 | 1760 | 0 | 500 | 2396 | 16.11%
Misamis Oriental | Cagayan de Oro City | 18436 | 5801 | 12635 | 356 | 1869 | 0 | 500 | 2725 | 21.57%
Unspecified | Unspecified |  |  |  | 0 | 1699 | 0 | 0 | 1699
TOTAL | TOTAL | 38556 | 11047 | 27509 | 492 | 5328 | 0 | 1000 | 6820 | 24.79%
PROVINCE | MUNICIPALITY | NUMBER OF DAMAGE HOUSES* |  |  | RECONSTRUCTION SUPPORT / FAMILY
|  | TOTAL | TOTALLY | PARTIALLY | SEMI-PERMANENT SHELTER | SEMI-PERMANET PLANNED | PERMANENT HOUSING | PERMANENT PLANNED | TOTAL | PROJECTED COVERAGE
Lanao del Norte | Iligan City | 20120 | 5246 | 14874 | 0 | 1000 | 0 | 1000 | 2000 | 38.12%
Misamis Oriental | Cagayan de Oro City | 18436 | 5801 | 12635 | 0 | 1600 | 0 | 5844 | 7444 | 128.3%
Unspecified | Unspecified |  |  |  | 0 | 0 | 0 | 2450 | 2450
TOTAL | TOTAL | 38556 | 11047 | 27509 | 0 | 2600 | 0 | 9294 | 11894 | 107.7%
NOTE: Need for permanent housing is expected to increase due to no-build zones
* Updates from DSWD as of 11 January 2012
** Source: DTM Snapshot, dated 9 Januaury 2012, assuming all families in ECs have damaged houses

## Agency Summary
SENDONG 2012 SHELTER CLUSTER: SUMMARY OF SHELTER RESPONSE BY AGENCY
2012-01-15
| TEMPORARY SHELTER |  |  |  | REHABILITATION |  |  |  | RECONSTRUCTION
IMPLEMENTING ORGANISATION | TENTS | TENT PLANNED | TEMPORARY SHELTER | T-SHLETER PLANNED | SHELTER KIT | SHELTER KIT PLANNED | VOUCHER/ CASH | VOUCHER PLANNED | SEMI-PERMANENT SHELTER | SEMI-PERMANET PLANNED | PERMANENT HOUSING | PERMANENT PLANNED
Values
Implementing Organisation | Tent Distributed | Tent Planned | Sum of TEMPORARY SHELTER | Sum of T-SHLETER PIPELINE | Shelter Kit Distributed | ShelterKit_Planned | Voucher Support | Voucher_Planned | Semi-Permanent Built | Semi_Planned | Permenent Built | Permanent_Planned
CRS |  |  |  | 400 | [5 empty] | 600
DepEd | 63
Disaster Aid Internation |  | 100
DOE | 38
DSWD |  | 530 |  | 150
FFCCCII | [11 empty] | 600
Habitat for Humanity Philippines | [5 empty] | 2119 | [5 empty] | 6844
IOM |  |  |  | 230 | 492 | 2209
Kapuso Foundation | [11 empty] | 200
Oro Habitat | [11 empty] | 150
Plan International | 152 | 248
PRC | 150 | 200 |  |  |  | 1000 |  | 1000 |  | 2000
Shelter Box | 489 | 1085
Xavier University | [11 empty] | 500
Grand Total | 892 | 2163 |  | 780 | 492 | 5328 |  | 1000 |  | 2600 |  | 8294

## 3W
SENDONG 2012 SHELTER CLUSTER: 3W
2012-01-15
|  |  |  | TEMPORARY SHELTER |  |  |  | REHABILITATION |  |  |  | RECONSTRUCTION
Values
MUNICIPALITY | BARANGAY | Admin 4 Pcode | Implementing Organisation | Tent Distributed | Tent Planned | Temporary Shelters | T-Shelter Planned | Shelter Kits | Shelter Kits Planned | Voucher Support | Voucher Planned | Semi-Permanent Built | Semi-permanent Planned | Permenent Built | Permanent Planned
CAGAYAN DE ORO CITY | BULUA | 104305003 | IOM | [5 empty] | 411
| CANITO-AN | 104305043 | Habitat for Humanity Philippines | [11 empty] | 2948
|  |  | IOM |  |  |  |  | 91 | 509
|  |  | Shelter Box | 366 | 200
| CARMEN | 104207003 | Plan International | 40
| IPONAN | 104305051 | IOM |  |  |  |  | 265 | 239
|  |  | Shelter Box |  | 40
| LUMBIA | 104305054 | DSWD |  |  |  | 150
|  |  | IOM |  |  |  | 230
|  |  | PRC | 150
| MACASANDIG | 104305056 | CRS |  |  |  | 400 | [5 empty] | 600
|  |  | Plan International | 80
|  |  | Shelter Box |  | 40
| (blank) | #N/A | DOE | 38
|  |  | Habitat for Humanity Philippines | [5 empty] | 210 | [5 empty] | 2896
|  |  | PRC | [5 empty] | 500 |  | 500 |  | 1000
HINATUAN | (blank) | #N/A | Habitat for Humanity Philippines | [5 empty] | 971
ILIGAN CITY | DIGKILAAN | 103504007 | IOM | [5 empty] | 200
| HINAPLANON | 103504008 | IOM | [5 empty] | 360
|  |  | Shelter Box | 123
| MANDULOG | 103504014 | Habitat for Humanity Philippines | [11 empty] | 1000
| SANTIAGO | 101314020 | IOM |  |  |  |  | 65 | 490
| TAMBACAN | 103504025 | Plan International | 32
| TUBOD | 101803013 | IOM |  |  |  |  | 71 | 0
| (blank) | #N/A | Habitat for Humanity Philippines | [5 empty] | 210
|  |  | PRC | [5 empty] | 500 |  | 500 |  | 1000
|  |  | Shelter Box |  | 250
(blank) | (blank) | #N/A | DepEd | 63
|  |  | Disaster Aid Internation |  | 100
|  |  | DSWD |  | 530
|  |  | FFCCCII | [11 empty] | 600
|  |  | Habitat for Humanity Philippines | [5 empty] | 728
|  |  | Kapuso Foundation | [11 empty] | 200
|  |  | Oro Habitat | [11 empty] | 150
|  |  | Plan International |  | 248
|  |  | PRC |  | 200
|  |  | Shelter Box |  | 555
|  |  | Xavier University | [11 empty] | 500
Grand Total |  |  |  | 892 | 2163 |  | 780 | 492 | 5328 |  | 1000 |  | 2600 |  | 8294